## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Batter Hinge Extender | itp |  |  |  |  | ITP - Batter Hinge Extender Rev 0
section | 1.0. Aggregate Acceptance Testing
checkpoint | 1.01 - NZTA M04
label | Detail of Activity / Test - Crushing Resistance
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
label | Inspection / Test method - NZS4407:2.4.7
label | Acceptance Criteria - > 130KN
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - NZTA M04
label | Detail of Activity / Test - Particle size distribution
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
label | Inspection / Test method - NZS4407:2.4.7
label | Acceptance Criteria - As per NZTA M04 Specfication
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
section | 2.0. Construction
checkpoint | 2.01 - Mark out earthwork extents
label | Detail of Activity / Test - Set out and approve extent of earthworks
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to earthworks
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - QA/Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.02 - Earthworks
label | Detail of Activity / Test - Excavate to a depth required in the design drawing
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where hinge extender is required
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - QA/Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Photo
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.03 - Post Installation
label | Detail of Activity / Test - EZY-Guard LDS Z-Post 2000mm long at 1.0m C/C spacing or NU-Guard High Tensile Posts 1900mm at 1.0m C/C spacing
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where hinge extender is required
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - As Per Design Drawing
label | Record documents (QCP - Quality Control Portal) - Photo
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.04 - Timber Board Installation
label | Detail of Activity / Test - Install 2 to 3 No. 250mm X 50mm H5 Timber Boards fixed with galvanised M12 bolt and square washers
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where shoulder support is required
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - As Per Design Drawing
label | Record documents (QCP - Quality Control Portal) - Photo
label | Responsibility - Contractor
label | Project Specific Notes / Instructions - To Ensure a minimum of 150mm of the bottom timber board buried in the embankment
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.05 - AP40 Placement
label | Detail of Activity / Test - Backfill and compact using M4 AP40
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Test Every 10m
label | Inspection / Test method - Clegg
label | Acceptance Criteria - Clegg Results >30
label | Record documents (QCP - Quality Control Portal) - Checksheet/Photo
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature