## struct
resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
| step |  |  | Tier 1: Civils
| step |  |  | Tier 2: MRP-DPK-102-00-CFN-0010
| step |  |  | Tier 3: Kerb & Channel South of Rail Ferris Rd
| step |  |  | Tier 4: 103-493 - South of Rail - Ferris Rd - Kerb and Channel Installation SM2
| step |  |  | Tier 4: 103-494 - South of Rail - Ferris Rd - Kerb and Channel Installation SM3
| step |  |  | Tier 3: Kerb & Channel Enterprise Street
| step |  |  | Tier 4: 103-495 - Enterprise Street - Kerb and Channel Installation M2
| step |  |  | Tier 4: 103-496 - Enterprise Street - Kerb and Channel Installation SM1
| step |  |  | Tier 4: 103-497 - Enterprise Street - Kerb and Channel Installation SM2
| step |  |  | Tier 4: 103-498 - Enterprise Street - Kerb and Channel Installation SM3
| step |  |  | Tier 3: Kerb & Channel Eastern Service Rd
| step |  |  | Tier 4: 103-499 - Eastern Service Rd - Kerb and Channel Installation M2
| step |  |  | Tier 4: 103-500 - Eastern Service Rd - Kerb and Channel Installation SM1
| step |  |  | Tier 4: 103-501 - Eastern Service Rd - Kerb and Channel Installation SM2
| step |  |  | Tier 4: 103-502 - Eastern Service Rd - Kerb and Channel Installation SM3
| step |  |  | Tier 3: Kerb & Channel Wastern Service Rd
| step |  |  | Tier 4: 103-503 - Wastern Service Rd - Kerb and Channel Installation M2
| step |  |  | Tier 4: 103-504 - Wastern Service Rd - Kerb and Channel Installation SM1
| step |  |  | Tier 4: 103-505 - Wastern Service Rd - Kerb and Channel Installation SM2
| step |  |  | Tier 4: 103-506 - Wastern Service Rd - Kerb and Channel Installation SM3
| step |  |  | Tier 2: MRP-DPK-102-00-CFN-0011
| step |  |  | Tier 3: South RSS Fill
| step |  |  | Tier 4: 103-0127 - South RSS Fill - Foundation Layer 1 (South CH 0 - 176)
| step |  |  | Tier 4: 103-0128 - South RSS Fill - Foundation Layer 2 (South CH 0 - 176)
| step |  |  | Tier 4: 103-0129 - South RSS Fill - Layer 1 (South CH 0 - 70)
| step |  |  | Tier 4: 103-0130 - South RSS Fill - Layer 2 (South CH 0 - 66)
| step |  |  | Tier 4: 103-0131 - South RSS Fill - Layer 3 (South CH 0 - 62)
| step |  |  | Tier 4: 103-0132 - South RSS Fill - Layer 4 (South CH 0 - 60)
| step |  |  | Tier 4: 103-0133 - South RSS Fill - Layer 5 (South CH 0 - 58)
| step |  |  | Tier 4: 103-0134 - South RSS Fill - Layer 6 (South CH 0 - 92)
| step |  |  | Tier 4: 103-0135 - South RSS Fill - Layer 7 (South CH 0 - 88)
| step |  |  | Tier 4: 103-0136 - South RSS Fill - Layer 8 (South CH 0 - 84)
| step |  |  | Tier 4: 103-0137 - South RSS Fill - Layer 9 (South CH 0 - 80)
| step |  |  | Tier 4: 103-0138 - South RSS Fill - Layer 10 (South CH 0 - 76)
| step |  |  | Tier 4: 103-0139 - South RSS Fill - Layer 11 (South CH 0 - 71)
| step |  |  | Tier 4: 103-0140 - South RSS Fill - Layer 12 (South CH 0 - 66)
| step |  |  | Tier 4: 103-0141 - South RSS Fill - Layer 13 (South CH 0 - 62)
| step |  |  | Tier 4: 103-0142 - South RSS Fill - Layer 14 (South CH 0 - 59)
| step |  |  | Tier 4: 103-0143 - South RSS Fill - Layer 15 (South CH 0 - 56)
| step |  |  | Tier 4: 103-0144 - South RSS Fill - Layer 16 (South CH 0 - 53)
| step |  |  | Tier 4: 103-0145 - South RSS Fill - Layer 17 (South CH 0 - 50)
| step |  |  | Tier 4: 103-0146 - South RSS Fill - Layer 18 (South CH 0 - 46)
| step |  |  | Tier 4: 103-0147 - South RSS Fill - Layer 19 (South CH 0 - 44)
| step |  |  | Tier 4: 103-0148 - South RSS Fill - Layer 20 (South CH 0 - 42)
| step |  |  | Tier 4: 103-0149 - South RSS Fill - Layer 21 (South CH 0 - 40)
| step |  |  | Tier 4: 103-0150 - South RSS Fill - Layer 22 (South CH 0 - 37)
| step |  |  | Tier 4: 103-0151 - South RSS Fill - Layer 23 (South CH 0 - 34)
| step |  |  | Tier 4: 103-0152 - South RSS Fill - Layer 24 (South CH 0 - 30)
| step |  |  | Tier 4: 103-0153 - South RSS Fill - Layer 25 (South CH 0 - 27)
| step |  |  | Tier 4: 103-0154 - South RSS Fill - Layer 26 (South CH 0 - 23)
| step |  |  | Tier 4: 103-0155 - South RSS Fill - Layer 27 (South CH 0 - 19)
| step |  |  | Tier 4: 103-0156 - South RSS Fill - Layer 28 (South CH 0 - 16)
| step |  |  | Tier 4: 103-0157 - South RSS Fill - Layer 29 (South CH 0 - 13)
| step |  |  | Tier 4: 103-0158 - South RSS Fill - Layer 30 (South CH 0 - 10)
| step |  |  | Tier 4: 103-0159 - South RSS Fill - Layer 32 (South CH 0 - 7)
| step |  |  | Tier 4: 103-0160 - South RSS Fill - Layer 33 (South CH 0 - 4)
| step |  |  | Tier 4: 103-0161 - South RSS Fill - Layer 1 (South CH 0 - 176)
| step |  |  | Tier 4: 103-0162 - South RSS Fill - Layer 2 (South CH 0 - 170)
| step |  |  | Tier 4: 103-0163 - South RSS Fill - Layer 3 (South CH 0 - 164)
| step |  |  | Tier 4: 103-0164 - South RSS Fill - Layer 4 (South CH 0 - 158)
| step |  |  | Tier 4: 103-0165 - South RSS Fill - Layer 5 (South CH 0 - 152)
| step |  |  | Tier 4: 103-0166 - South RSS Fill - Layer 6 (South CH 0 - 146)
| step |  |  | Tier 4: 103-0167 - South RSS Fill - Layer 7 (South CH 0 - 138)
| step |  |  | Tier 4: 103-0168 - South RSS Fill - Layer 8 (South CH 0 - 134)
| step |  |  | Tier 4: 103-0169 - South RSS Fill - Layer 9 (South CH 0 - 128)
| step |  |  | Tier 4: 103-0170 - South RSS Fill - Layer 10 (South CH0 - 122)
| step |  |  | Tier 4: 103-0171 - South RSS Fill - Layer 11 (South CH 0 - 116)
| step |  |  | Tier 4: 103-0172 - South RSS Fill - Layer 12 (South CH 0 - 112)
| step |  |  | Tier 4: 103-0173 - South RSS Fill - Layer 13 (South CH 0 - 106)
| step |  |  | Tier 4: 103-0174 - South RSS Fill - Layer 14 (South CH 0 - 100)
| step |  |  | Tier 4: 103-0175 - South RSS Fill - Layer 15 (South CH 0 - 98)
| step |  |  | Tier 4: 103-0176 - South RSS Fill - Layer 16 (South CH 0 - 96)
| step |  |  | Tier 4: 103-0177 - South RSS Fill - Layer 17 (South CH 0 - 94)
| step |  |  | Tier 4: 103-0178 - South RSS Fill - Layer 18 (South CH 0 - 92)
| step |  |  | Tier 4: 103-0179 - South RSS Fill - Layer 19 (South CH 0 - 88)
| step |  |  | Tier 4: 103-0180 - South RSS Fill - Layer 20 (South CH 0 - 86)
| step |  |  | Tier 4: 103-0181 - South RSS Fill - Layer 21 (South CH 0 - 84)
| step |  |  | Tier 4: 103-0182 - South RSS Fill - Layer 22 (South CH 0 -82)
| step |  |  | Tier 4: 103-0183 - South RSS Fill - Layer 23 (South CH 0 - 78)
| step |  |  | Tier 4: 103-0184 - South RSS Fill - Layer 24 (South CH 0 - 76)
| step |  |  | Tier 4: 103-0185 - South RSS Fill - Layer 25 (South CH 0 - 70)
| step |  |  | Tier 3: North RSS FIll
| step |  |  | Tier 4: 103-0186 - North RSS Fill - Foundation Layer 1 (North CH 0 - 220)
| step |  |  | Tier 4: 103-0187 - North RSS Fill - Foundation Layer 2 (North CH 0 - 220)
| step |  |  | Tier 4: 103-0188 - North RSS Fill - Layer 1 (North CH 0 - 220)
| step |  |  | Tier 4: 103-0189 - North RSS Fill - Layer 2 (North CH 0 - 218)
| step |  |  | Tier 4: 103-0190 - North RSS Fill - Layer 3 (North CH 0 - 216)
| step |  |  | Tier 4: 103-0191 - North RSS Fill - Layer 4 (North CH 0 - 212)
| step |  |  | Tier 4: 103-0192 - North RSS Fill - Layer 5 (North CH 0 - 210)
| step |  |  | Tier 4: 103-0193 - North RSS Fill - Layer 6 (North CH 0 - 208)
| step |  |  | Tier 4: 103-0194 - North RSS Fill - Layer 7 (North CH 0 - 206)
| step |  |  | Tier 4: 103-0195 - North RSS Fill - Layer 8 (North CH 0 - 204)
| step |  |  | Tier 4: 103-0196 - North RSS Fill - Layer 9 (North CH 0 - 202)
| step |  |  | Tier 4: 103-0197 - North RSS Fill - Layer 10 (North CH 0 - 200)
| step |  |  | Tier 4: 103-0198 - North RSS Fill - Layer 11 (North CH 0 - 198)
| step |  |  | Tier 4: 103-0199 - North RSS Fill - Layer 12 (North CH 0 - 196)
| step |  |  | Tier 4: 103-0200 - North RSS Fill - Layer 13 (North CH 0 - 194)
| step |  |  | Tier 4: 103-0201 - North RSS Fill - Layer 14 (North CH 0 - 192)
| step |  |  | Tier 4: 103-0202 - North RSS Fill - Layer 15 (North CH 0 - 190)
| step |  |  | Tier 4: 103-0203 - North RSS Fill - Layer 16 (North CH 0 - 188)
| step |  |  | Tier 4: 103-0204 - North RSS Fill - Layer 17 (North CH 0 - 186)
| step |  |  | Tier 4: 103-0205 - North RSS Fill - Layer 18 (North CH 0 - 184)
| step |  |  | Tier 4: 103-0206 - North RSS Fill - Layer 19 (North CH 0 - 182)
| step |  |  | Tier 4: 103-0207 - North RSS Fill - Layer 20 (North CH 0 - 180)
| step |  |  | Tier 4: 103-0208 - North RSS Fill - Layer 21 (North CH 0 - 178)
| step |  |  | Tier 4: 103-0209 - North RSS Fill - Layer 22 (North CH 0 - 176)
| step |  |  | Tier 4: 103-0210 - North RSS Fill - Layer 23 (North CH 0 - 174)
| step |  |  | Tier 4: 103-0211 - North RSS Fill - Layer 24 (North CH 0 - 172)
| step |  |  | Tier 4: 103-0212 - North RSS Fill - Layer 25 (North CH 0 - 170)
| step |  |  | Tier 4: 103-0213 - North RSS Fill - Layer 26 (North CH 0 - 168)
| step |  |  | Tier 4: 103-0214 - North RSS Fill - Layer 27 (North CH 0 - 166)
| step |  |  | Tier 4: 103-0215 - North RSS Fill - Layer 28 (North CH 0 - 164)
| step |  |  | Tier 4: 103-0216 - North RSS Fill - Layer 29 (North CH 0 - 162)
| step |  |  | Tier 4: 103-0217 - North RSS Fill - Layer 30 (North CH 0 - 160)
| step |  |  | Tier 4: 103-0218 - North RSS Fill - Layer 31 (North CH 0 - 158)
| step |  |  | Tier 4: 103-0219 - North RSS Fill - Layer 32 (North CH 0 - 156)
| step |  |  | Tier 4: 103-0220 - North RSS Fill - Layer 33 (North CH 0 - 154)
| step |  |  | Tier 4: 103-0221 - North RSS Fill - Layer 34 (North CH 0 - 152)
| step |  |  | Tier 4: 103-0222 - North RSS Fill - Layer 35 (North CH 0 - 150)
| step |  |  | Tier 4: 103-0223 - North RSS Fill - Layer 36 (North CH 0 - 148)
| step |  |  | Tier 4: 103-0224 - North RSS Fill - Layer 37 (North CH 0 - 146)
| step |  |  | Tier 4: 103-0225 - North RSS Fill - Layer 38 (North CH 0 - 144)
| step |  |  | Tier 4: 103-0226 - North RSS Fill - Layer 39 (North CH 0 - 142)
| step |  |  | Tier 4: 103-0227 - North RSS Fill - Layer 40 (North CH 0 - 140)
| step |  |  | Tier 4: 103-0228 - North RSS Fill - Layer 41 (North CH 0 - 138)
| step |  |  | Tier 4: 103-0229 - North RSS Fill - Layer 42 (North CH 0 - 136)
| step |  |  | Tier 4: 103-0230 - North RSS Fill - Layer 43 (North CH 0 - 134)
| step |  |  | Tier 4: 103-0231 - North RSS Fill - Layer 44 (North CH 0 - 132)
| step |  |  | Tier 4: 103-0232 - North RSS Fill - Layer 1 (North CH 0 - 130)
| step |  |  | Tier 4: 103-0233 - North RSS Fill - Layer 2 (North CH 0 - 128)
| step |  |  | Tier 4: 103-0234 - North RSS Fill - Layer 3 (North CH 0 - 126)
| step |  |  | Tier 4: 103-0235 - North RSS Fill - Layer 4 (North CH 0 - 122)
| step |  |  | Tier 4: 103-0236 - North RSS Fill - Layer 5 (North CH 0 - 120)
| step |  |  | Tier 4: 103-0237 - North RSS Fill - Layer 6 (North CH 0 - 118)
| step |  |  | Tier 4: 103-0238 - North RSS Fill - Layer 7 (North CH 0 - 116)
| step |  |  | Tier 4: 103-0239 - North RSS Fill - Layer 8 (North CH 0 - 112)
| step |  |  | Tier 4: 103-0240 - North RSS Fill - Layer 9 (North CH 0 - 110)
| step |  |  | Tier 4: 103-0241 - North RSS Fill - Layer 10 (North CH 0 - 108)
| step |  |  | Tier 4: 103-0242 - North RSS Fill - Layer 11 (North CH 0 - 104)
| step |  |  | Tier 4: 103-0243 - North RSS Fill - Layer 12 (North CH 0 - 100)
| step |  |  | Tier 4: 103-0244 - North RSS Fill - Layer 13 (North CH 0 - 98)
| step |  |  | Tier 4: 103-0245 - North RSS Fill - Layer 14 (North CH 0 - 96)
| step |  |  | Tier 4: 103-0246 - North RSS Fill - Layer 15 (North CH 0 - 92)
| step |  |  | Tier 4: 103-0247 - North RSS Fill - Layer 16 (North CH 0 - 90)
| step |  |  | Tier 4: 103-0248 - North RSS Fill - Layer 17 (North CH 0 - 88)
| step |  |  | Tier 4: 103-0249 - North RSS Fill - Layer 18 (North CH 0 - 86)
| step |  |  | Tier 4: 103-0250 - North RSS Fill - Layer 19 (North CH 0 - 84)
| step |  |  | Tier 4: 103-0251 - North RSS Fill - Layer 20 (North CH 0 - 82)
| step |  |  | Tier 4: 103-0252 - North RSS Fill - Layer 21 (North CH 0 - 80)
| step |  |  | Tier 4: 103-0253 - North RSS Fill - Layer 22 (North CH 0 - 78)
| step |  |  | Tier 4: 103-0254 - North RSS Fill - Layer 23 (North CH 0 - 76)
| step |  |  | Tier 4: 103-0255 - North RSS Fill - Layer 24 (North CH 0 - 74)
| step |  |  | Tier 4: 103-0256 - North RSS Fill - Layer 25 (North CH 0 - 72)
| step |  |  | Tier 4: 103-0257 - North RSS Fill - Layer 26 (North CH 0 - 70)
| step |  |  | Tier 4: 103-0258 - North RSS Fill - Layer 27 (North CH 0 - 68)
| step |  |  | Tier 4: 103-0259 - North RSS Fill - Layer 28 (North CH 0 - 66)
| step |  |  | Tier 4: 103-0260 - North RSS Fill - Layer 29 (North CH 0 - 64)
| step |  |  | Tier 4: 103-0261 - North RSS Fill - Layer 30 (North CH 0 - 62)
| step |  |  | Tier 4: 103-0262 - North RSS Fill - Layer 31 (North CH 0 - 60)
| step |  |  | Tier 4: 103-0263 - North RSS Fill - Layer 32 (North CH 0 - 58)
| step |  |  | Tier 4: 103-0264 - North RSS Fill - Layer 33 (North CH 0 - 56)
| step |  |  | Tier 4: 103-0265 - North RSS Fill - Layer 34 (North CH 0 - 54)
| step |  |  | Tier 4: 103-0266 - North RSS Fill - Layer 35 (North CH 0 - 52)
| step |  |  | Tier 4: 103-0267 - North RSS Fill - Layer 1 (North CH 0 - 50)
| step |  |  | Tier 4: 103-0268 - North RSS Fill - Layer 2 (North CH 0 - 48)
| step |  |  | Tier 4: 103-0269 - North RSS Fill - Layer 3 (North CH 0 - 46)
| step |  |  | Tier 4: 103-0270 - North RSS Fill - Layer 4 (North CH 0 - 44)
| step |  |  | Tier 4: 103-0271 - North RSS Fill - Layer 5 (North CH 0 - 42)
| step |  |  | Tier 4: 103-0272 - North RSS Fill - Layer 6 (North CH 0 - 40)
| step |  |  | Tier 4: 103-0273 - North RSS Fill - Layer 7 (North CH 0 - 38)
| step |  |  | Tier 4: 103-0274 - North RSS Fill - Layer 8 (North CH 0 - 36)
| step |  |  | Tier 4: 103-0275 - North RSS Fill - Layer 9 (North CH 0 - 34)
| step |  |  | Tier 4: 103-0276 - North RSS Fill - Layer 10 (North CH 0 - 32)
| step |  |  | Tier 4: 103-0277 - North RSS Fill - Layer 11 (North CH 0 - 30)
| step |  |  | Tier 4: 103-0278 - North RSS Fill - Layer 12 (North CH 0 - 28)
| step |  |  | Tier 4: 103-0279 - North RSS Fill - Layer 13 (North CH 0 - 26)
| step |  |  | Tier 4: 103-0280 - North RSS Fill - Layer 14 (North CH 0 - 24)
| step |  |  | Tier 4: 103-0281 - North RSS Fill - Layer 15 (North CH 0 - 22)
| step |  |  | Tier 4: 103-0282 - North RSS Fill - Layer 16 (North CH 0 - 20)
| step |  |  | Tier 4: 103-0283 - North RSS Fill - Layer 17 (North CH 0 - 18)
| step |  |  | Tier 4: 103-0284 - North RSS Fill - Layer 18 (North CH 0 - 16)
| step |  |  | Tier 4: 103-0285 - North RSS Fill - Layer 19 (North CH 0 - 14)
| step |  |  | Tier 4: 103-0286 - North RSS Fill - Layer 20 (North CH 0 - 12)
| step |  |  | Tier 4: 103-0287 - North RSS Fill - Layer 21 (North CH 0 - 10)
| step |  |  | Tier 4: 103-0288 - North RSS Fill - Layer 22 (North CH 0 - 9)
| step |  |  | Tier 4: 103-0289 - North RSS Fill - Layer 23 (North CH 0 - 8)
| step |  |  | Tier 4: 103-0290 - North RSS Fill - Layer 24 (North CH 0 - 7)
| step |  |  | Tier 4: 103-0291 - North RSS Fill - Layer 25 (North CH 0 - 6)
| step |  |  | Tier 4: 103-0292 - North RSS Fill - Layer 26 (North CH 0 - 5)
| step |  |  | Tier 4: 103-0293 - North RSS Fill - Layer 27 (North CH 0 - 4)
| step |  |  | Tier 4: 103-0294 - North RSS Fill - Layer 28 (North CH 0 - 3)
| step |  |  | Tier 4: 103-0295 - North RSS Fill - Layer 29 (North CH 0 - 2)
| step |  |  | Tier 4: 103-0296 - North RSS Fill - Layer 30 (North CH 0 - 1)
| step |  |  | Tier 3: Pipe Installation
| step |  |  | Tier 4: 103-296 - Drainage Pipe Installation -PIPE-2
| step |  |  | Tier 4: 103-297 - Drainage Pipe Installation -PIPE-3
| step |  |  | Tier 4: 103-298 - Drainage Pipe Installation -PIPE-4
| step |  |  | Tier 4: 103-299 - Drainage Pipe Installation -PIPE-5
| step |  |  | Tier 4: 103-300 - Drainage Pipe Installation -PIPE-6
| step |  |  | Tier 4: 103-301 - Drainage Pipe Installation -PIPE-7
| step |  |  | Tier 4: 103-302 - Drainage Pipe Installation -PIPE-8
| step |  |  | Tier 4: 103-303 - Drainage Pipe Installation -PIPE-9
| step |  |  | Tier 4: 103-304 - Drainage Pipe Installation -PIPE-10
| step |  |  | Tier 4: 103-305 - Drainage Pipe Installation -PIPE-11
| step |  |  | Tier 4: 103-306 - Drainage Pipe Installation -PIPE-12
| step |  |  | Tier 4: 103-307 - Drainage Pipe Installation -PIPE-13
| step |  |  | Tier 4: 103-308 - Drainage Pipe Installation -PIPE-14
| step |  |  | Tier 4: 103-309 - Drainage Pipe Installation -PIPE-15
| step |  |  | Tier 4: 103-310 - Drainage Pipe Installation -PIPE-16
| step |  |  | Tier 4: 103-311 - Drainage Pipe Installation -PIPE-17
| step |  |  | Tier 4: 103-312 - Drainage Pipe Installation -PIPE-18
| step |  |  | Tier 4: 103-313 - Drainage Pipe Installation -PIPE-19
| step |  |  | Tier 4: 103-314 - Drainage Pipe Installation -PIPE-20
| step |  |  | Tier 4: 103-315 - Drainage Pipe Installation -PIPE-21
| step |  |  | Tier 4: 103-316 - Drainage Pipe Installation -PIPE-22
| step |  |  | Tier 4: 103-317 - Drainage Pipe Installation -PIPE-23
| step |  |  | Tier 4: 103-318 - Drainage Pipe Installation -PIPE-24
| step |  |  | Tier 4: 103-319 - Drainage Pipe Installation -PIPE-25
| step |  |  | Tier 4: 103-320 - Drainage Pipe Installation -PIPE-26
| step |  |  | Tier 4: 103-321 - Drainage Pipe Installation -PIPE-27
| step |  |  | Tier 4: 103-322 - Drainage Pipe Installation -PIPE-28
| step |  |  | Tier 4: 103-323 - Drainage Pipe Installation -PIPE-29
| step |  |  | Tier 4: 103-324 - Drainage Pipe Installation -PIPE-30
| step |  |  | Tier 4: 103-325 - Drainage Pipe Installation -PIPE-31
| step |  |  | Tier 4: 103-326 - Drainage Pipe Installation -PIPE-32
| step |  |  | Tier 4: 103-327 - Drainage Pipe Installation -PIPE-33
| step |  |  | Tier 4: 103-328 - Drainage Pipe Installation -PIPE-34
| step |  |  | Tier 4: 103-329 - Drainage Pipe Installation -PIPE-35
| step |  |  | Tier 4: 103-330 - Drainage Pipe Installation -PIPE-36
| step |  |  | Tier 4: 103-331 - Drainage Pipe Installation -PIPE-37
| step |  |  | Tier 4: 103-332 - Drainage Pipe Installation -PIPE-38
| step |  |  | Tier 4: 103-333 - Drainage Pipe Installation -PIPE-39
| step |  |  | Tier 4: 103-334 - Drainage Pipe Installation -PIPE-40
| step |  |  | Tier 4: 103-335 - Drainage Pipe Installation -PIPE-41
| step |  |  | Tier 4: 103-336 - Drainage Pipe Installation -PIPE-42
| step |  |  | Tier 4: 103-337 - Drainage Pipe Installation -PIPE-43
| step |  |  | Tier 4: 103-338 - Drainage Pipe Installation -PIPE-44
| step |  |  | Tier 3: Pit Installation
| step |  |  | Tier 4: 103-339 - Drainage Pit Installation - D1-02
| step |  |  | Tier 4: 103-340 - Drainage Pit Installation - D1-03
| step |  |  | Tier 4: 103-341 - Drainage Pit Installation - D1-04
| step |  |  | Tier 4: 103-342 - Drainage Pit Installation - D1-05
| step |  |  | Tier 4: 103-343 - Drainage Pit Installation - D1-06
| step |  |  | Tier 4: 103-344 - Drainage Pit Installation - D1-07
| step |  |  | Tier 4: 103-345 - Drainage Pit Installation - D1-08
| step |  |  | Tier 4: 103-346 - Drainage Pit Installation - D1-09
| step |  |  | Tier 4: 103-347 - Drainage Pit Installation - D1-10
| step |  |  | Tier 4: 103-348 - Drainage Pit Installation - D1-11
| step |  |  | Tier 4: 103-349 - Drainage Pit Installation - D1-12
| step |  |  | Tier 4: 103-350 - Drainage Pit Installation - D1-13
| step |  |  | Tier 4: 103-351 - Drainage Pit Installation - D1-14
| step |  |  | Tier 4: 103-352 - Drainage Pit Installation - D1-15
| step |  |  | Tier 4: 103-353 - Drainage Pit Installation - D1-16
| step |  |  | Tier 4: 103-354 - Drainage Pit Installation - D1-17
| step |  |  | Tier 4: 103-355 - Drainage Pit Installation - D1-18
| step |  |  | Tier 4: 103-356 - Drainage Pit Installation - D1-19
| step |  |  | Tier 4: 103-357 - Drainage Pit Installation - D1-20
| step |  |  | Tier 4: 103-358 - Drainage Pit Installation - D1-21
| step |  |  | Tier 4: 103-359 - Drainage Pit Installation - D1-22
| step |  |  | Tier 4: 103-360 - Drainage Pit Installation - D1-23
| step |  |  | Tier 4: 103-361 - Drainage Pit Installation - D1-24
| step |  |  | Tier 4: 103-362 - Drainage Pit Installation - D1-25
| step |  |  | Tier 4: 103-363 - Drainage Pit Installation - D1-26
| step |  |  | Tier 4: 103-364 - Drainage Pit Installation - D1-27
| step |  |  | Tier 4: 103-365 - Drainage Pit Installation - D1-28
| step |  |  | Tier 4: 103-366 - Drainage Pit Installation - D1-29
| step |  |  | Tier 4: 103-367 - Drainage Pit Installation - D1-30
| step |  |  | Tier 4: 103-368 - Drainage Pit Installation - D1-31
| step |  |  | Tier 4: 103-369 - Drainage Pit Installation - D1-32
| step |  |  | Tier 4: 103-370 - Drainage Pit Installation - D1-33
| step |  |  | Tier 4: 103-371 - Drainage Pit Installation - D1-34
| step |  |  | Tier 3: Headwall Installation
| step |  |  | Tier 4: 103-372 - Headwall Installation D1-01
| step |  |  | Tier 4: 103-373 - Headwall Installation D4-01
| step |  |  | Tier 4: 103-374 - Headwall Installation D4-02
| step |  |  | Tier 4: 103-375 - Headwall Installation D5-02
| step |  |  | Tier 3: Subsoil
| step |  |  | Tier 4: 103-376 - Type 3 (DTP SD 1601) Subsurface Drain 1
| step |  |  | Tier 4: 103-377 - Type 3 (DTP SD 1601) Subsurface Drain 2
| step |  |  | Tier 4: 103-378 - Type 3 (DTP SD 1601) Subsurface Drain 3
| step |  |  | Tier 4: 103-379 - Type 3 (DTP SD 1601) Subsurface Drain 4
| step |  |  | Tier 4: 103-380 - Type 3 (DTP SD 1601) Subsurface Drain 5
| step |  |  | Tier 4: 103-381 - Type 3 (DTP SD 1601) Subsurface Drain 6
| step |  |  | Tier 4: 103-382 - Type 3 (DTP SD 1601) Subsurface Drain 7
| step |  |  | Tier 4: 103-383 - Type 3 (DTP SD 1601) Subsurface Drain 8
| step |  |  | Tier 4: 103-384 - Type 3 (DTP SD 1601) Subsurface Drain 9
| step |  |  | Tier 4: 103-385 - Type 3 (DTP SD 1601) Subsurface Drain 10
| step |  |  | Tier 4: 103-386 - Type 3 (DTP SD 1601) Subsurface Drain 11
| step |  |  | Tier 4: 103-387 - Type 3 (DTP SD 1601) Subsurface Drain 12
| step |  |  | Tier 4: 103-388 - Type 3 (DTP SD 1601) Subsurface Drain 13
| step |  |  | Tier 4: 103-389 - Type 3 (DTP SD 1601) Subsurface Drain 14
| step |  |  | Tier 4: 103-390 - Type 3 (DTP SD 1601) Subsurface Drain 15
| step |  |  | Tier 4: 103 -391 - Type 3 (DTP SD 1601) Subsurface Drain 16
| step |  |  | Tier 4: 103- 392 - Type 3 (DTP SD 1601) Subsurface Drain 17
| step |  |  | Tier 4: 103 -393 - Type 2 - No Fines Concete (DTP SD 1601) Subsurface Drain 1
| step |  |  | Tier 4: 103 -394 - Type 2 - No Fines Concete (DTP SD 1601) Subsurface Drain 2
| step |  |  | Tier 4: 103 -395 - Type 2 - No Fines Concete (DTP SD 1601) Subsurface Drain 3
| step |  |  | Tier 4: 103 -396 - Type 2 - No Fines Concete (DTP SD 1601) Subsurface Drain 4
| step |  |  | Tier 4: 103 -397 - Type 2 - No Fines Concete (DTP SD 1601) Subsurface Drain 5
| step |  |  | Tier 4: 103 -398 - Type 2 - No Fines Concete (DTP SD 1601) Subsurface Drain 6
| step |  |  | Tier 4: 103 -399 - Type 2 - No Fines Concete (DTP SD 1601) Subsurface Drain 7
| step |  |  | Tier 4: 103 -400 - Type 2 - No Fines Concete (DTP SD 1601) Subsurface Drain 8
| step |  |  | Tier 4: 103 -401 - Type 2 - No Fines Concete (DTP SD 1601) Subsurface Drain 9
| step |  |  | Tier 4: 103 -402 - Type 2 - No Fines Concete (DTP SD 1601) Subsurface Drain 10
| step |  |  | Tier 4: 103 -403 - Type 2 - No Fines Concete (DTP SD 1601) Subsurface Drain 11
| step |  |  | Tier 4: 103 -404 - Type 2 - No Fines Concete (DTP SD 1601) Subsurface Drain 12
| step |  |  | Tier 4: 103 -405 - Type 2 - No Fines Concete (DTP SD 1601) Subsurface Drain 13
| step |  |  | Tier 4: 103 -406 - Type 2 - No Fines Concete (DTP SD 1601) Subsurface Drain 14
| step |  |  | Tier 4: 103 -407 - Type 2 - No Fines Concete (DTP SD 1601) Subsurface Drain 15
| step |  |  | Tier 4: 103 -408 - Type 2 - No Fines Concete (DTP SD 1601) Subsurface Drain 16
| step |  |  | Tier 3: Road Pavement Enterprise St
| step |  |  | Tier 4: 103-409 - Pavement Type H: Concrete Base
| step |  |  | Tier 4: 103-410 - Pavement Type H:Subbase
| step |  |  | Tier 4: 103-411 - Pavement Type H:Subgrade
| step |  |  | Tier 4: 103-468 - Pavement Type E:Wearing Course
| step |  |  | Tier 4: 103-469 - Pavement Type E: Intermediate Layer
| step |  |  | Tier 4: 103-470 - Pavement Type E: Base Course
| step |  |  | Tier 4: 103-471 - Pavement Type E: Subbase Course
| step |  |  | Tier 4: 103-472 - Pavement Type E: Select Fill
| step |  |  | Tier 4: 103-473 - Pavement Type E: Subgrade
| step |  |  | Tier 4: 103-474 - Pavement Type K: Initial Seal
| step |  |  | Tier 4: 103-475 - Pavement Type K: Base
| step |  |  | Tier 4: 103-476 - Pavement Type K: Subbase
| step |  |  | Tier 4: 103-477 - Pavement Type K: Select Fill
| step |  |  | Tier 3: Road Pavement Eastern Service Rd
| step |  |  | Tier 4: 103-412 - Pavement Type H: Concrete Base
| step |  |  | Tier 4: 103-413 - Pavement Type H:Subbase
| step |  |  | Tier 4: 103-414 - Pavement Type H:Subgrade
| step |  |  | Tier 4: 103-478 - Pavement Type K: Initial Seal
| step |  |  | Tier 4: 103-479 - Pavement Type K: Base
| step |  |  | Tier 4: 103-480 - Pavement Type K: Subbase
| step |  |  | Tier 4: 103-481 - Pavement Type K: Select Fill
| step |  |  | Tier 4: 103-482 - Pavement Type E:Wearing Course
| step |  |  | Tier 4: 103-483 - Pavement Type E: Intermediate Layer
| step |  |  | Tier 4: 103-484 - Pavement Type E: Base Course
| step |  |  | Tier 4: 103-485 - Pavement Type E: Subbase Course
| step |  |  | Tier 4: 103-486 - Pavement Type E: Select Fill
| step |  |  | Tier 4: 103-487 - Pavement Type E: Subgrade
| step |  |  | Tier 3: Road Pavement North of Rail
| step |  |  | Tier 4: 103-415 - Pavement Type A:Select Fill
| step |  |  | Tier 4: 103-416 - Pavement Type A:Subbase
| step |  |  | Tier 4: 103-417 - Pavement Type A: As Base
| step |  |  | Tier 4: 103-418 - Pavement Type A: Intermediate Layer
| step |  |  | Tier 4: 103-419 - Pavement Type H: Concrete Base
| step |  |  | Tier 4: 103-420 - Pavement Type H:Subbase
| step |  |  | Tier 4: 103-421 - Pavement Type H:Subgrade
| step |  |  | Tier 4: 103-422 - Pavement Type E:Wearing Course
| step |  |  | Tier 4: 103-423 - Pavement Type E: Intermediate Layer
| step |  |  | Tier 4: 103-424 - Pavement Type E: Base Course
| step |  |  | Tier 4: 103-425 - Pavement Type E: Subbase Course
| step |  |  | Tier 4: 103-426 - Pavement Type E: Select Fill
| step |  |  | Tier 4: 103-427 - Pavement Type E: Subgrade
| step |  |  | Tier 4: 103-428 - Pavement Type G: Base
| step |  |  | Tier 4: 103-429 - Pavement Type G:Subbase
| step |  |  | Tier 4: 103-430 - Pavement Type M: Surfacing
| step |  |  | Tier 4: 103-431 - Pavement Type M: Concrete Base
| step |  |  | Tier 4: 103-432 - Pavement Type M: Subbase
| step |  |  | Tier 4: 103-433 - Pavement Type M: Subgrade
| step |  |  | Tier 4: 103-434 - Pavement Type D: Concerete Base
| step |  |  | Tier 4: 103-435 - Pavement Type D: Subbase
| step |  |  | Tier 4: 103-436 - Pavement Type D: Subgrade or New Embankment
| step |  |  | Tier 4: 103-437 - Pavement Type F:Wearing Course
| step |  |  | Tier 4: 103-438 - Pavement Type F: Regulating Layer ( Only required to achieve design Level )
| step |  |  | Tier 3: Western Service Rd Existing Ferris Rd
| step |  |  | Tier 4: 103-439 - Pavement Type J: Wearing Course
| step |  |  | Tier 4: 103-440 - Pavement Type J: Regulating Layer (Only required to achieve design level)
| step |  |  | Tier 4: 103-441 - Pavement Type H: Concrete Base
| step |  |  | Tier 4: 103-442 - Pavement Type H:Subbase
| step |  |  | Tier 4: 103-443 - Pavement Type H:Subgrade
| step |  |  | Tier 3: Road Pavement South of Rail
| step |  |  | Tier 4: 103-444 - Pavement Type C: Wearing Course
| step |  |  | Tier 4: 103-445 - Pavement Type C: Regulation Course
| step |  |  | Tier 4: 103-446 - Pavement Type A:Select Fill
| step |  |  | Tier 4: 103-447 - Pavement Type A:Subbase
| step |  |  | Tier 4: 103-448 - Pavement Type A: As Base
| step |  |  | Tier 4: 103-449 - Pavement Type A: Intermediate Layer
| step |  |  | Tier 4: 103-450 - Pavement Type A : Ashpalt Wearing Course
| step |  |  | Tier 4: 103-451 - Pavement Type E:Wearing Course
| step |  |  | Tier 4: 103-452 - Pavement Type E: Intermediate Layer
| step |  |  | Tier 4: 103-453 - Pavement Type E: Base Course
| step |  |  | Tier 4: 103-454 - Pavement Type E: Subbase Course
| step |  |  | Tier 4: 103-455 - Pavement Type E: Select Fill
| step |  |  | Tier 4: 103-456 - Pavement Type D: Concerete Base
| step |  |  | Tier 4: 103-457 - Pavement Type D: Subbase
| step |  |  | Tier 4: 103-458 - Pavement Type D: Subgrade or New Embankment
| step |  |  | Tier 4: 103-459 - Pavement Type A:Select Fill
| step |  |  | Tier 4: 103-460 - Pavement Type A:Subbase
| step |  |  | Tier 4: 103-461 - Pavement Type A: As Base
| step |  |  | Tier 4: 103-462 - Pavement Type A: Intermediate Layer
| step |  |  | Tier 4: 103-463 - Pavement Type A : Ashpalt Wearing Course
| step |  |  | Tier 4: 103-464 - Pavement Type J: Wearing Course
| step |  |  | Tier 4: 103-465 - Pavement Type J: Regulating Layer ( Only required to achieve design level)
| step |  |  | Tier 4: 103-466 - Pavement Type G: Base
| step |  |  | Tier 4: 103-467 - Pavement Type G:Subbase
| step |  |  | Tier 3: Kerb & Channel North of Rail Ferris Rd
| step |  |  | Tier 4: 103-488 - North of Rail- Ferris Rd - Kerb and Channel Installation M2
| step |  |  | Tier 4: 103-489 - North of Rail- Ferris Rd - Kerb and Channel Installation SM1
| step |  |  | Tier 4: 103-490 - North of Rail - Ferris Rd - Kerb and Channel Installlation SM2
| step |  |  | Tier 4: 103-491 - South of Rail - Ferris Rd - Kerb and Channel Installation M2
| step |  |  | Tier 4: 103-492 - South of Rail - Ferris Rd - kerb and Channel Installation SM1
| step |  |  | Tier 2: MRP-DPK-103-00-AUD-0071
| step |  |  | Tier 3: Landscaping Median Ferris Rd
| step |  |  | Tier 4: 103-507 - Median Ferris Rd - Landscaping - Top Soil
| step |  |  | Tier 4: 103-508 - Median Ferris Rd - Landscaping - Mulch
| step |  |  | Tier 4: 103-509 - Median Ferris Rd - Landscaping - Planting
| step |  |  | Tier 3: Landscaping Enterprise Street
| step |  |  | Tier 4: 103-510 - Enterprise Street - Landscaping - Top Soil
| step |  |  | Tier 4: 103-511 - Enterprise Street - Landscaping - Mulch
| step |  |  | Tier 4: 103-512 - Enterprise Street - Landscaping - Planting
| step |  |  | Tier 3: Landscaping Eastern Service Rd
| step |  |  | Tier 4: 103-513 - Eastern Service Rd - Landscaping - Top Soil
| step |  |  | Tier 4: 103-514 - Eastern Service Rd - Landscaping - Mulch
| step |  |  | Tier 4: 103-515 - Eastern Service Rd - Landscaping - Planting
| step |  |  | Tier 3: Landscaping Wastern Service Rd
| step |  |  | Tier 4: 103-516 - Wastern Service Rd - Landscaping - Topsoil
| step |  |  | Tier 4: 103-517 - Wastern Service Rd - Landscaping - Mulch
| step |  |  | Tier 4: 103-518 - Wastern Service Rd - Landscaping - Planting