## res_ITP-217-CIV-HOP-Subgrade Pr
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-233-RAIL-HOP-Track Removal & Construction | itp |  |  |  |  | ITP-233-RAIL-HOP-Track Removal & Construction Rev 1
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-233-Rail-Track Removal & Construction
label | ITP Description: Track Removal & Construction
label | Discipline (e.g. CIV/STR/RAIL): 233-Rail
label | Revision Number: 1
label | Revision Date: 22/10/2024
label | ITP created by: Jake Argentaro
label | 1.01 - Non Dependent
label | Reference - Hopkins Road Track & Civil IFC Drawing Set MRP-DPK-102-00-CPW-0061, MRP-DPK-102-00-CPW-0060
label | 1.02 - Non Dependent
label | Reference - NIST-2654 Ballast
label | 1.03 - Non Dependent
label | Reference - NIST-2651 Sleepers and Fastenings
label | 1.04 - Non Dependent
label | Reference - NIST-2650 Rail Use Laying and Adjustment
label | 1.05 - Non Dependent
label | Reference - NIST-2630 Track Construction
label | 1.06 - Non Dependent
label | Reference - NIST-2706 Track Geometry
label | 1.07 - Non Dependent
label | Reference - NIST-2659 Earthworks and Drainage
label | 1.08 - Non Dependent
label | Reference - NIST-2618 Track Design
label | 1.09 - Non Dependent
label | Reference - NIFO-2650.5 Aluminothermic Weld Record
label | 1.10 - Non Dependent
label | Reference - NIFO-2690.3 Certificate of Track for Operation
section | 2. Preliminaries
checkpoint | 2.01 - Obtain and submit Material Certificate of Compliance for Track Materials;
label | – Track Rail
label | – Track Sleepers
label | – Track Jewellery
label | – Geofabric
label | – Ballast Matting
label | – Ballast 60mm Aggregate
label | – Welding Kits
label | – Welding Crucibles
label | Reference - IFC Drawing(s), Track Constrction Site Mudmap, Bill of Materials
label | Acceptance Criteria - Units to be free from damage, total and types of units for full set validated No signs of discoloration
label | ○ Attach: Manufacturer Cetificates of Compliance
label | Method - Review Document
label | Frequency - Once
label | Category - HP
label | Responsibility - Site/Project Engineer
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.02 - Submit Welding Procedure/welding qualification welders Record
label | Reference - NIST-2650 Rail, AS 1085.20 Welding Rail Steels
label | Acceptance Criteria - Qualified personnel & welding accordance with manufacturers specs.
label | Method - Review Document
label | Frequency - Once
label | Category - HP
label | Responsibility - Site/Project Engineer
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Inspect supplied items upon delivery
label | Reference - Bill of Materials
label | Acceptance Criteria - No damage or debris on components
label | ○ Validate total number and type of components matches drawing
label | ○ Attach: Photos on site;
label | – Track Rail
label | – Track Sleepers
label | – Track Jewellery
label | – Geofabric
label | – Ballast 53mm Aggregate
label | – Welding Kits
label | – Welding Crucibles
label | Method - Visual, Measure
label | Frequency - Per delivery
label | Category - IP
label | Responsibility - Site/Project Engineer
label | Verifying Documents - Material Inspection Report
date | Date Completed:
checkpoint | 2.04 - Confirm extent of track removal required for civil works
label | Reference - IFC Drawing(s), Track Constrction Site Mudmap
label | Acceptance Criteria - Extent of civil works and subsequent track removal to be confirmed in conjunction with MRPA civil team, limits of removal to be marked up on site
label | ○ Pre-removal survey of existing track alignment
label | Method - Visual, Measure
label | Frequency - Once
label | Category - IP
label | Responsibility - Site/Project Engineer
label | Verifying Documents - This ITP
date | Date Completed:
section | 3. Construction / Installation Activities
checkpoint | 3.01 - Deconstruct and remove track componends, including rail, sleepers, jewellery & ballast. Stockpile materials as required for reuse during construction
label | Reference - IFC Drawing(s), Track Constrction Site Mudmap
label | Acceptance Criteria - Track structure to be removed to the designated limits as identified.
label | ○ Visual confirmation of removal on site
label | Method - Visual, Measure
label | Frequency - Once
label | Category - IP
label | Responsibility - Track Supervisor, Site/Project Engineer
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.02 - Earthworks completed and site handed over from Civil Contractor
label | Reference - NIST-2659 Earthworks and Drainage
label | Acceptance Criteria - Confirmation of completion of underlying ITP(s)
textbox | Underlying ITP reference:
label | ○ Applicable: Stage 2 Track Construction
label | Method - Visual, Measure
label | Frequency - Once
label | Category - IP
label | Responsibility - Track Supervisor, Site/Project Engineer
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.03 - Installlation of Bottom Ballast
label | Reference - NIST-2654 Ballast
label | Acceptance Criteria - Overal Minimum 300mm bottom ballast depth
label | ○ Ballast to be placed in 150mm max layers. Layers to be compacted with 10 tonne smooth drum vibrating roller with minimum 3 passes, in areas where wheeled roller cannot access, ballast to be compated using a vibratory compaction plate
label | ○ Bottom Ballast to be left 20mm below final design level
label | ○ Tolerance: Under sleeper -0mm/+25mm.
label | ○ Attach Site Photo: Installed Bottom Ballast Layer
label | ○ Applicable: Stage 2 Track Construction
label | Method - Visual, Measure
label | Frequency - Once
label | Category - IP
label | Responsibility - Track Surveyor, Track Supervisor, Site/Project Engineer
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.04 - Laying of Sleepers
label | Reference - NIST-2651 Sleepers and Fastenings
label | Acceptance Criteria - Sleepers square at nominal 685mm +/-25mm for open track
label | ○ Attach Site Photo:
label | – Laid Sleepers
label | – Sleeper Spacing Measurement
label | Method - Visual, Measure
label | Frequency - Once
label | Category - IP
label | Responsibility - Track Supervisor, Site/Project Engineer
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.05 - Rail & Fastening Installation
label | Reference - NIST-2650 Rail, NIST-2651 Sleepers and Fastenings
label | Acceptance Criteria - All rail sitting within Sleeper footing with correct sleeper insulators, rail ends positioned the midpoint of sleeper bays +/-50mm, no rail ends to be located within 3m of existing track welds, rail fastenings installed
label | ○ New Rail lengths installed to be as per approved Hopkins Road Rail Weld Plan
label | ○ Gauge of track to be checked upon installation of fastenings
label | ○ Gauge +4mm/-3mm
label | ○ Gauge Variation over 2m 4mm
label | ○ Attach Site Photo:
label | – Laid rail
label | – Rail joint to exisiting weld measurement
label | – Rail joint between sleeper bay measurements
label | Method - Visual, Measure
label | Frequency - Once
label | Category - IP
label | Responsibility - Track Supervisor, Site/Project Engineer
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.06 - Track Tamping
label | Reference - NIST-2630 Track Construction, NIST-2706 Track Geometry
label | Acceptance Criteria - Tamping Ensures Track Geometry Tolerances are not breached (dimentions are in mm);
label | ○ Line (10m Chord) +/-5mm
label | ○ Twist (3.5m Chord) +/-5mm
label | ○ Twist 10m (Chord) +/-10mm
label | ○ Cant +/-5mm
label | ○ Top (10m Chord) +/-5mm
label | ○ Alignment +/-20mm
label | ○ Survey measurment of RL of top of rail head
label | ○ A minimum horizontal clearance of 3.0m from track centreline to structure.
label | ○ Attach;
label | – Tamping Geometry Recording
label | – Survey RL measuring sheet
label | ○ Attach Site Photos:
label | – Tamping Activity
label | – Structual Offset Measurement
label | Method - Visual, Measure
label | Frequency - Once
label | Category - HP
label | Responsibility - Track Surveyor, Track Supervisor, Site/Project Engineer
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.07 - Regualting and Ballast Profile
label | Reference - NIST-2630 Track Construction, NIST-2706 Track Geometry
label | Acceptance Criteria - Ballast shoulder of 400mm width from outer edge of sleeper and with 1:1.5 angle of repose thereafter
label | ○ No Ballast to be on top surface of sleepers or aorund rail Fastenings
label | ○ Attach Site Photos:
label | – Ballast Shoulder Measurement
label | – Rubber Panels free of ballast materials
label | Method - Visual, Measure
label | Frequency - Once
label | Category - IP
label | Responsibility - Track Supervisor, Site/Project Engineer
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.08 - Aluminothermic Welding
label | Reference - NIST-2650 Rail, NIFO-2650.5 Aluminothermic Weld Record
label | Acceptance Criteria - Welds to be lined and finished to alignment standard
label | ○ Tolerance:
label | – Gauge Face +1.0/-0.5mm
label | – Running Face +0.6/-0.0mm
label | ○ Verify Aluminothermic welding carried out in accordance with AS1085.20
label | ○ Aluminothermic Weld Return Form to be completed
label | ○ Attach
label | – Aluminothermic Weld Return Form
label | ○ Attach Site Photos:
label | – Welding Aligning
label | – Welding Process
label | Method - Visual, Measure
label | Frequency - Each Weld
label | Category - IP
label | Responsibility - Track Welder, Track Supervisor, Site/Project Engineer
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.09 - Track Stressing
label | Reference - NIST-2650 Rail, NIFO-2650.5 Aluminothermic Weld Record
label | Acceptance Criteria - Stressing Rail in line with V/Line Rail Welding Process
label | ○ Ensure Stressing only performed between rail temperatures; >10 and <38 degrees
label | ○ Complete track stressing in 330m module or otherwise as noted on approved track stressing plan
label | ○ Reference Marks recorded pre and post tensing of rail
label | ○ Aluminothermic Weld Return Form to be completed
label | ○ Attach
label | – Aluminothermic Weld Return Form
label | ○ Attach Site Photos:
label | – Stressing Activity
label | – Under Rail Roller Spacing
label | – Before/After Reference Mark Measurments
label | Method - Visual, Measure
label | Frequency - Each Restress module
label | Category - IP
label | Responsibility - Track Welder, Track Supervisor, Site/Project Engineer
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.10 - Weld Ultrasonic Testing
label | Reference - NIST-2650 Rail, NIFO-2650.5 Aluminothermic Weld Record
label | Acceptance Criteria - Ultrasonic testing to be carried out in accordance with NIST-2650 Rail
label | ○ The cross section of the area of the head and web shall be completely scanned;
label | – The foot area shall be scanned in accordance with AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2.
label | – Welds shall be scanned to both directions.
label | ○ No classified internal defects found
label | ○ Final weld geometry to be assessed
label | ○ Tolerance:
label | – Gauge Face +1.0/-0.5mm
label | – Running Face +0.6/-0.0mm
label | ○ Aluminothermic Weld Return Form to be completed
label | ○ Attach
label | – Aluminothermic Weld Return Form
label | – Aluminothermic Weld Test Report
label | ○ Attach Site Photos:
label | – Welding Aligning
label | – Welding Process
label | Method - Visual, Measure, Test
label | Frequency - Each Weld
label | Category - HP
label | Responsibility - Weld Tester, Track Supervisor, Site/Project Engineer
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.11 - Installation of Guard Rail & Guard Rail Nose
label | Reference - IFC Drawing(s), NIST-2650 Rail
label | Acceptance Criteria - Install guard rail and guard rail nose as per IFC design
label | ○ Guardrail to be installed with alternating fastening pattern
label | ○ Guardrail to be isntalled at lengths of either 13.7m, 19.9m or 27.5m, joints to be gap adjusted and plate & bolted upon completion
label | ○ Attach Site Photo:
label | – Guard rail isntalled
label | – Guard rail nose installed
label | Method - Visual, Measure, Test
label | Frequency - Once
label | Category - HP
label | Responsibility - Track Supervisor, Site/Project Engineer
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4. Post-construction / Post-installation Activities
checkpoint | 4.01 - As-built Survey
label | Reference - IFC Drawing(s)
label | Acceptance Criteria - Survey activities undertaken to validate correct construction
label | ○ Attach:
label | – Survey Report
label | – Engineering Asset From
label | Method - Survey, Document Review
label | Frequency - Once
label | Category - IP
label | Responsibility - Track Surveyor, Site/Project Engineer
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.02 - Track Certification
label | Reference - NIFO-2690.3 Certificate of Track for Operation
label | Acceptance Criteria - Attach:
label | – Track Geometry Conformance Certificate
label | – Track System and Component
label | ○ Attach Site Photos:
label | – Before/After Photo of worksite
label | Method - Visual, Measure, Doument Reivew
label | Frequency - Once when all occupation works complete
label | Category - HP
label | Responsibility - Track Certifier, Site/Project Engineer
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP