## to_add
Step Id | Warnings | State | Checklist Template | Type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
5962ae52-52e0-47f0-be8b-a55144948af4 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A101 | WD01.4
362dfdae-a1ab-4d7e-ae47-16da4a95e074 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A101 | WD12.4
6b93dbbe-e564-41cd-9008-a6c5dd4fffa5 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A101 | WSD07.8
7ac24946-9b5c-4d74-bf46-5449644ea9b4 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A101 | WSD08.6A
abaa5bbe-61be-4bce-a14b-7bbc130fbdce |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A102 | WSD02.6
35ae2ff2-86aa-4583-97ce-18b8c859e239 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A102 | WD13.2
c748c4e2-a784-4ed9-a033-daf2dd68d52e |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A102 | WD01.6
99fc5684-9143-4c0c-afa4-91af00cd50a1 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A103 | WD01.4
3317fb3a-6bfc-490d-8c66-216ef7de92dd |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A103 | WD04.2
fbbb7492-6207-47b8-8b2a-14e94c11b9e6 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A103 | WD08.6
05759902-9f1e-47b7-85c2-697887ae1eed |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A103 | WD12.2
db977268-830f-4ba6-bfa0-a39462207040 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A103 | WSD08.8
cf036a78-6c31-47b7-b391-1a6d43ddea17 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A103 | WSD09.3
eb0a7c26-e9f4-497c-b35c-d7a4a5349f0f |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A104 | WD01.4
76ba54b1-67ea-41c4-834a-87c8ebc77305 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A104 | WD12.4
df447b1a-920f-46b9-9f16-7b45a5ef1cba |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A104 | WSD04.4
a0e772da-2abb-443f-8405-5ad0a35f63dd |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A104 | WSD07.7
b666b0a3-6636-4d50-9ac0-4b29d7322e98 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A105 | WD01.4
709d228a-f7b4-49c6-a413-6b90a27ec96c |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A105 | WD11.4
4081a318-838e-4f10-a863-c2e14da22d2c |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A105 | WSD03.4
3a902b5f-c5f5-42a6-bc8a-b9cd1bc3e973 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A105 | WSD08.4
c8b54940-0b47-4645-b725-fcc80b961e73 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A106 | WD01.4
be777340-96f3-407b-af83-369d849652b2 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A106 | WD12.4
57021f13-9751-4bca-99b7-284ba594e5b0 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A106 | WSD04.4
6fe5254d-2db0-4da9-b6b3-c77641cadf2e |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A106 | WSD07.7
b29e6ba1-69f1-4c07-8e3a-15546af458fb |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A107 | WD01.2
428a54cd-0656-4b7f-a6ce-c6abac00b3a3 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A107 | WSD08.10
2d28e25a-7132-4e39-ac5f-7754fe8a1ccf |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A107 | WD09.2
9ffff965-5474-4a8b-a460-73f4ea6470ef |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A107 | WSD03.2
8d08a128-f577-4bed-8d69-95c4075eedae |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A108 | WD01.2
dea6ca8e-2233-4938-b1a7-7c37e4663e33 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A108 | WD04.2
8f00c6e3-6a1a-4996-9dce-521195f473c4 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A108 | WD07.9
117a72a4-832a-4423-8fb2-530161e2cd3d |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A108 | WD08.6
5ed590f7-a509-4495-ae93-212287005cb6 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A108 | WD11.2
c828ffc2-bcf6-4f2f-a517-a8c9531e9d86 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A108 | WSD07.6
d71327e0-8ea8-4c81-b0c9-95451d89b9d9 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A108 | WSD08.2
9f9626b8-eb0a-4316-aca6-0fde0511cfd9 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A109 | WHD05.2
556c08a4-e00d-4b9a-918d-1fb065b024a8 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A109 | WSD08.6A
a65f538b-94f1-44ca-b8b8-d137c9b47369 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A109 | WD10.7
dfc0cf3f-d898-4dfa-baab-23e69aeb94fd |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A110 | WD01.2
786bd484-a38b-4e2e-b02c-0e58b1096f23 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A110 | WD10.4
d7c194cb-4e59-4e06-9d57-1039dc81a08e |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A110 | WSD04.2
26bf3adc-25fa-4d2a-8423-028bb37cb4da |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A110 | WSD07.5
8a16ba48-5af8-4806-bda3-678a230823ec |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A111 | WSD02.6
310f1a2d-59f1-4764-9995-52304f5bd1bf |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A111 | WSD07.6
53a56b32-5f2b-462b-83e2-ead6e6946cb9 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A111 | WSD14.1
ce7bfaeb-8b01-48fa-8132-73549c87da0e |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | A111 | WD07.11
1f705d4f-8cda-4a8a-ad7d-70f4e80bc24d |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | Others | R104 WD21.1
a7725262-dd8d-481f-8b1f-bcea680a262b |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | Others | R104 WD21.1/WSD13.1
5cd26cc8-7119-46e5-974b-19048ae871fe |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | Others | R106 WD30.1
7254a2ba-cf1f-498d-84f5-8d791891e933 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building A | Others | R116 WD17.2
14bbbc0e-00a6-4c1d-8817-0ea92af1dbfd |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B101 | WD01.7
e090fddd-ba2a-4732-a2a8-b1bdd575c2e1 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B101 | WD11.4
671284d7-9bc9-42ad-b433-2b074ddf051c |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B101 | WSD02.4
eda939b3-c9c9-4674-945a-675e2f4f6723 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B101 | WSD03.4
2748746f-58b4-4bbc-a9f8-3414b9460d9d |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B102 | WD01.7
befae697-36fc-42f4-9fd2-8adfe3c3dbd2 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B102 | WD12.4
ef3005a1-e35f-4d61-a623-1380d17679f9 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B102 | WSD01.2
e6006494-e9da-4833-b92c-fa1b1bd4d0cb |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B102 | WSD04.4
b5248f10-29af-47a0-9218-71ca24b46f54 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B103 | WD01.7
d9ff5148-e5c1-437f-88fc-0af00fc4895b |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B103 | WD11.4
dfb4806e-165b-4a98-bb18-048b62351d0e |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B103 | WSD02.4
87c0aa64-4243-4647-ba5c-8d4d607e9784 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B103 | WSD03.4
fec8a352-37e5-4df8-b12b-8b377c82e33d |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B104 | WD01.2
c49c57d1-43d8-4656-bc76-64f0c1965bac |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B104 | WD07.9
32f53c0a-1e5a-40e3-a05b-aae2c254039e |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B104 | WD10.4
3bac1ef4-5887-4297-8878-7f71b2fb6f3b |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B104 | WSD04.2
2d3803f8-bac7-4519-8981-fc751eb82683 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B104 | WSD07.5
3c5a6431-c606-422c-aa9b-f331322ad84e |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B105 | WD08.2
f581b429-47d5-472b-9dd9-bf3ef005ae36 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B105 | WSD04.2
fd43c3a4-6b89-4ccb-bf23-4a3b0a542f1b |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B105 | WSD08.4
f83bbef6-e871-4cc1-b251-15780ceaa0ef |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B105 | WSD16.2
c3e9e6a1-d31e-4e0a-8cf3-54a09d12d62f |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B106 | WD01.2
62bcfb4a-3b2f-4d49-adce-01ac735a5d4a |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B106 | WD07.9
d28fd0a9-ec7a-45c0-b02b-fc655617abb6 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B106 | WD10.6
12bf2faa-2226-457d-bdf1-f628ade83b03 |  | fail | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B106 | WSD04.2
be2f083d-6d7c-46eb-8e63-82d4df3c4dc6 |  | fail | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B106 | WSD07.6
4dc7c9c8-61a7-4c01-8a2c-356d3dce550b |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B107 | WD01.2
241d6bdb-6258-4e36-a622-491a067bb0f7 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B107 | WD08.2
2acb0b50-112a-4770-844c-70c732b2b79c |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B107 | WD09.6
1e8ceff0-f1a4-418b-b6c3-cfe05077db21 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B107 | WSD03.2
c48c82ef-9dd0-4131-b9fc-b804345b10d6 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B107 | WSD08.6
b0ffc96f-a0fe-4186-aea6-91ca947f8af8 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B108 | WD01.2
07cd61e1-4e16-4a9d-8ca0-3eaa1fc3bb26 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B108 | WD07.9
62b08cec-7cce-45f1-9077-f105e51001d6 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B108 | WD10.4
86191237-ec2c-4aef-b2cc-eef3f3ade9cc |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B108 | WSD04.2
426ec02e-a7ca-47f5-9d38-b2dd285bbbd6 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B108 | WSD07.5
f27e065a-2b04-4ab3-8993-b9383ca2d272 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B109 | WD01.2
830a2426-25de-478b-af7a-765fd560977c |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B109 | WD08.2
e6a9dbb0-9fde-4bef-845f-95ea2e1e463b |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B109 | WD09.4
efb7fc81-ed18-41f7-acab-eed5b7459409 |  | fail | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B109 | WSD03.2
5d7c8d18-879d-4612-a94e-8161d2dbf331 |  | fail | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B109 | WSD08.2
edf04809-f18c-4531-9c68-c8f6ad06f219 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B110 | WD01.2
1f248c4b-e6d6-4341-b6e6-1b7b8c720e5e |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B110 | WD07.9
170395c5-5c20-4de7-a8bc-13fbce80464e |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B110 | WD10.4
88f50f59-5c4d-4e4d-a7cd-3ad689bfe3ff |  | fail | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B110 | WSD04.2
5bc5c2fe-82d4-463c-8f7a-b11db362053b |  | fail | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B110 | WSD07.5
21c4ccec-840e-4f7a-ac52-9a876bc7b1a1 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B111 | WD01.2
f69fe46a-9489-4759-80f9-885510f5f3c3 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B111 | WD08.2
98f7f524-9240-4aa1-9511-3e9fe9b13d8c |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B111 | WD09.4
328d9444-c03a-4815-8d75-05d2b23876cd |  | fail | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B111 | WSD03.2
4494cfed-e073-4aa2-a70b-bf1f62b02784 |  | fail | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B111 | WSD08.2
b0622f17-9e40-44b2-9a64-816c339a8ae7 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B112 | WD01.2
767af352-ec4c-4fea-9822-53d52282b479 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B112 | WD07.2
830965f1-636d-414b-89f0-418c0c7fc4b1 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B112 | WD10.2
2db30d15-a24e-4cae-891c-ef709787071a |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B112 | WD13.4
4c99ce57-e368-4b6c-b393-36d06383ca63 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B112 | WD15.2
0949a332-14e7-4452-91e1-2fd52f5a3232 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B112 | WSD08.2
a8536be3-92f1-40d9-9823-16f0c3e948a8 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B112 | WHD05.2
a0e5edf3-f0c3-4d2d-8559-004745d20fbb |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B113 | WD04.4
961ebb95-ba1f-4692-8493-1fddd04644fd |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B113 | WD14.1
5c01ee69-c528-44be-a613-6387dfc2e91e |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B113 | WSD02.5
24274758-b002-4dff-a5be-975f668c2b39 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B113 | WSD09.3
3bcaf470-cf13-46e6-99cc-982b1319b089 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B114 | WD01.2
39023871-4ba7-4c2b-a895-2644ded67b7c |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B114 | WD08.2
ce3fedc2-7051-44cb-a019-b956ee427a56 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B114 | WD09.4
71abb7b2-1e43-4520-942c-bff3bb3f58e1 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B114 | WSD03.2
288e48ea-cae6-4885-b5bc-8d239925542a |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B114 | WSD08.2
cb658384-8ad5-464f-a2c4-dbd8a02c7cd3 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B115 | WD01.2
c6840dc1-e605-4f64-8287-d35fbb98c902 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B115 | WD07.9
da7ad334-64c0-4d55-bc46-e4d1da5c1d57 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B115 | WD10.4
583d92cf-6499-4c58-a2c3-7328f755b0fe |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B115 | WSD04.2
83a7ab53-79e0-4f4f-91ed-03d4b00b1bb2 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | B115 | WSD07.5
dddc5dc4-5c55-4244-8dfc-2c220a85fe36 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | Others | N102 WD02.2
35bac51e-ea1b-446e-8ce1-b3c3595b009b |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L1-Building B | Others | N102 WD20.1
82917336-f213-483f-86e3-01ed7855cfc1 |  | pass | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A201 | WD01.3
c869c0ab-9073-4045-b08c-575badd21d55 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A201 | WD12.3
ae9973ab-38a9-4bb5-91af-296d8b142228 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A201 | WSD07.1
0a0af0bf-75c4-408e-9818-b5c4ca0d4bd2 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A201 | WSD08.5A
ee22b294-5c52-4af2-ac74-7898a2df1a1c |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A202 | WD13.1
84987fb6-4075-4ba0-954b-f47f73b4fd02 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A202 | WD01.5
cdf845f8-346d-42de-834a-e795508b6fff |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A202 | WSD02.2A
c491302d-2111-4709-aff2-3774cc29678a |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A203 | WD01.3
f4ec901d-4c1a-4ee4-8841-85352951f4a1 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A203 | WD04.1
0c64bb4b-70b1-40f7-8c27-e02846dc127c |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A203 | WD08.5
350cfde6-f615-4ac9-ae93-391e44b3589d |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A203 | WD12.1
dfd35ba7-fc45-40ef-90a9-63e3896bf86d |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A203 | WSD08.7
c9b6306f-0330-49bc-b7d9-c78867e59fc3 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A203 | WSD09.4
bdb8f2c1-2306-4179-8013-64bdd74fb4f0 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A204 | WD01.3
544d0b21-6477-4818-8d9a-46d4fca04ac9 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A204 | WD12.3
ded8b551-9428-46eb-9e0e-051109c0e193 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A204 | WSD04.3
4c3d4023-6219-4cfa-b3cf-5e7b5a8b3300 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A204 | WSD07.4
2fb08758-ddb2-4cfe-8b00-2054ef86fd24 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A205 | WD01.3
843c6e62-6690-4bee-8abf-3a7f2a2b0779 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A205 | WD11.3
fc754cc8-3b21-45ce-bcac-3bce79af58f5 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A205 | WSD03.3
3298b1bc-7629-4b5f-8cfa-9acb7bfc9640 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A205 | WSD08.3
ede489c2-241f-4c97-a3d1-37dc07f80876 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A206 | WD01.3
64d42e4a-6d22-4d4e-bf08-2680de0d8d47 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A206 | WD12.3
845e6d4b-b624-40a0-99fa-b961659f5d47 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A206 | WSD04.3
ee59b226-c5b6-45ad-847f-c18846f43c92 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A206 | WSD07.4
583561af-b53b-44b4-b607-da121110be89 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A207 | WD01.1
094a3bd1-752f-44e2-99c6-cebcc7128ae5 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A207 | WD08.5
0a5ce310-dd2e-42c6-8cab-9ab655240428 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A207 | WSD08.9
a7490665-582f-49c0-b630-fd9ec6c23917 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A207 | WD09.1
ed9edfab-e396-4a3a-aa4c-8aac1bfffd03 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A207 | WSD03.1
98575e97-2cfa-4050-87e2-9bf3746b5f14 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A208 | WD01.1
0b5aa701-0a6c-44b3-bc5a-ae90864e7362 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A208 | WD07.8
1f2687b6-ae1a-4ff5-8f47-f8714b9d7616 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A208 | WD08.1
150952fb-b15f-4919-9c8f-9f07da3b1a31 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A208 | WD11.1
319a0182-2fff-46f9-9e3a-5dd10d47f786 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A208 | WSD07.2
7744b7b9-38a8-451c-b46c-e3ec63f3f4de |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A208 | WSD08.1
c3951b24-e88a-4b78-abe5-556de885b6f3 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A208 | WD04.1A
7c8945b0-3cc0-4149-a9ae-7cdf63825e9f |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A209 | WD01.1
474678e5-d267-49f6-a837-f00c1b7cdf67 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A209 | WD07.8
754cbf59-3af4-47ac-ab8c-d53df98f11d2 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A209 | WD10.3
0f9fcef9-76b9-4834-bfbd-180435ca5cb6 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A209 | WSD04.1
9986d3c9-2b1d-4da0-abea-4ab3cc2de2d0 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A209 | WSD07.3
2987fcc4-2ee4-4263-a7c2-22b8e5a50f8e |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A210 | WD15.1
9c868772-ec41-4b57-8b06-77cc3f4bab8d |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A210 | WSD02.2
c81d6a11-4b03-4950-b18e-286dfe320b8f |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A210 | WSD08.3
cfc40461-193f-43f6-b4a0-be2883654ba5 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A210 | WD06.1
ae8872bd-2b7f-4000-bc57-55442ecdcaa1 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A210 | WD07.10
83421a3b-7204-43d9-9552-3d705d0b9210 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A210 | WSD07.2A
7f97ae79-f292-406c-8bb7-36ce1b15825b |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A211 | WD16.2
d559a7a5-01d0-4516-a76d-1964a1e60f30 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A211 | WSD04.3
42960948-49af-47e6-be95-0e0fad183a4e |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A211 | WSD07.4
85d6ff84-b6f6-49a7-ad84-c16b22afd143 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A211 | WD09.1A
fdee484d-4ea9-4785-80d7-8bf3a912353c |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A211 | WHD03.1A
9e8fea8c-cb59-4f2f-ade3-9cfc8717850b |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A212 | WD01.3
a9882e25-3e0d-4a25-a4a2-61f6412af500 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A212 | WD11.3
2ff45ddf-6d81-406d-9606-b2e9ebc06f16 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A212 | WSD03.3
569e0535-9f97-4d2a-a65f-cc4274ad1735 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | A212 | WSD08.3
9af0349a-9126-45dc-adfc-25771aa20198 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building A | Others | R206 WD17.1
8361b0a1-8974-4b9b-b7f1-4d0b6d3f8fcd |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B201 | WD01.8
a26f99db-ad3a-4aa2-bc95-d98cf3e97006 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B201 | WD11.3
d43268fc-186a-4780-ae89-92410fd1aa0f |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B201 | WSD02.1
904f8d42-e37c-4b69-8321-30a3ce2693c4 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B201 | WSD03.3
2c8abe2b-3a01-4496-9e6b-8b8da2b08063 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B202 | WD01.8
5b3220e9-e68a-4e45-8ce0-2ac3eabc018f |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B202 | WD12.3
d8dcdd4b-83fc-47f1-914e-82773e81588c |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B202 | WSD01.1
5ba00088-e3ef-48f0-822d-ba33f0c0aedb |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B202 | WSD04.3
aa39915e-da07-43b6-9266-b5b102bdc939 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B203 | WD01.8
f13c59ec-d157-4e13-922c-fffb162dee89 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B203 | WD11.3
c783e2a9-c36e-4618-b446-9b79c8ec1c97 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B203 | WSD02.1
5e2f1a25-d103-4fef-9bde-aebacfbf322e |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B203 | WSD03.3
8494f5eb-ad3b-4b09-b9d5-f3bcddb74664 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B204 | WD01.1
e9a85840-3ca2-4202-8558-538b0387c869 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B204 | WD07.8
dd1910e5-3918-496a-bd9e-d5a1259a6ce8 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B204 | WD10.3
9200b300-b9df-41c5-80c1-09d18478c833 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B204 | WSD04.1
f0933474-0d9e-4971-9c92-9e2386201629 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B204 | WSD07.3
0f6bd0f6-b999-4caf-bf8d-f26813da3785 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B205 | WD08.1
3c3a441c-6896-4959-8b6a-c027dc0ae4b2 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B205 | WSD04.1
3567bd65-931e-43da-a9d1-b5fd2461f6ea |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B205 | WSD08.3
4d03a392-ec30-49e7-bf4a-fbdfefb8ef99 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B205 | WSD16.1A
9f1d8336-d119-42be-892e-1c959ecc4549 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B206 | WD01.1
54bfe90a-f1fc-44a4-9ca4-f08e40cf996e |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B206 | WD07.8
c0552314-cfec-453a-ad8f-46b77f3ea44b |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B206 | WD10.5
876a9ced-5633-4e37-a6fd-f1df6c93366b |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B206 | WSD04.1
489bae3c-2d76-46bd-a323-addef30ee988 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B206 | WSD07.2
13c4af83-b98e-4a0f-a2e1-6c1e1e417c86 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B207 | WD01.1
c3dbe5c2-5bfb-4fb3-8749-fba281fcab6c |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B207 | WD08.1
ba2372bc-1dd1-4156-bd4b-14f2cd764aaf |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B207 | WD09.5
cba9f2cf-fe72-4978-987d-f87007fadf1c |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B207 | WSD03.1
ea195469-e100-41ff-88c7-0f619449abd5 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B207 | WSD08.5
bd43a640-7ad3-418f-a556-00274aa94cd7 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B208 | WD01.1
13add815-831b-4fcd-a491-8e1d77780341 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B208 | WD07.8
f5c4d98f-179e-4718-a876-4e4c33b5a161 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B208 | WD10.3
e5ef051b-7496-442d-aefc-03b00273add2 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B208 | WSD04.1
38d6e956-e257-46d5-abc5-e0844f4c1ac4 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B208 | WSD07.3
9d42dc19-1f4a-46e2-850c-623fc76d9505 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B209 | WD08.1
bb56a074-32b5-4485-95f9-bcedd228010f |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B209 | WD09.3
7e2bfc6c-7fa3-42ea-b3ff-f612880dd50a |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B209 | WSD03.1
a2ff9072-6363-4268-ba2e-ee6462f76253 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B209 | WSD08.1
aa471a00-3a69-4978-ab6a-063687cce1c4 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B210 | WD01.1
660c4aee-df0b-4644-a7b5-6731e469ee67 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B210 | WD07.8
71c567d2-0642-4ae8-a3bb-80b0343535fb |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B210 | WD10.3
705ec30e-2f8b-4ada-b814-f2aed96ccf49 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B210 | WSD04.1
1cb51d5c-2262-4cda-9691-642c5e8750ae |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B210 | WSD07.3
224eff13-8cb6-4430-82a2-2218f60c7b0b |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B211 | WD01.1
c53f8e56-58b3-4995-bcda-4bf414dc3278 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B211 | WD08.1
bd22d347-636f-49de-8a42-a67114ae7b99 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B211 | WD09.3
060775d1-04fe-4ac3-a112-558c0c4f05c9 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B211 | WSD03.1
02e81527-ed34-48fb-9388-54163b577848 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B211 | WSD08.1
9bff1fec-9856-4bdf-80b5-dd921c87b15b |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B212 | WD01.1
30baa1e2-22cf-44ef-a818-76c181bcb798 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B212 | WD07.1
95baf654-baf9-4799-bb2d-0e9d9ee7772a |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B212 | WD10.1
e8e32279-ae2d-4dcb-92c5-c505d36dd9fb |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B212 | WD13.3
1d174ad1-5cdc-4a1e-92b9-17673ebfc4b2 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B212 | WD15.1
928f7269-a807-4146-bf1c-3c234c52652d |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B212 | WSD08.1
2d9f00f9-e8e4-45e1-b205-62fc7cda4529 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B212 | WHD05.1
d93523d4-cfb6-4c64-9897-83f819564aa2 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B213 | WD04.3
655fd34e-9bcd-4de2-9feb-663b30dfde9f |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B213 | WD14.2
2b3d4586-1c46-4bf8-b089-2e1b1b41504e |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B213 | WSD02.3
3f856037-951d-4f03-a1ed-01bbab65fd32 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B213 | WSD09.1
b0e9588f-f8cc-4be8-844c-fe9a587872d4 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B214 | WD01.1
f5dc8a81-6307-4f70-8b6c-77e1a8ca3aa3 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B214 | WD08.1
6a8c09ad-1dba-460c-b533-208aa02e9650 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B214 | WD09.3
926a3818-fd3d-4d2e-becf-27e4749e490b |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B214 | WSD03.1
800844ef-9c77-462a-acc0-5712e633b5e1 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B214 | WSD08.1
6a3ea61f-bc69-4f1b-a616-742a42e79087 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B215 | WD01.1
91fd7344-8111-42dc-aa11-bef15569665d |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B215 | WD07.8
04041838-6894-4db1-9451-88a0c57be839 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B215 | WD10.3
fb02fe66-48d5-4ba3-8964-da4c6bea8893 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B215 | WSD04.1
7fda00ba-69f9-4d76-823c-b6ca085708b4 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | B215 | WSD07.3
3f6b1e02-ed55-4e1a-a92c-0b655621157f |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | Others | N202 WD02.1
d7970955-157e-4945-b038-2aa8a89be665 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L2-Building B | Others | N202 WD20.1
0ed90773-f919-4bbd-ac60-bdbbd520fc87 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A301 | WD01.3
df251dfb-cd68-4a9f-8593-83319363cfd6 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A301 | WD12.3
8da952ce-c657-4b8d-8b7a-8f2b8d115f94 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A301 | WSD07.1
c9dbdfd3-6fc1-4b90-b40a-55d5b672950b |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A301 | WSD08.5A
72bbf449-1cab-4f72-a661-a93fb17527a3 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A302 | WD13.1
7568195e-527b-4215-a416-23b0f4c84905 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A302 | WD01.5
ea6074a7-7543-43cc-b30e-4a413c952f9c |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A302 | WSD02.2A
7cdf8e81-2382-4bae-bb58-ab0825d6c357 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A303 | WD01.3
3212a0c9-211c-4821-99ae-89e57867f59a |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A303 | WD04.1
bac43e37-f32c-4c70-9f73-3dac81fabe1d |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A303 | WD08.5
9935df76-bb57-4095-ae93-73c7f4b1ba91 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A303 | WD12.1
09ab5871-a3b0-42dd-8f06-348d0639f7b8 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A303 | WSD08.7
026b4141-bc79-4b5b-aaa7-548c3435822d |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A303 | WSD09.4
2af41f55-f888-4bfe-b61b-f0e07f03c279 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A304 | WD01.3
74f5626b-1ca6-4aa5-a839-ac2af3dad971 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A304 | WD12.3
5fa39501-76c0-446a-9a15-18bbdae28874 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A304 | WSD04.3
166e4036-463b-4c38-8e27-72456879f91f |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A304 | WSD07.4
bdbc5536-5b34-4ff6-88c0-035b681699e1 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A305 | WD01.3
d0b51397-5cc3-442f-aab8-11bed85bd49f |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A305 | WD11.3
8796eaf9-d351-4330-9d83-30802ae527c1 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A305 | WSD03.3
0d315f16-77c0-47c8-a560-d8dc7d83db31 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A305 | WSD08.3
477a0eae-485d-4677-b0ff-26e315012e94 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A306 | WD01.3
2a90941f-19ee-494b-81fd-0e666364a605 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A306 | WD12.3
0dbf16cc-50a4-41e8-ae35-43b718f35708 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A306 | WSD04.3
47787a52-0a8c-47f4-997c-bd280278b44b |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A306 | WSD07.4
ff9a0e6a-4368-449d-92e4-d44938ff4eff |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A307 | WD01.1
8e1ee835-ccc2-423a-8ff7-a699d4a9813c |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A307 | WD08.5
4fe05786-f3e6-42b0-91d0-29812612af50 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A307 | WSD08.9
e9c2a8a8-71ea-47c2-a198-1f4f77207fc5 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A307 | WD09.1
bc93b9c2-5a28-432c-9ba5-d28218a6de16 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A307 | WSD03.1
0f4e8712-89fc-4650-8c25-1b8c2ad6bfd1 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A308 | WD01.1
4b7a3a0c-9341-45b1-8cb0-71a4318b4950 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A308 | WD07.8
2d2c5543-fd98-4369-9b41-c04ddbcc79da |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A308 | WD08.1
563d7082-197c-4aec-956c-8e612337cef8 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A308 | WD11.1
34e6abfd-6ddb-4799-be1f-50bd7ae0cef9 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A308 | WSD07.2
2983701c-5b28-499d-a6ae-30b7fb851264 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A308 | WSD08.1
4abcb837-53f5-4492-9b95-6395c6f80764 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A308 | WD04.1A
ed2efeb7-81b2-4d2c-b8b7-719638581afd |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A309 | WD01.1
503b5c51-e9fe-4d22-ad5e-8c21ac079040 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A309 | WD07.8
e32a86d7-fa82-4429-861e-8dc2ad0e7023 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A309 | WD10.3
8ed5c521-df2e-43b6-9c6f-61cf9264fedf |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A309 | WSD04.1
64a46a3f-9236-4600-a08a-a75d6b888c35 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A309 | WSD07.3
5801f8dd-f2a6-4d19-9df7-db135cd4190e |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A310 | WD15.1
b9ae5680-5c0c-45d5-bbf0-8f3a80b3e50f |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A310 | WSD02.2
bc0424e7-01d4-4bfe-8687-fec4d1a5e5d7 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A310 | WSD08.3
d51ec79c-623e-4859-945d-fbd8b3e60036 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A310 | WD06.1
35e31ea6-2c0a-47e2-ae21-30ff4bc5a64f |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A310 | WD07.10
11bda1dd-ed25-44ae-9c6b-dc74668f1384 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A310 | WSD07.2A
84954fa8-15a4-4081-a1a2-8b8621043d9d |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A311 | WD16.2
d21a4cbf-a203-4d3d-944e-55f85a54b9d4 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A311 | WSD04.3
2aa10958-7fcb-4527-88ca-a45a34139b8e |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A311 | WSD07.4
7a27729a-f3c4-4b75-ba06-778cf5f75b38 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A311 | WD09.1A
b385c14e-400e-4fe6-b4d4-2aacad948ed4 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A311 | WHD03.1A
bd10d676-d1e1-426f-b839-7c89badc5aae |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A312 | WD01.3
2061533b-233e-4122-90e3-b9ad446c6aba |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A312 | WD11.3
2dd8bc9a-7318-40dc-8f2f-b7244be61127 |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A312 | WSD03.3
1d0b5387-e39d-4bc4-b7cd-cd5071cfb2eb |  | work-in-progress | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | A312 | WSD08.3
eeeb611a-8d75-43e4-a4d4-a1903b64b1a5 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building A | R306 | WD17.1
f7ab22c5-7ac6-4a44-8838-0757ca25beb8 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B301 | WD01.8
fefa41a9-7cc3-4ad6-b898-b0df3fe2b83a |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B301 | WD11.3
56424338-3f44-4e9c-8f63-87423c08512d |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B301 | WSD02.1
1e140c3f-cd54-4f07-b38c-3dec346af753 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B301 | WSD03.3
508d9967-3cae-44f4-983f-34613a81cd74 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B302 | WD01.8
6afc124d-a2cb-41cb-83d0-1fc4a289f730 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B302 | WD12.3
9221ce2f-d382-4450-8c88-ff567ef32c36 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B302 | WSD01.1
452bac2a-63cb-4c09-a819-b19f01093c13 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B302 | WSD04.3
e9cd55e4-5132-44f5-944f-e15f02544fe0 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B303 | WD01.8
98b04275-ce5a-49d8-afe6-17d017059904 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B303 | WD11.3
d0c6d941-feb8-44c9-8b9e-516648e920eb |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B303 | WSD02.1
25912cce-7984-424b-8f2e-9e6895cae2ec |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B303 | WSD03.3
6a05423b-31c8-4961-b848-845ba99a08c5 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B304 | WD01.1
12583c33-3def-4d6c-aed9-2b958c8edf9b |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B304 | WD07.8
76c38124-3048-42ab-934b-4b3a2e7b713b |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B304 | WD10.3
64bd5382-131c-44ed-88a2-3c8cc971851f |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B304 | WSD04.1
b1f80edd-5b49-409f-b9ed-23a5ca11a244 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B304 | WSD07.3
d0e946d3-b72b-47ee-911a-0ae487b24db8 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B305 | WD08.1
582c45ba-1c75-4525-ba5f-861e477f1ed2 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B305 | WSD04.1
0358a287-5884-47a0-9be6-541513b6bbbf |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B305 | WSD08.3
45cb136d-8986-4870-8417-b318c514beb3 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B305 | WSD16.1A
50a442ef-7dbc-4a7d-bb91-97f9ea7fbe71 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B306 | WD01.1
19a724a7-41d7-4d4a-8135-be648aa6417c |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B306 | WD07.8
19e5975d-4a32-43f3-9425-900e6fbc6caf |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B306 | WD10.5
d49819ee-2725-4286-a096-95bb6880f2d8 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B306 | WSD04.1
0aa8fb7d-78c3-44ae-bfb5-ae4e058b169e |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B306 | WSD07.2
0e9f7a53-6d8a-4c8f-970d-5bbb6d9719fe |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B307 | WD01.1
1b47941c-c53f-43ab-b024-472c30342c1a |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B307 | WD08.1
87325dd1-b4e4-4832-aa3a-7d472b23c9e0 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B307 | WD09.5
c495f438-3e44-4556-be68-75dbb5468604 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B307 | WSD03.1
9e6a3c36-8c47-4f6a-ba6a-28698bf900d2 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B307 | WSD08.5
2c353efc-116f-424f-9009-df4a0ceae3ce |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B308 | WD01.1
d95b98c0-b22a-4953-826d-6cf43963345c |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B308 | WD07.8
e899f913-a0d3-45ff-a087-100e6e019308 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B308 | WD10.3
f409878e-28a3-4ddd-8bc4-265ee2eedfc4 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B308 | WSD04.1
0409c716-d9ab-4969-9d72-ba2e07272197 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B308 | WSD07.3
229bfdfd-ea9b-4dbb-bec8-055723c8e574 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B309 | WD01.1
ce8445e2-d688-410b-83e9-bc35132a739a |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B309 | WD08.1
a4e9dbd6-2359-473d-8cce-351efcb99507 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B309 | WD09.3
a5059cf3-2ea7-4268-8b8c-062048ac3e58 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B309 | WSD03.1
06f91f87-c4e4-4017-aa29-eb1e50858454 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B309 | WSD08.1
12b5e0c5-b13a-44ed-b88c-1613cd4c0594 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B310 | WD01.1
28578ab7-69b0-4d22-8410-1287f8053783 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B310 | WD07.8
24087848-103b-44f4-a715-b813cfc48eeb |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B310 | WD10.3
6e8e23b0-10cc-4394-b0ec-aebe84671210 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B310 | WSD04.1
5b30abf6-a8a0-4bd1-bb0f-b5f20e970904 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B310 | WSD07.3
b9fc5d17-9b34-445b-bca5-9e9177886042 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B311 | WD01.1
aa521df7-58c0-4cb4-8e9c-668cee88d511 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B311 | WD08.1
852d9343-0d51-4fa9-945b-f951db926f2c |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B311 | WD09.3
a1ca52d1-6282-4c52-b615-30bd75313a70 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B311 | WSD03.1
4d961701-558e-4bf5-99b1-d44a257809f5 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B311 | WSD08.1
04b4def5-4e91-470b-aa1e-6209e5ff3283 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B312 | WD01.1
b3515a51-c3b8-40d2-aa49-35d46cedb90b |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B312 | WD07.1
4537610f-5d7d-44ed-90a9-97433f06c4b8 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B312 | WD10.1
db02d602-744a-429b-bd5b-1121207e4ea6 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B312 | WD13.3
4b166c01-ab23-4d67-80ac-30be3384479a |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B312 | WD15.1
c318eea2-5229-4ba7-a3fa-9db003780a66 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B312 | WSD08.1
dd7d323e-101b-4fa0-a2ee-1ceb338e306b |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B312 | WHD05.1
0bee7ca6-a7fa-46af-a09d-b050d1893d37 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B313 | WD04.3
4eec4c4f-74a0-4688-96f1-90322d2919c6 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B313 | WD14.2
7411d927-cb54-4278-a334-f4193cb25f88 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B313 | WSD02.3
8d34bf26-0254-4809-b626-f4c489f2542c |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B313 | WSD09.1
9ec4e318-d568-46b5-90e4-5ef90972d6fe |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B314 | WD01.1
8694d89a-8a58-4596-915e-ac5b7639cecf |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B314 | WD08.1
0e195261-bc8c-4312-b0e2-de9017a3c344 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B314 | WD09.3
59e31a11-debb-44f1-9837-85d4c419ad5e |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B314 | WSD03.1
434a2112-1c28-4291-923c-7ece98e50512 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B314 | WSD08.1
2d86ab04-ec97-48bf-892c-770b6f30e406 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B315 | WD01.1
5bf7b6f3-16f4-44cf-9a5f-9952ce10b49e |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B315 | WD07.8
f62f9afa-81da-4bf9-879d-0aea78fbb997 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B315 | WD10.3
0751fcfe-a0ee-43f0-9f19-2563e63acfda |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B315 | WSD04.1
7b4d930f-f9fc-476e-9e40-5eeb738287dd |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | B315 | WSD07.3
6a7132df-ec99-4178-99e0-0c81d11328aa |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | N302 | WD02.1
41ff317d-e42d-4760-89d1-29b0b60bedf2 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L3-Building B | N302 | WD20.1
9e693401-5527-4c19-9e6c-aca7ebbc9186 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A401 | WD01.3
aa0e515e-453c-4f54-b2a1-ee4f72bdb7a0 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A401 | WD12.3
0d5614ef-c87b-4945-b33d-30fdb17f4b0b |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A401 | WSD07.1
548dd2bd-66fa-4632-b54f-2ff30836906a |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A401 | WSD08.5A
f9086130-21c7-43db-a299-127b44de13af |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A402 | WSD02.2
fec4a3c2-999b-451a-b9ea-eec91b4e7fcb |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A402 | WD13.1
67db2560-1475-4f1e-9b72-f2f02cb9d0b3 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A402 | WD01.5
df3f3e1c-440d-4654-ab7e-2696ee536d90 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A403 | WD01.3
01e2d484-58b3-4f58-bae1-41120367d370 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A403 | WD04.1
d9c4b545-99ec-4327-81bc-deb1ba74487f |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A403 | WD08.5
54f8c948-6056-435b-900a-13c551066589 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A403 | WD12.1
a5c9c489-47ea-4b87-908a-3a05edb5af15 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A403 | WSD08.7
35530c74-746f-4291-aeac-e802f9a553f8 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A403 | WSD09.4
90602b35-e394-4716-badf-29553fbad070 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A404 | WD01.3
bfe5da03-0c5d-4f5c-a39b-c6f1a54b1476 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A404 | WD12.3
779eb123-55ca-4f19-a164-61633721186b |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A404 | WSD04.3
35b3af70-bfc8-4ac9-9e7f-52f4f69d2a6a |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A404 | WSD07.4
98f3eb23-5f46-4a94-9e75-d384fa0b5471 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A405 | WD01.3
15352751-c5f2-446f-bc41-0d11b6e8a31d |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A405 | WD11.3
c0b41071-4033-478e-8283-7522e8603698 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A405 | WSD03.3
ccd051d6-7728-49b5-ac7d-884800d6be73 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A405 | WSD08.3
db2a54b0-6dcd-464e-b6ac-0063e65c78b7 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A406 | WD01.3
6b3adc0b-ada4-463a-aaaa-fcab84060a58 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A406 | WD12.3
4d30dc18-563b-497f-a848-ea33acb56baa |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A406 | WSD04.3
06a64079-b2f0-485c-a97e-297b5f6c32d1 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A406 | WSD07.4
8ab64e4b-b693-447e-b49c-a8db498bf623 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A407 | WD01.1
233574b7-01e1-4f6b-a16d-4be17b16bc70 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A407 | WD08.5
34c02820-3429-43b6-a850-1d9c6b5d05c0 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A407 | WSD08.9
a5213dc0-03a5-4fdc-8ff3-9e3f11e5f3cd |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A407 | WD09.1
4396a701-6522-4051-962d-a6517f3afc49 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A407 | WSD03.1
1c06c7a6-0fb9-4d53-b752-4fec589e5dff |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A408 | WD01.1
7d90ca2f-8609-4c01-b4d6-7601f955a871 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A408 | WD04.1
db1bc571-35e6-419b-af2f-f785e554ba62 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A408 | WD07.8
de35e7cf-a612-45d7-a1e0-9b814766b182 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A408 | WD08.1
4eebd208-294b-4d9d-b673-6d9f66f8c2fd |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A408 | WD11.1
0f01fda6-773a-45fe-aa20-b36f11e97fdc |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A408 | WSD07.2
5405506c-de20-441a-9fe1-bfa6b08fdd30 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A408 | WSD08.1
436ef741-c2a8-4759-a5db-eb9cf47ba246 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A409 | WD01.1
8f20f00d-66cf-41ff-9bdf-25b5861a2a60 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A409 | WD07.8
546779e0-20e5-4131-8146-671bfc8fe37b |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A409 | WD10.3
a690efd4-9a3b-4103-aaeb-b4f8fa84262d |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A409 | WSD04.1
31ba36c5-739e-4539-a3a8-8f17103ad514 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A409 | WSD07.3
1bf1bcf0-f637-4166-82fc-f6fb8d034796 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A410 | WD15.1
be022df8-d67c-4e3a-9b3b-f41b6b817db0 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A410 | WSD02.2
32147804-cbc9-45f9-ba81-6f8574558d3e |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A410 | WSD07.2
c77d3054-a12a-4abf-9adc-fbd4d36a86b8 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A410 | WSD08.3
56ea53c6-a77d-40b5-8a73-12a4bdae2469 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A410 | WD06.1
a7d03892-f98b-47d1-945b-aa9f2bc4d424 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A410 | WD07.10
8a0c790f-d89c-46a8-be43-d5125c94dcc3 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A411 | WD09.1
ab2ab2f1-c336-4dfb-97cf-1a0e1f76ed0e |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A411 | WD16.2
fdaaca3a-a6b1-4820-a84e-40d37d616fb8 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A411 | WSD04.3
bf4c4d86-a0e9-4b05-8a5c-fc90d6341ae2 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A411 | WSD07.4
a033b8f7-b7a6-4586-a0a5-c15c488d3032 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A411 | WHD03.1
c83db3ca-ea82-440a-97e6-c215f2db772e |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A412 | WD01.3
95c49c31-b5ce-4ce0-82bb-3ded48b8065e |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A412 | WD11.3
3e0d6194-4642-401c-a375-ef6ed4e4825f |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A412 | WSD03.3
c4b1bfed-6b7d-433d-8a61-e64a6d20c7a5 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | A412 | WSD08.3
8117f397-20fd-4d23-bd39-f0f6e8e25b15 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building A | R406 | WD17.1
570f1ee5-3ac2-4893-a6e1-52caf61b2547 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B401 | WD01.8
f8cb723e-66e1-4b16-b956-2d73aa46e238 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B401 | WD11.3
687b2544-bf56-465b-8ee2-63ac4e9bd325 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B401 | WSD02.1
c4f50cca-96b1-42c6-8d46-c16c0b0bb498 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B401 | WSD03.3
530ddafb-39b8-48e1-a366-954285a96cca |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B402 | WD01.8
db41f15e-8737-4da3-bc7a-ddcdc6a5255d |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B402 | WD12.3
d56d563b-987f-427a-8f6e-893726caba11 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B402 | WSD01.1
17821c0b-a2c6-4398-969a-d98bee851909 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B402 | WSD04.3
9cb359d8-bfca-4d9e-ac73-33bb51c331ae |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B403 | WD01.8
c858ab17-03c5-4c41-b40b-ec9b5d55da01 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B403 | WD11.3
a558c301-640a-4af1-aace-e442928d265c |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B403 | WSD02.1
811af17b-6ff4-4d63-85f2-ca73e0e288ca |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B403 | WSD03.3
5badcbe3-ff47-4aed-b546-4e4806c096d1 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B404 | WD01.1
2b63c87f-2a95-4964-83bc-2bb22ec01e9e |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B404 | WD07.8
46829506-b158-420e-8a09-8c02e379e64c |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B404 | WD10.3
479858b6-dcf2-4c1a-8254-0aea050e6087 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B404 | WSD04.1
f2141c9f-29d5-4195-b9fe-2e442eef0f7c |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B404 | WSD07.3
818f6284-af41-44b9-a673-347ba288bbbd |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B405 | WD08.1
928716ef-d7e5-4513-8ca7-6852db57ef84 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B405 | WSD04.1
17ffc244-6230-4497-96f4-8466002eb25b |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B405 | WSD08.3
6a026010-7973-4f9b-a5d3-6c1ab086afc8 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B405 | WSD16.1
2adf351a-1544-4471-b1c6-f861dfd69952 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B406 | WD01.1
1e701de8-7b43-4ab4-87e9-9f660515a021 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B406 | WD07.8
37dc15e1-46b0-4ba5-8cdc-cee9d93f54c9 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B406 | WD10.5
33663db0-cb35-4d46-bd2a-442e42ecd770 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B406 | WSD04.1
c63e62df-bc30-4af5-925d-5741b8b08f5d |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B406 | WSD07.2
2912cdf7-01f5-4d99-b943-4dc1c7ab91a2 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B407 | WD01.1
9ef96ce0-c789-40e4-96c8-2e04f842eb5b |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B407 | WD08.1
1b72f96d-4e4c-4279-821e-2228fa35f2e0 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B407 | WD09.5
55f5612d-6441-4fef-9259-ccf981001dad |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B407 | WSD03.1
7f6c7298-f227-4206-9a83-c202296ff1c3 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B407 | WSD08.5
f231eece-ccbc-4bb9-97d3-8ffd289f00a0 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B408 | WD01.1
4362dedc-ca2f-434d-8e4d-d970bfd45026 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B408 | WD07.8
36f41e05-3708-4fcc-8406-810752968347 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B408 | WD10.3
f13c051f-9419-4919-82da-185c8487d297 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B408 | WSD04.1
441b26b3-420a-44f9-82b4-9e3dc4d72633 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B408 | WSD07.3
1cba948a-3937-4413-bb5f-2a17c741bcd6 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B409 | WD01.1
f9dc105a-258d-4341-bddf-24cc59f9f630 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B409 | WD08.1
d02b1d6e-1b8e-4633-a667-b25b887237dd |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B409 | WD09.3
ddc2febc-b6d0-4b79-95ad-a93b53782bb1 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B409 | WSD03.1
3f836f8f-61bf-4bd3-b894-a5218baf2527 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B409 | WSD08.1
d87e296a-61d3-428d-9bfa-ddd070e19882 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B410 | WD01.1
4a831005-ea21-4ff4-ac3a-515d65187333 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B410 | WD07.8
472879cd-056e-4823-b1c0-16ab137580ac |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B410 | WD10.3
d60a8f4e-f887-47bb-b38f-e0a0da65c4c7 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B410 | WSD04.1
ada07a69-6e07-4fca-9284-0e7d6a455bff |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B410 | WSD07.3
f9f61051-a9f8-4b30-a992-a78188355b64 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B411 | WD01.1
8001ba58-5012-46b5-837e-296fbb47d284 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B411 | WD08.1
5b67030d-12b9-4c12-9738-7390c684916d |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B411 | WD09.3
c79d2eb6-3f92-4208-832f-5db658865d5d |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B411 | WSD03.1
41ec1f2c-6f44-427f-9b92-336cf2a8a89b |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B411 | WSD08.1
eb8b8513-4ab4-4b12-a72a-7c6c38317759 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B412 | WD01.1
7bc6abb7-5b2c-473a-9646-afe93a204efd |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B412 | WD07.1
db2f4b0f-8f98-49ac-ab36-7a9973ccb3d0 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B412 | WD10.1
03535b2f-7534-4371-9d73-5cc1485f38f1 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B412 | WD13.3
e6c3ce11-a770-4d83-9dc0-30eef2c048a3 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B412 | WD15.1
5af8d594-58dd-4a02-b375-c47ec46d87d5 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B412 | WSD08.1
21e86211-9e82-4074-a65a-481780467897 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B412 | WHD05.1
41daeca2-e1cd-4b45-9c7a-f26aae663084 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B413 | WD04.3
77a19289-3229-4e2e-a14d-07d2dda61ef5 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B413 | WD14.2
ae4b6d3a-4b79-41bb-85be-fbb9e713b402 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B413 | WSD02.3
62a15866-639f-450c-b7d1-25faee3478bb |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B413 | WSD09.1
26ba59e9-469a-4870-9ade-db9914515e36 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B414 | WD01.1
7ae2d40f-34f0-4209-a154-316207fcb538 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B414 | WD08.1
0dce4c55-e3b0-4442-8a6a-2bcc5da8c20d |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B414 | WD09.3
a41042b9-cd10-480d-8bb3-b3038c6e6d9b |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B414 | WSD03.1
d976c1b2-bb6d-4346-b5de-064a5e74c446 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B414 | WSD08.1
f534bd0c-0932-4205-9cbe-8bd5f0283a3f |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B415 | WD01.1
eb36881a-ea67-485f-b9a5-b98b3547e700 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B415 | WD07.8
2b3a7abd-881c-45cf-a943-47cfc3948b81 |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B415 | WD10.3
6574d760-fdb6-4254-a630-336fbaa5b21d |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B415 | WSD04.1
c78185a0-58bc-4bf8-ba81-9e360fae082e |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | B415 | WSD07.3
26e72dea-0c6e-4bec-a74b-3a853d01a46f |  | not-started | Windows Installation Checklist | checklist | FALSE | FALSE | Site QA | L4-Building B | N402 | WD20.1