## Sheet1
2.01 | Obtain and submit Material Certificate of Compliance for Track Materials; -Track Rail -Track Sleepers -Track Jewellery -Geofabric -Ballast Matting -Ballast 60mm Aggregate -Welding Kits -Wleding Crucibles | IFC Drawing(s) Track Constrction Site Mudmap Bill of Materials | Units to be free from damage, total and types of units for full set validated No signs of discoloration Attach: Manufactuer Cetificates of Compliance | Review Document | Once | HP | Site/Project Engineer | ConQA Hold Point Release | 2.01 - Obtain and submit Material Certificate of Compliance for Track Materials; -Track Rail -Track Sleepers -Track Jewellery -Geofabric -Ballast Matting -Ballast 60mm Aggregate -Welding Kits -Wleding Crucibles | Reference - IFC Drawing(s) Track Constrction Site Mudmap Bill of Materials | Acceptance Criteria - Units to be free from damage, total and types of units for full set validated No signs of discoloration Attach: Manufactuer Cetificates of Compliance | Method - Review Document | Frequency - Once | Category - HP | Responsibility - Site/Project Engineer | Verifying Documents - ConQA Hold Point Release | Date Completed: | 2.01 - Obtain and submit Material Certificate of Compliance for Track Materials; -Track Rail -Track Sleepers -Track Jewellery -Geofabric -Ballast Matting -Ballast 60mm Aggregate -Welding Kits -Wleding Crucibles
Reference - IFC Drawing(s) Track Constrction Site Mudmap Bill of Materials
Acceptance Criteria - Units to be free from damage, total and types of units for full set validated No signs of discoloration Attach: Manufactuer Cetificates of Compliance
Method - Review Document
Frequency - Once
Category - HP
Responsibility - Site/Project Engineer
Verifying Documents - ConQA Hold Point Release
Date Completed: