## Sheet1
PROJECT BREAKDOWN (Draft for Interior Fit-out subcontractor)
I Shephard Interiors (Kevin Hickman)
Stage 8 - B04
B01 - Level 2
Area A
|  |  |  | ALS Corridor- Grid lines | prepopulate | POST - S - Internal Lining - Ceilings
[6 empty] | checklist-flat | POST - S - Internal Lining - Ceilings
[6 empty] | checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
[6 empty] | checkpoint | Bracing, adhesive/sealant & lining layer(s) requirements achieved
[6 empty] | checkpoint | Services/penetrations, correctly formed & located
[6 empty] | checkpoint | Correct fixing pattern/sealant/adhesive/layers installed to align with consented design and specifications
[6 empty] | checkpoint | Any bracing elements completed to design specification
[6 empty] | checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
[6 empty] | checkpoint | Inspections completed and issued to Foreman
[6 empty] | holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[6 empty] | checklist-flat | POST - S - Internal Lining - Walls
[6 empty] | checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
[6 empty] | checkpoint | Bracing, adhesive/sealant & lining layer(s) requirements achieved
[6 empty] | text | Specific products used (photos Required)
[6 empty] | checkpoint | Services/penetrations, correctly formed & located
[6 empty] | checkpoint | Correct fixing pattern/sealant/adhesive/layers installed to align with consented design and specifications
[6 empty] | checkpoint | Any bracing elements completed to design specification
[6 empty] | checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
[6 empty] | checkpoint | Inspections completed and issued to Foreman
[6 empty] | holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
[5 empty] | prepopulate | POST - S - Stopping
[6 empty] | checklist-flat | POST - S - Stopping
[6 empty] | checkpoint | Complete fire stopping between layers of lining & apply compound(s) as specified
[6 empty] | checkpoint | Openings/penetrations/corners & bulkheads, correctly formed
[6 empty] | checkpoint | Square stopping, slimlines, joints checked & acceptable
[6 empty] | checkpoint | Correct compound(s) used to align with consented specifications
[6 empty] | checkpoint | Adequate drying time between coats, no visible bubbling/deforms & each coat is sanded as applicable
[6 empty] | checkpoint | Light check completed to ensure no sheet joins stand out
[6 empty] | checkpoint | Stopping work completed - specified level of finish achieved
[6 empty] | checkpoint | Inspections completed and issued to Foreman
[6 empty] | holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
[5 empty] | prepopulate | POST - S - Painting
[6 empty] | checklist-flat | POST - S - Painting
[6 empty] | checkpoint | Any prep work & sealer coat completed
[6 empty] | checkpoint | Light inspection completed and approved to continue
[6 empty] | checkpoint | Any additional prep work completed (stopping, filling, sanding etc)
[6 empty] | checkpoint | First top coat completed
[6 empty] | checkpoint | Additional top coat applications completed
[6 empty] | checkpoint | Final coat completed as per specifications
[6 empty] | checkpoint | Painting work completed - specified level of finish achieved
[6 empty] | checkpoint | Inspections completed and issued to Foreman
[6 empty] | holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
|  |  |  | Store | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | ACC Laundry | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lounge | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Comms | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Stair 1 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lifts 1 &2 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS/Care 279 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS/Care 280 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS/Care 281 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS/Care 282 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS/Care 283 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS/Care 284 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS/Care 285 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS/Care 286 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS/Care 287 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS/Care 288 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS/Care 289 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS/Care 290 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
Area B
|  |  |  | Corridor- Grid lines | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lounge | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lounge 01 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Hoist | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Store | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Linen Store | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Dining | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Servery | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Care Hub 5/A7-155 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Treatment 1/A7-146 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Stair 2B | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - 257 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - 277 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - 278 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - 237 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
Area C
|  |  |  | Corridor | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Stairs | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Room 1/A7-035 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - 251 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - 252 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - 253 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - 254 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - 255 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - 256 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - 257 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
Area D
|  |  |  | Corridor- Grid lines | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Store | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lobby | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Sluice | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Comms | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Stair 4 & Cleaner area | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lifts 3 & 4 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Room 1/A7-035 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 258 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 201 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Acc Care 202 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 203 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Acc Care 204 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 205 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 206 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 207 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 208 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 209 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 210 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 211 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 212 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 213 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 214 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 215 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 216 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 217 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 218 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 219 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 220 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
Area E1
|  |  |  | Corridor | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Store (West) | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | EDB (West) | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Store (East) | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Store (East) | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Stairs | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 259 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 260 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 261 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 262 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 263 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 264 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
Area F
|  |  |  | ALS Corridor- Grid lines | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lounge | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Stair 5 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 265 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 266 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 267 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 268 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 269 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 270 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 271 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 272 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 273 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 274 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 275 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 276 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
POST - S - Stopping
POST - S - Painting
B01 - Level 1
Area A
|  |  |  | ALS Corridor- Grid lines | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Store | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | ACC Laundry | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lounge | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Comms | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | EDB | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Stair 1 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lifts / Lobby | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Void | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 179 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 180 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 181 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 182 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 183 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 184 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 185 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 186 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 187 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 188 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 189 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
POST - S - Stopping
POST - S - Painting
Area B
|  |  |  | Corridor- Grid lines | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lounge | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lounge 01 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Hoist | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Store | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Linen Store | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Acc WC | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Dining | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Servery | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Care Hub 5/A7-155 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Treatment 1/A7-146 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Stair 2B | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - 177 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - 178 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
POST - S - Stopping
POST - S - Painting
Area C
|  |  |  | Corridor | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Stair 3 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Bin room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Laundry | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - 151 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - 152 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - 153 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - 154 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - 155 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - 156 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - 157 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
Area D
|  |  |  | Corridor- Grid lines | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | EDB | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Serv Store | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lobby | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Laundry | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Comms | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Stair 4 & Cleaner area | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lifts 3 & 4 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Room 1/A7-140 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 158 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 101 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Acc Care 102 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 103 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Acc Care 104 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 105 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 106 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 107 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 108 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 109 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 110 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 111 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 112 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 113 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 114 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 115 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 116 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 117 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 118 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 119 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care 120 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
Area E1
|  |  |  | Corridor | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Store (West) | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | EDB (West) | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Store (East) | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Store (East) | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Stairs | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 159 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 160 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 161 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 162 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 163 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 164 | prepopulate | POST - S - Internal Lining - Ceilings
POST - S - Internal Lining - Walls
POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
Area F
|  |  |  | ALS Corridor- Grid lines | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lounge | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Stair 5 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS165 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 166 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 167 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 168 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 169 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 170 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 171 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 172 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 173 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 174 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 175 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - ALS 176 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
B01 - Level G
Area A
|  |  |  | Corridor- Grid lines | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Café | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Sales Office 1 & 2 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Entry Foyer | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lobby WC & Acc WC | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | EDB | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Stairs | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lifts 1 & 2 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Platform Lift | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Reception | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | General Office | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Meeting Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Valve Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Buggy Storage Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Chemicals Store | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Inward Goods | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Comms Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Waste Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | MSB Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Salon & Beauty Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
Area B
|  |  |  | Corridor- Grid lines | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Craft Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Gym | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Reflection Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lobby | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Cleaning Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | WC & Showers | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Library | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Cinema | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Pool | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Pool Plant & Area | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Activities Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
Area C
|  |  |  | Corridor | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Stair 3 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Games Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | ALS Dining | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Servery | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lounge | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Bar | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Kitchen Store | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
Area D
|  |  |  | Corridor- Grid lines | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | EDB Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Store | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Secure Lobby | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Sluice | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Comms Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Cleaner area | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lifts 3 & 4 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | WC & Acc WC | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Locker Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Staff Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Staff Room Store & Riser | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Stair 4 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lounge | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G09 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G10 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G11 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G12 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G13 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G14 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G15 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G16 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G17 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G18 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G19 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G20 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
Area E1
|  |  |  | Corridor | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Library & Turn Around Zone | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Female Acc WC, WC & Lobby | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Male Acc WC, WC & Lobby | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | EDB Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G1 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G2 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G3 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G4 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G5 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G6 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G7 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G8 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
Area E2
|  |  |  | Secure Lobby | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Nurse Station | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lounge/Dining/Servery (East) | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lounge/Dining/Servery (West) | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Meeting/Dining Room (East) | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Meeting/Dining Room (West) | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Treatment Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Care Hub | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
Area F
|  |  |  | Corridor- Grid lines | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Library & Turn Around Zone | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Stair 5 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Cleaner's Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Sluice | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lounge | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Acc WC | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | ST3 Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | TAZ area | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G21 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G22 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G23 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G24 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G25 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G26 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G27 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G28 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G29 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G30 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G31 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G32 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G33 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G34 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G35 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G36 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G37 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G38 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G39 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Apartment - Care G40 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
B01 - Level B
Area A/B
|  |  |  | Corridor- Grid lines | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lift 3 & 4 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lobby | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Cleaner's Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Acc WC, WC & Lobby | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Residents Workshop | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Washup Area | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Kitchen | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Prep Area | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Inwards Goods Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Finished Goods Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Freezer Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Pantry | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Storage Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | HWC Tank Room | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Laundry | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Linen Store | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Stair 2A | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Lift 1 & 2 | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Plarform Lift | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Storage Room (by Platform Lift) | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting
|  |  |  | Store (by Lift 1 & 2) | prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | prepopulate | POST - S - Internal Lining - Walls
[5 empty] | prepopulate | POST - S - Stopping
[5 empty] | prepopulate | POST - S - Painting