## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | INF-HSEQ CC0375-ITP-012 Concrete Pavement Construction & Checklist - Rev.3 | itp |  |  |  |  | INF-HSEQ CC0375-ITP-012 Concrete Pavement Construction & Checklist - Rev.3
section | 1.0 Preliminaries
checkpoint | 1.1 - Determine lot size
label | Ref docs - Spec. 0161 Quality [Cl 7.15]
label | Acceptance criteria - Lots to be broken up accordingly and outlined on a lot map
button | Acceptance | Yes,No,N/A
label | Key - S |  |  | 0
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Lot map
checkpoint | 1.2 - Material classification and source
label | Ref docs - Drawings
label | Acceptance criteria - Mix design to be approved prior to placement.
label | ○ Material properties meet project specification.
label | – Minimum Concrete strength 32 MPa or as specified in Drawings
label | – Lean-mix concrete subbase (5MPa)
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Mix design
section | 2.0 Concrete placement
checkpoint | 2.1 - Set out
label | Ref docs - Drawings
label | Acceptance criteria - Extents and levels correct to relevant drawings
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Survey report
checkpoint | 2.2 - Bedding preparation
label | Ref docs - Drawings
label | Acceptance criteria - Loose material to be removed from the surface prior to pouring.
label | ○ Waterproof membrane installed on subgrade prior to placement of lean-mix concrete.
label | ○ Notice: 1 working day prior to covering
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 2.3 - Conduit installation
label | Ref docs - Drawings
label | Acceptance criteria - Correct size electrical conduit as per drawings, to be installed before blinding layer
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 2.4 - Formwork set out and positioning correct
label | Ref docs - Drawings
label | Acceptance criteria - Ensure drawings have been checked and the set out is correct
label | ○ Notice: 1 working day prior to covering
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 2.5 - Steel reinforcement
label | Ref docs - Drawings
label | Acceptance criteria - Steel reinforcement to be placed as per design drawings with the correct amount of cover.
label | ○ Concrete pre-pour inspection complete.
label | ○ Notice: 2 working days prior to covering
button | Acceptance | Yes,No,N/A
label | Key - H
label | HPP CON Key - H
label | HPP QA Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Pre-pour inspection
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Concrete placement
label | Ref docs - Spec. 0319 Minor Concrete Works [Cl 4.8, 4.9, 4.10, 4.11] Drawings
label | Acceptance criteria - As per drawings concrete strength of cast in-situ units shall be min. Grade N32 or otherwise stated on drawings.
label | ○ Placing of concrete ambient shade temperatures:
label | – Cold: < 10°C
label | – Hot: > 32°C
label | ○ Cold weather: Placing
label | – Concrete: Maintain the temperature of the freshly mixed concrete at ≥ 5°C
label | – Formwork and reinforcements: Before and during placing maintain temperature at ≥ 5°C
label | ○ Hot weather placing table:
label | – – – – – – – – – – – – – – – –
label | Concrete element ¦¦ Temperature limit
label | – – – – – – – – – – – – – – – –
label | Normal concrete in footings, beams, columns, walls and slabs ¦¦ 35°C
label | Concrete in sections ≥ 1 m in all dimensions except for concrete of strength 40 MPa or greater, in sections exceeding 600 mm in thickness ¦¦ 27°C
label | – – – – – – – – – – – – – – – –
label | ○ Concrete placed in layers ≤ 300mm thick and adequately vibrated avoiding over-vibration.
label | ○ Slump shall not exceed 75mm unless shown otherwise on the drawings.
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Delivery dockets
checkpoint | 2.7 - Surface finish
label | Ref docs - As per drawings
label | Acceptance criteria - Concrete surfaces shall be true and even, free from honeycombed surface depressions or rejections.
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 2.8 - Joints
label | Ref docs - As per drawings
label | Acceptance criteria - As per design drawings. Sawn joints to commence as soon as the concrete has hardened sufficiently.
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 2.9 - Curing
label | Ref docs - Spec. 0319 Minor Concrete Works [Cl 4.13]
label | Acceptance criteria - From completion of finishing cure continuously with an approved method for a min period of 7 days or as directed by the Superintendent.
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 2.10 - Compressive strength
label | Ref docs - Drawings
label | Acceptance criteria - Average strength of all samples must exceed required value.
label | ○ Strength of any one sample must be 0.85 the required value.
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
section | 3.0 Conformance check
checkpoint | 3.1 - Survey pick-up
label | Ref docs - Spec. 0161 Quality (Construction) [Cl 3.13]
label | Acceptance criteria - An as-built survey completed to ensure all structures are within construction tolerances.
label | ○ Plan: +/- 30mm
label | ○ Level: +/ 10mm
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
textbox | Surveyor:
date | Date picked up: