## ITP
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | F3001B Fault ID609 Te Puia Subsidence site |  | CPS Approver | Quality Approver | CPS Eng. | Jamie Walker
|  |  |  | Procedure: |  |  | Name / Signature | Name / Signature | Site Engineer | Amritpal Singh
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng. | Dale Gibson
Lot No:F3001B |  |  |  | Corresponding Work Instruction: |  | (insert Sharepoint link to Construction Work Plan folder here) |  | Compliance with Work Instructions and Specifications
Detailed Location:SH35 RS225. RP0470
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Specification/Drawings Reference | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
Section 1: RECEIVING INSPECTIONS
1.1 | Rock Armour (D50=450) | W | Buttress typical details and F3001B-DS-GT-RP-001 | Prior to commencement | Supplier material test certificate | Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious materail. Shall have a D50 of 450 with a minimum specific Gravity SG of 2350kg/m3. Traceability of materials is required | Material source test results, Delivery dockets | Site Engineer
1.2 | BulkFill AP65 or GAP65/GAP100 | H | Buttress typical details and F3001B-DS-GT-RP-001 | Prior to commencement | Supplier material test certificate | Should comprise clean granular aggregate and have broken faces. Material source testing Traceability of materials is required | Material source test results, Delivery dockets | Site Engineer | CPS Engineer
1.3 | Class D A39 Geotextile | W | Buttress typical details and F3001B-DS-GT-RP-001 | Prior to commencement | Manufacturers certificate | On dry bed below fill Comply with NZTA F/7 | Material certificate(s), Delivery dockets | Site Engineer
1.4 | TNZ F/2 drainage material | W | Buttress typical details and F3001B-DS-GT-RP-001, TNZ F/2 | Prior to commencement | Supplier material test certificate | Comply with TNZ F/2 Traceability of materials is required | Material source test results, Delivery dockets | Site Engineer
1.5 | Megaflow strip drain or drainage blanket for seepage if encountered | W | Buttress typical details and F3001B-DS-GT-RP-001 | Prior to commencement | Manufacturers certificate | Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved. | Material certificate(s), Delivery dockets | Site Engineer
1.6 | 110mm Novaflo drainage pipe | W | Buttress typical details and F3001B-DS-GT-RP-001 | Prior to commencement | Manufacturers certificate | Comply with TNZ F/2 | Material certificate, Delivery dockets | Site Engineer
1.7 | Biocore erosion control matting | W | Buttress typical details and F3001B-DS-GT-RP-001 | Prior to commencement | Manufacturers certificate | NZTA Erosion and Sediment Control Guidelines for State Highway Infrastructure - Section 8.12 Geotextiles, plastic covers, erosion control blankets and geo binders | Material certificate(s), Delivery dockets | Site Engineer
1.8 | Enkamat 7018 | W | Buttress typical details and F3001B-DS-GT-RP-001 | Prior to commencement | Manufacturers certificate | NZTA Erosion and Sediment Control Guidelines for State Highway Infrastructure - Section 8.12 Geotextiles, plastic covers, erosion control blankets and geo binders | Material certificate(s), Delivery dockets | Site Engineer
Section 2: IN PROGRESS INSPECTIONS
2.1 | Survey Setout | H | Consistency with Construction Drawing | Prior to commencement | Survey | Set out extents of fill and check against design drawings | Survey receipt | Site Engineer | CPS Engineer
2.2 | Vegetation Clearance and removal of loose debris | W | Buttress typical details type A and F3001B-DS-GT-RP-0001 | During Construction | Visual Inspection | Remove and clear the vegetation | Photo's | Site Engineer
2.3 | Subgrade Inspection | H | Buttress typical details type A and F3001B-DS-GT-RP-0001 | Per area as required | Inspection by the Geotechnical Design Manager or representative | Inspect fill foundation. Fill foundation must be approved, in writing, before filling commences CPS Engineer - to determine any testing requirements here | 1M Scala checksheet, CPS COR report | Site Engineer | CPS Engineer
2.4 | Ground Improvements | H | Buttress typical details type A and F3001B-DS-GT-RP-0001 | During Construction | Document Review | Any area that requires Ground Improvements must be completed as per Engineer requirements and be signed off and closed before bulk earthwork operations commence | Photo's, CPS COR Report | Site Engineer | CPS Engineer
2.5 | Class D (A39) Geotextile installation on the excavated face | W | Buttress typical details type A and F3001B-DS-GT-RP-0001 | During Construction | Visual Inspection | Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation material and engineered fill. | Photo's | Site Engineer
2.6 | Sub soil drainage | H | Buttress typical details type A and F3001B-DS-GT-RP-0002, TNZ F/2 or approved equivalent. CPS requested a 110mm diameter nova flow drain around the perimeter of the works | As works progress in agreement with the CPS Engineer | Visual Inspection | Engineer to assess suitable drainage location and confirm drainage positions on site. | Photo's, Drainage Line Record check sheet (CS-4025) | Site Engineer | CPS Engineer
2.7 | Megaflow strip or drainage blanket installation for seepage if Encountered | W | Buttress typical details A and F3001B-DS-GT-RP-0001 | During Construction | Visual Inspection | Installed in accordance with manufacturers recommendations | Photo's | Site Engineer
2.8 | Bulk Fill Placement | M | Buttress typical details A and F3001B-DS-GT-RP-0001 | During Construction | Visual Inspection | Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on dry subgrade | Photo's, Bulk Fill Earthworks Check Sheet (CS-4020) | Site Engineer
2.9 | Bulk Fill Compaction | M | Buttress typical details type A and F3001B-DS-GT-RP-0001 | During Construction | NDM testing | A target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3 CPS Engineer to confirm number of tests / lifts to be completed | NDM test report | Site Engineer
|  | M | Buttress typical details type A and F3001B-DS-GT-RP-0001 | Every lift/layer | Clegg Hammer testing | CIV>=25 Shall be carried out for each lift/layer and recorded | Clegg Record test sheet (CS-4037c), Clegg calibration certificate, Photos | Site Engineer
2.1 | Form and cut fill batter as per design 2H:1V | H | Buttress typical details type A and F3001B-DS-GT-RP-0001 | During Construction | Visual Inspection | Erosion control matting to be placed and pinned on the face of the fill in accordance with the manufacturers recommendations | Site inspection on completion, Survey as builts | Site Engineer | CPS Engineer
2.11 | Rock Armour (50-450dia) placed on the toe of the slope | W | Buttress typical details type A and F3001B-DS-GT-RP-0001 | During Construction | Visual Inspection | The buttress to be keyed in to natural ground as required and agreed with the CPS Engineer. Rock armour to be added to the toe as required | Photo's | Site Engineer
2.12 | Verge & Fence Reinstatement | M | Buttress typical details type A and F3001B-DS-GT-RP-0001 | During Construction | Visual Inspection | Verge reinstatement as per site instruction by Engineer Fence reinstalled to match existing | Photo's | Site Engineer
2.13 | As-built Survey | H |  | At completion of Lot | Survey / Drawings | As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer | As-builts, CPS COR Report | Site Engineer | CPS Engineer
Section 3 : Final Inspection and Handover
3.1 | Final Walkover (Snags) | H | The final walkover must be scheduled at least one week before the site's completion or demobilisation. | At the completion of the Lot of work | Walkover must be attended by Handover/Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out) | Completed report | Snag List signed by attendees | QM
3.2 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer
3.3 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Manager: |  |  |  |  | Signature: |  |  | Date:

## SSI
SITE SPECIFIC INSTRUCTIONS
Any changes to design to be approved in writing by Design Engineer
Site Instruction details | Name | Position | Date | Quality & Design Engineer notified (date)