## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP - F3001B - Te Puia Dropout | itp |  |  |  | Yes | ITP - F3001B - Te Puia Dropout | d6eca4ab-a250-43f8-b33d-7c027e0b5123
checkpoint-group |  |  | section | Section 1: RECEIVING INSPECTIONS
checkpoint-status |  |  | checkpoint | Project Site reps.
text | d5886eb3-a0de-5c61-921b-d30af2fbf729 |  | textbox | CPS Eng.
text | bae783f7-d269-5d23-999c-b42af6f08699 |  | textbox | Site Engineer
text | 7ca7109d-b0ca-5f9e-b2e6-fd77ddc4d7ff |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Rock Armour (D50=450)
label | 2efad191-92e2-5f3a-a888-fe001effe14f |  | note | ACTION (Hold, Monitor, Witness) - W
label | a93e5f66-7e0d-52d5-971a-0822c653d1c0 |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | 65236aa0-90e6-5f1f-9c88-dcbb1f2b88a1 |  | note | Frequency - Prior to commencement
label | b072a4ad-2c07-548a-9499-b644f49b6ecb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 706525fc-135b-5755-89fe-535780952c20 |  | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious materail. Shall have a D50 of 450 with a minimum specific Gravity SG of 2350kg/m3.
label | 9f9414e7-179e-50c9-89b9-cfafea24efe7 |  | note | ○ Traceability of materials is required
label | 8735c40e-d22e-5a8c-a712-559b9c81298b |  | note | Records - Material source test results, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.2 - BulkFill AP65 or GAP65/GAP100
label | 4831e455-3774-531c-9c51-7e18c56eeec1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 94c285c2-727e-5b2f-8fad-06be49e5c555 |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | 2c6406b0-8b8d-515c-afa3-ded7b052d44f |  | note | Frequency - Prior to commencement
label | a57aae86-37a1-551d-9d97-38dacf1d0f74 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 31b99d8f-4b28-5650-a06b-f069550175f9 |  | note | Conformance Criteria - Should comprise clean granular aggregate and have broken faces.
label | 654f126e-4009-5869-82e7-0639a4c005cc |  | note | ○ Material source testing
label | e8da746e-fca7-57a0-b041-592acf263bdf |  | note | ○ Traceability of materials is required
label | ce03e7b2-888f-537d-85a9-dfe8f262ecc3 |  | note | Records - Material source test results, Delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Class D A39 Geotextile
label | eb3c85d5-c7cd-51cc-93c6-9780893699a5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 32293d84-98aa-5f8e-9b4a-5a415ed2c725 |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | 41279df7-1183-575c-9791-c38fb7460287 |  | note | Frequency - Prior to commencement
label | 075c13cb-d0a8-516a-bbc5-4d898c6ef833 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 1edfa198-df8f-55e5-9d3f-746e9ce35216 |  | note | Conformance Criteria - On dry bed below fill
label | e77e60a7-4a5d-51fe-8474-336ffa92a226 |  | note | ○ Comply with NZTA F/7
label | 702d1850-5ec5-52c0-935e-57cbdb07b409 |  | note | Records - Material certificate(s), Delivery dockets
checkpoint-status |  |  | checkpoint | 1.4 - TNZ F/2 drainage material
label | 2b3b2145-ccef-5ef0-87cb-197976fd1cfc |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6460b965-ab28-5b06-a43c-143553b14fda |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001, TNZ F/2
label | a48b02be-73fc-5b30-88c8-9d47a9b9d41d |  | note | Frequency - Prior to commencement
label | 77b7796a-640b-5aae-80df-60d2c0abd7e5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | f2c36c2e-b630-5d08-b702-133405225cd7 |  | note | Conformance Criteria - Comply with TNZ F/2
label | 6e2cb734-6e63-5fab-aac6-4a271d08cb2c |  | note | ○ Traceability of materials is required
label | 631dd9f5-cd29-54fd-b325-030f2100f413 |  | note | Records - Material source test results, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.5 - Megaflow strip drain or drainage blanket for seepage if encountered
label | 24043b29-1917-5891-9cb0-ee2dc9bd1d8c |  | note | ACTION (Hold, Monitor, Witness) - W
label | a5c320ff-ce1a-5d03-9f13-0e662a8fc012 |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | 8d3d2cbd-ed40-5c36-a9a2-f479ea3bf373 |  | note | Frequency - Prior to commencement
label | 189e2faf-74c6-5ca8-ae7b-de70bc0dd7e9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 5e8385b9-49e4-58ba-ae6d-eb68c2cb5c52 |  | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved.
label | 74fa60f2-83d5-5f74-a5f0-4c8e6140caa8 |  | note | Records - Material certificate(s), Delivery dockets
checkpoint-status |  |  | checkpoint | 1.6 - 110mm Novaflo drainage pipe
label | fb978551-3cea-5a47-baa0-37a7969f6304 |  | note | ACTION (Hold, Monitor, Witness) - W
label | bd71725a-1d6e-54ba-abe0-916860cca927 |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | 85819755-63f1-5a4f-9cd5-b03ca8f11403 |  | note | Frequency - Prior to commencement
label | 79400abf-ebbf-5468-bbdc-e18f3b6e8de5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 85744991-173d-5f9c-be99-0e1ef7746d02 |  | note | Conformance Criteria - Comply with TNZ F/2
label | d8a4f37f-faed-5968-8f79-21e2aab3cc76 |  | note | Records - Material certificate, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.7 - Biocore erosion control matting
label | 040045b0-3555-5cb8-bee8-929356def80e |  | note | ACTION (Hold, Monitor, Witness) - W
label | f5597053-1948-535f-bb09-69cfc6ed04b1 |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | c35dd2fc-6ae9-5bc1-bc8a-ee736cba8beb |  | note | Frequency - Prior to commencement
label | 959e8c3d-75fc-5981-b574-a4992a8f1d3e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 86c98595-dc53-5d6b-b75c-3c38537766bb |  | note | Conformance Criteria - NZTA Erosion and Sediment Control Guidelines for State Highway Infrastructure - Section 8.12 Geotextiles, plastic covers, erosion control blankets and geo binders
label | 5d593ebe-0950-58d7-b9f1-132628f737de |  | note | Records - Material certificate(s), Delivery dockets
checkpoint-status |  |  | checkpoint | 1.8 - Enkamat 7018
label | ce9c48a5-f190-561e-93b8-4d8fddbaa380 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b49111c6-049e-5580-be46-14d8ef5ca081 |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | b30aa0f8-92d5-54a4-b866-123efde2a14e |  | note | Frequency - Prior to commencement
label | 5cc3c0ef-ce25-583a-9412-fb94494f0aa6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 5923c629-5560-5cdd-9bcc-f572c2b98a76 |  | note | Conformance Criteria - NZTA Erosion and Sediment Control Guidelines for State Highway Infrastructure - Section 8.12 Geotextiles, plastic covers, erosion control blankets and geo binders
label | 0c1be551-040c-5285-a5d9-e3c4bb88cf19 |  | note | Records - Material certificate(s), Delivery dockets
checkpoint-group |  |  | section | Section 2: IN PROGRESS INSPECTIONS
checkpoint-status |  |  | checkpoint | 2.1 - Survey Setout
label | 2c6af61c-4d7c-5922-84d9-fc97da36b0a4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a44540ac-8d79-58b2-b082-2dfb9ee70b16 |  | note | Specification/Drawings Reference - Consistency with Construction Drawing
label | 245f2761-65e2-5c6e-9ebb-21bfbc36818b |  | note | Frequency - Prior to commencement
label | 0834b667-0b05-55d6-a8b3-71b3f4e134ec |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | ee72cd15-fbe1-5c15-9c36-6c0a716cdfe2 |  | note | Conformance Criteria - Set out extents of fill and check against design drawings
label | dba849cd-216c-5f96-96c7-e1c3c0dd7d59 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
label | d00fdfb6-9470-511d-93fe-39a5ecb142d6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 154733fc-f4c4-5789-8c09-3c6975db5845 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | eeaf5627-81de-5dd1-a8c2-812e497665f1 |  | note | Frequency - During Construction
label | 00f602ae-01dc-543f-b8ae-6495b87a3379 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 7925ccb3-df6c-5cd9-96fd-da53d14f930a |  | note | Conformance Criteria - Remove and clear the vegetation
label | ce65565f-9801-5688-8401-48398d39d8e2 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.3 - Subgrade Inspection
label | 3f34c1a7-c4df-5732-a75a-fdf70427b9be |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1d798224-c504-56cf-81bb-f1fad579d0a9 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | 4b1df22b-5ff4-5af6-ae72-7eb4c7175274 |  | note | Frequency - Per area as required
label | 886aab3e-c0b3-5594-bf1d-7ebd2ce80550 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager or representative
label | cbc261ef-2982-5449-a38b-67daa049bc7d |  | note | Conformance Criteria - Inspect fill foundation.
label | 834627b1-ad12-5926-ac77-33db0059bbfb |  | note | ○ Fill foundation must be approved, in writing, before filling commences
label | 2afa4c7d-76fb-52ce-8f53-f0aaa9102eb7 |  | note | ○ CPS Engineer - to determine any testing requirements here
label | decbc955-c5ff-5e7b-bef5-b6f6b4d66938 |  | note | Records - 1M Scala checksheet, CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Ground Improvements
label | 6feb87ae-c63a-5727-bb51-c66d3c25b74e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 86300ed6-823d-57bb-a36d-b1cd271134d7 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | 2145d0c3-0e3b-5ddf-b72a-cc1d9613cb19 |  | note | Frequency - During Construction
label | 7581ced4-6d66-59d5-ad4b-e796d7ff7bfe |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | d15431b8-2fd9-536e-b35b-c9f72f58bb79 |  | note | Conformance Criteria - Any area that requires Ground Improvements must be completed as per Engineer requirements and be signed off and closed before bulk earthwork operations commence
label | 1346da4e-c4cf-54fa-86e4-57b9095bf8d0 |  | note | Records - Photo's, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Class D (A39) Geotextile installation on the excavated face
label | b8486f92-3009-5058-acb7-a876885d2465 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8b50b391-8ed2-5679-8ca8-9eea19b66010 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | 83a3b3d7-ece8-5088-bd61-18b7ab017617 |  | note | Frequency - During Construction
label | c5c2a0fd-fc43-52de-9d48-9fb7e9da15cd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 11c55e9c-31a1-5cb6-a699-3c42919f412b |  | note | Conformance Criteria - Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation material and engineered fill.
label | 26b1cb0b-d88c-5440-b1b0-377f9ac001ac |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.6 - Sub soil drainage
label | 615e52b0-3922-511c-9d54-1e733d4c2b0c |  | note | ACTION (Hold, Monitor, Witness) - H
label | d3ec1b92-8253-596b-852f-6cc562b69a1b |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0002, TNZ F/2 or approved equivalent. CPS requested a 110mm diameter nova flow drain around the perimeter of the works
label | 0e37120b-6d1c-5e53-aeb0-6fdc6bf2eacc |  | note | Frequency - As works progress in agreement with the CPS Engineer
label | f45807c4-7a1b-5e05-8f4c-824f65b047c1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 81f9706f-ebfb-526d-97b0-9f4ee8d77af1 |  | note | Conformance Criteria - Engineer to assess suitable drainage location and confirm drainage positions on site.
label | 69edf05d-78db-5be7-b05a-9d4f490e7481 |  | note | Records - Photo's, Drainage Line Record check sheet (CS-4025)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Megaflow strip or drainage blanket installation for seepage if Encountered
label | 95cd155a-340f-5289-8ed1-5e003d53145d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7051c6bf-6253-5d2d-bb8a-573a7f5d23f6 |  | note | Specification/Drawings Reference - Buttress typical details A and F3001B-DS-GT-RP-0001
label | 15fbf63b-0dcd-5146-bf02-941bedf24121 |  | note | Frequency - During Construction
label | 3d2d5f62-85e3-58ff-a110-0cd7ccd9df15 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 498dca08-2c80-55ef-8875-b1bb70730803 |  | note | Conformance Criteria - Installed in accordance with manufacturers recommendations
label | 2d9df7f3-ed6b-58be-a86f-86e717266224 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.8 - Bulk Fill Placement
label | 85dee485-46b8-5991-a1f5-53a9488e65d0 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 95e787ff-46fb-5a2e-abe1-3d4e743b273c |  | note | Specification/Drawings Reference - Buttress typical details A and F3001B-DS-GT-RP-0001
label | 1e9ad25f-d1a4-51ff-a869-c143a9f61c3e |  | note | Frequency - During Construction
label | 05bb11a1-4e92-5b25-8bb7-8d7ae16d3e01 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | b8df0f9a-cf1c-5d82-8282-0b067f607b70 |  | note | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on dry subgrade
label | 647cad54-1dd3-53d7-8d56-e4b8b7a184c1 |  | note | Records - Photo's, Bulk Fill Earthworks Check Sheet (CS-4020)
checkpoint-status |  |  | checkpoint | 2.9 - Bulk Fill Compaction
label | e457a3c1-23c6-51f6-be4a-499e86d85de2 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 294b20c1-fefa-5294-8f74-696dc4619651 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | dd254345-2283-5c8a-8ab3-c79b3b2a9e81 |  | note | Frequency - During Construction
label | 8b13bce4-ab62-5ea8-b0c1-756a9c07673b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | 05240f67-5347-55e2-8605-1e1fa296115b |  | note | Conformance Criteria - A target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3 CPS Engineer to confirm number of tests / lifts to be completed
label | 5336a973-78cd-5d12-8d58-4f0741eb977f |  | note | Records - NDM test report
checkpoint-status |  |  | checkpoint | -
label | 0c068ee2-a4dc-5daa-bee5-15fa1fb845a3 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 1178116a-e1d0-5574-a6b4-7132a6b93781 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | c49587a8-aab8-5a68-8655-9b3f44b74339 |  | note | Frequency - Every lift/layer
label | 5e72fab6-53b0-5b6b-9101-df39325e5212 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | 5dc78e36-9e65-5e50-b8ed-204f404a21f8 |  | note | Conformance Criteria - CIV>=25
label | ec942465-645a-506e-9748-b98f054956e7 |  | note | ○ Shall be carried out for each lift/layer and recorded
label | 842ffe63-6ae8-5a0c-98d4-da0476004c90 |  | note | Records - Clegg Record test sheet (CS-4037c), Clegg calibration certificate, Photos
checkpoint-status |  |  | checkpoint | 2.1 - Form and cut fill batter as per design 2H:1V
label | e3b6bcb3-e47c-58a4-bb67-9cbb98f71c5a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 13adac06-f0e2-5b3a-9cb8-4dfcffddd604 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | 3a1555a9-80e6-54ee-a1a4-855b985dd024 |  | note | Frequency - During Construction
label | 27a2186b-9bd0-597e-ab46-b8ca46d3e300 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | b509a875-62a4-5e5a-b17f-14d437dd914e |  | note | Conformance Criteria - Erosion control matting to be placed and pinned on the face of the fill in accordance with the manufacturers recommendations
label | 2f986d59-913c-5cf8-8c22-81062e7e4257 |  | note | Records - Site inspection on completion, Survey as builts
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.11 - Rock Armour (50-450dia) placed on the toe of the slope
label | 56f83237-cb9d-5aff-8c37-de868fdb41db |  | note | ACTION (Hold, Monitor, Witness) - W
label | e6e173cf-b4d4-5314-8fa1-b6ff7ab0dc8a |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | 024d45d0-84a8-505d-8034-ea5259813bf9 |  | note | Frequency - During Construction
label | 52090ee9-1a05-5e30-a027-af6c505f3700 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 932aef3a-6a2b-51d9-b2fa-4cc43a8dbdbb |  | note | Conformance Criteria - The buttress to be keyed in to natural ground as required and agreed with the CPS Engineer. Rock armour to be added to the toe as required
label | 1d6f2f26-d1af-55d1-8858-1df7cc567b5d |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.12 - Verge & Fence Reinstatement
label | c0704f72-b43a-586f-8d8b-6ead4fc33fd7 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 9d7ce1a4-d9bf-51e5-b2ed-354b3deb27e0 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | 542efebe-36cc-511e-9f0d-67c1ce42fb09 |  | note | Frequency - During Construction
label | e2392eea-d2c3-518c-a10b-8e6f4396cf0c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | f2ebe251-a82f-5b9f-af93-751d7289968a |  | note | Conformance Criteria - Verge reinstatement as per site instruction by Engineer
label | 1c602820-e49e-5789-88f1-f4b1867f523c |  | note | ○ Fence reinstalled to match existing
label | bfff5779-5d2e-54e6-80fa-d566e1b638d9 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.13 - As-built Survey
label | defd746c-a0d4-5b34-8d91-d9e0a19ba431 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 67256af9-139d-5610-b747-cacc1e585581 |  | note | Frequency - At completion of Lot
label | 62ca4e0c-31b7-599f-a367-41e2ebfbbbc3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | 535da349-2897-5f6f-8f59-ca4c8c334842 |  | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | c5585b2f-58e4-58a6-9986-aaba2fcaa541 |  | note | Records - As-builts, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 3 : Final Inspection and Handover
checkpoint-status |  |  | checkpoint | 3.1 - Final Walkover (Snags)
label | 3133cf79-6721-5e85-a47b-81b912a70b7c |  | note | ACTION (Hold, Monitor, Witness) - H
label | ad7f4a42-bb8c-555b-9bed-cf4000415f9c |  | note | Specification/Drawings Reference - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | 507f2a2a-24da-53dd-8ca1-b122a6147ed5 |  | note | Frequency - At the completion of the Lot of work
label | 06f98d94-449d-5978-a3bc-6acbae604c2b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover/Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | a9463427-7da7-5a1b-8093-d2d596a6aa35 |  | note | Conformance Criteria - Completed report
label | ddfc20e8-8aa1-5a00-a6a9-7850a8cf227a |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Quality Assurance deliverables
label | 1ccc7a01-cf9c-52a7-ab7e-ac2839d347b6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a2830549-4943-5fd2-b4f7-d3f43438f7ec |  | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 75148702-9349-5372-813b-dd525415c2ac |  | note | Frequency - At completion of Lot
label | 5d910072-3ca1-534a-9289-0c76f705dcc8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | cfc21ccb-55e1-5bfb-9dcd-4b65b2c0f2dc |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | a956c156-6659-5642-9bc5-112ecb6e77f7 |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 3.3 - Completion Sign Off From Fields Below
label | 730f35aa-6dd0-5e99-b0c8-2865c67758e2 |  | note | Records - Signatures