## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - F3001B - Te Puia Dropout | itp |  |  |  |  | ITP - F3001B - Te Puia Dropout | d6eca4ab-a250-43f8-b33d-7c027e0b5123
section | Section 1: RECEIVING INSPECTIONS
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - Rock Armour (D50=450)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious materail. Shall have a D50 of 450 with a minimum specific Gravity SG of 2350kg/m3.
label | ○ Traceability of materials is required
label | Records - Material source test results, Delivery dockets
checkpoint | 1.2 - BulkFill AP65 or GAP65/GAP100
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Should comprise clean granular aggregate and have broken faces.
label | ○ Material source testing
label | ○ Traceability of materials is required
label | Records - Material source test results, Delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Class D A39 Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - On dry bed below fill
label | ○ Comply with NZTA F/7
label | Records - Material certificate(s), Delivery dockets
checkpoint | 1.4 - TNZ F/2 drainage material
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001, TNZ F/2
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Comply with TNZ F/2
label | ○ Traceability of materials is required
label | Records - Material source test results, Delivery dockets
checkpoint | 1.5 - Megaflow strip drain or drainage blanket for seepage if encountered
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved.
label | Records - Material certificate(s), Delivery dockets
checkpoint | 1.6 - 110mm Novaflo drainage pipe
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - Comply with TNZ F/2
label | Records - Material certificate, Delivery dockets
checkpoint | 1.7 - Biocore erosion control matting
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - NZTA Erosion and Sediment Control Guidelines for State Highway Infrastructure - Section 8.12 Geotextiles, plastic covers, erosion control blankets and geo binders
label | Records - Material certificate(s), Delivery dockets
checkpoint | 1.8 - Enkamat 7018
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - NZTA Erosion and Sediment Control Guidelines for State Highway Infrastructure - Section 8.12 Geotextiles, plastic covers, erosion control blankets and geo binders
label | Records - Material certificate(s), Delivery dockets
section | Section 2: IN PROGRESS INSPECTIONS
checkpoint | 2.1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawing
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Set out extents of fill and check against design drawings
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Remove and clear the vegetation
label | Records - Photo's
checkpoint | 2.3 - Subgrade Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | Frequency - Per area as required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager or representative
label | Conformance Criteria - Inspect fill foundation.
label | ○ Fill foundation must be approved, in writing, before filling commences
label | ○ CPS Engineer - to determine any testing requirements here
label | Records - 1M Scala checksheet, CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Ground Improvements
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Any area that requires Ground Improvements must be completed as per Engineer requirements and be signed off and closed before bulk earthwork operations commence
label | Records - Photo's, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Class D (A39) Geotextile installation on the excavated face
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation material and engineered fill.
label | Records - Photo's
checkpoint | 2.6 - Sub soil drainage
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0002, TNZ F/2 or approved equivalent. CPS requested a 110mm diameter nova flow drain around the perimeter of the works
label | Frequency - As works progress in agreement with the CPS Engineer
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineer to assess suitable drainage location and confirm drainage positions on site.
label | Records - Photo's, Drainage Line Record check sheet (CS-4025)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Megaflow strip or drainage blanket installation for seepage if Encountered
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details A and F3001B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Installed in accordance with manufacturers recommendations
label | Records - Photo's
checkpoint | 2.8 - Bulk Fill Placement
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Buttress typical details A and F3001B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on dry subgrade
label | Records - Photo's, Bulk Fill Earthworks Check Sheet (CS-4020)
checkpoint | 2.9 - Bulk Fill Compaction
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | Conformance Criteria - A target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3 CPS Engineer to confirm number of tests / lifts to be completed
label | Records - NDM test report
checkpoint | -
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | Frequency - Every lift/layer
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | Conformance Criteria - CIV>=25
label | ○ Shall be carried out for each lift/layer and recorded
label | Records - Clegg Record test sheet (CS-4037c), Clegg calibration certificate, Photos
checkpoint | 2.1 - Form and cut fill batter as per design 2H:1V
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Erosion control matting to be placed and pinned on the face of the fill in accordance with the manufacturers recommendations
label | Records - Site inspection on completion, Survey as builts
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.11 - Rock Armour (50-450dia) placed on the toe of the slope
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - The buttress to be keyed in to natural ground as required and agreed with the CPS Engineer. Rock armour to be added to the toe as required
label | Records - Photo's
checkpoint | 2.12 - Verge & Fence Reinstatement
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Verge reinstatement as per site instruction by Engineer
label | ○ Fence reinstalled to match existing
label | Records - Photo's
checkpoint | 2.13 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
section | Section 3 : Final Inspection and Handover
checkpoint | 3.1 - Final Walkover (Snags)
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover/Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | Conformance Criteria - Completed report
label | Records - Snag List signed by attendees
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 3.3 - Completion Sign Off From Fields Below
label | Records - Signatures