## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
d2f9b665-4ae6-4be1-8df6-d4c1ed452388 | checklist | Guest Room - Water Rehau |  | Guest Room - Water Rehau
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
bb44e45b-f53e-4d66-b0b2-c50b57fd37ab | checkpoint | Details
0fa5673a-5404-5289-91b1-346abf74b960 | textbox | Guest room Number:
b9a54ac7-5c89-4db7-bfa0-a44f269636ef | checkpoint | Water Pipeout
7f1321fc-e348-4eaf-9461-d9dde459d5cc | checkpoint | Correct Pipe sizing
f41b3afd-a394-48ee-a30f-d8b7cbc19116 | checkpoint | All pipe work crimps checked
33adbe60-e444-4e6c-83c8-0fbcf9511d06 | checkpoint | No Cross connections
48b85a74-99fc-45ee-a904-8d7fd0a817a6 | checkpoint | Shower Mixer at Height & Centre
4e8d8d45-e183-4c66-8c73-649671cd455f | checkpoint | All fixings installed - Nogs
d9410a41-eb8d-44b8-b643-a3349ae606b4 | checkpoint | Toilet Inwall Cistern Fixed & Secure
d8464881-7b89-44de-ab15-45c4587f4f35 | checkpoint | Toilet waste & Flush pipe centre & at Height
57299d7e-7c04-473c-8a4f-1212729b3520 | checkpoint | Guest Room Isolation Valves Installed
8bc92e22-99b0-4520-86c7-f831d0b968f7 | checkpoint | Pipework Clips & fixings installed
3139b767-c00a-4941-8fd5-b1df221f3502 | checkpoint | Double check set outs and measurements
464db29d-d2f9-4e35-bc0a-5cb73775c599 | checkpoint | All test plugs installed or capped off
8f2a445f-c10a-4224-8d59-9bf5093f89c4 | checkpoint | Shower mixer removed for testing
98466b14-0890-4bef-abec-f2248daa2023 | checkpoint | Pressure Test 1500 KPA in accordance with AS/NZS 3500 and rehau testing 30 mins procedure
520181bc-152a-46ca-9197-65aa1a383a2a | checkpoint | Re instate shower mixer into position post test
cc7a0637-ad28-45ec-9af3-08b06232442a | checkpoint | Pipework siliconed and secured
59816f77-5512-4869-8e21-3c34645cf0ba | checkpoint | Area cleaned & rubbish removed
bc684ba8-03a4-4d0e-95d5-a002315f9d65 | checkpoint | Installers name & date works completed
c56c4f00-70ff-5b4c-b8ca-8dc0c9486264 | textbox | Installers name
782de8a4-4b01-5a33-8314-e2aad79f2348 | date | Date:
23300a47-81b5-400b-bd89-f77cf33e1b98 | checkpoint | Tested by & date
4d1cfd12-4fda-5fa1-912c-98010cd0bdcd | textbox | Tested by:
c0bb7e0b-0256-5cca-b839-8b31f871341a | date | Date tested:
b8ee7d65-d37b-430b-b544-36c743e7707d | checkpoint | Council inspector sign off and date
cf71a4db-12cf-4cc0-b36a-c4fb23009a6f | signoff | SIGN HERE OR REQUEST SIGNOFF