## Abutment
type | name Abutment | values
checklist-sectioned | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction" |  | upload a copy to CONQA?
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
tickbox | 5T Foot Anchor - Nexus 170mm | 4
tickbox | Reinforcement
tickbox | ID Plate
tickbox | 50 Panel Mix
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Pour Checks
checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
tickbox | All Concrete Dockets Attached
section | Final Inspection
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
checklist | Checkers Checklist
checkpoint | Overall Measurements
checkpoint | Void/Hole Correct Position - 470mm Diameter
checkpoint | Lifters Correct - Position, Size, Orientation
checkpoint | Fillet is Installed
checkpoint | Check Concrete cover around Reo 65mm
checkpoint | Panel Thickness confirmed
dropdown | 1000mm | 1000mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | 5T Foot Anchor - Nexus 170mm | 4
textbox | ID Plate
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use timber formwork
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Check Concrete cover around reo 30mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - GOOD as near face is outside face of building
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN |  | upload docket?
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER |  | signoff?

## Plain Slab
type | name Plain Slab | values
checklist-sectioned | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction" |  | upload a copy to CONQA?
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
tickbox | 5T Foot Anchor - Nexus 170mm | 4
tickbox | Reinforcement
tickbox | Grout Tubes - 250mm | 3
tickbox | ID Plate
tickbox | 50 Panel Mix
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Pour Checks
checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
tickbox | All Concrete Dockets Attached
section | Final Inspection
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
checklist | Checkers Checklist
checkpoint | Overall Measurements
checkpoint | Lifters Correct - Position, Size, Orientation
checkpoint | Grout Tubes - 250mm | 3
checkpoint | Fillet is Installed
checkpoint | Check Concrete cover around Reo 50mm
checkpoint | Panel Thickness confirmed
dropdown | 270mm | 270mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | 5T Foot Anchor - Nexus 170mm | 4
textbox | ID Plate
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use timber formwork
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Check Concrete cover around reo 50mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - GOOD as near face is outside face of building
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix N50 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN |  | upload docket?
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER |  | signoff?

## Headstock 1
type | name Headstock 1 | values
checklist-sectioned | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction" |  | upload a copy to CONQA?
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
tickbox | 5T Foot Anchor - Nexus 170mm | 4
tickbox | Reinforcement
tickbox | ID Plate
tickbox | 50 Panel Mix
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Pour Checks
checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
tickbox | All Concrete Dockets Attached
section | Final Inspection
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
checklist | Checkers Checklist
checkpoint | Overall Measurements
checkpoint | Voids/Holes Correct Position and diameter - 100mm
checkpoint | Lifters Correct - Position, Size, Orientation
checkpoint | Fillet is Installed
checkpoint | Check Concrete cover around Reo 65mm
checkpoint | Panel Thickness confirmed
dropdown | 600mm | 600mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | 5T Foot Anchor - Nexus 170mm | 4
textbox | ID Plate
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use timber formwork
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Check Concrete cover around reo 65mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - GOOD as near face is outside face of building
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix N50 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN |  | upload docket?
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER |  | signoff?