## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - ETPO - Enabling Works - Footpath, Kerb and channel | itp |  |  |  |  | ITP - ETPO - Enabling Works - Footpath, Kerb and channel
section | Site Set Out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Onsite records/photos
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Materials
checkpoint | 2 - Kerb & Channel
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40
label | HOLD POINT: Inprocess Inspection - Engineer to check the Stringline Set out
label | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Extruded standard Kerb & Channel- TYPE 3
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0002
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Extruded Kerb & Channel to be laid on site using machine. On compacted GAP40. Concrete 25MPa fibre reinforced @28 Days on 100mm GAP40
label | HOLD POINT: Inprocess Inspection - Engineer to check the Stringline Set out
label | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Extruded Cycle Kerb- TYPE 15
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0003
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Extruded Kerb to be laid on site using machine or hand. On compacted GAP40. Concrete 25MPa fibre reinforcedfor machine laid or 20 Mpa standard concrete for hand laid @28 Days on 100mm GAP40
label | HOLD POINT: Inprocess Inspection - Engineer to check the Stringline Set out
label | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4 - Channel Level
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | CIVIL WORKS
checkpoint | 5 - Concrete Footpaths and Pram Crossings
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness GAP40
label | ○ Clegg CIV > 15
label | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
label | ○ Expansion Joint cut for every 3m interval
label | ○ Pram crossing to have 600mm flare from kerb; Minmum 1.5m deep and wide.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 6 - Shared footpath
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: Pavement Details- 5 (3236765-CA-3010)
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: Subgrade Improvement materials( If Subgrade CBR <3.5%)- 300mm SIL materials
label | ○ Basecourse - 100mm min. thickness GAP40
label | ○ Clegg CIV > 15
label | ○ Surfacing - Concrete 150mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with exposed finish
label | ○ Single layer 665 mesh with 50mm cover (for concrete slabs with service covers)
label | ○ Expansion Joint cut for every 3m interval
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 7 - Tactiles
label | VERIFICATION ACTIVITY:
label | METHODS OR REFERENCE: TDM Technical Standards - FP0010
label | FREQUENCY: Each PX
label | ACCEPTANCE CRITERIA: Tile set out position to be agreed with ATOC and Engineer.
label | ○ Warning TGSI tiles should have 100mm concrete slab underneath
label | HOLD POINT: Inprocess Inspection, Measurement
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 7.1 - Tactiles
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Tactile to be yellow/ green concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 7.2 - Tactiles
label | VERIFICATION ACTIVITY:
label | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 7.3 - Tactiles
label | VERIFICATION ACTIVITY:
label | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow/green pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Materials Dockets
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 8 - As built information
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
note | Prepared by: Yeswanth Vemula
note | Approving Delegate: Sam
checklist | ITP - ETPO - Enabling Works - Vehicle Crossings | itp |  |  |  |  | ITP - ETPO - Enabling Works - Vehicle Crossings
section | Site Set Out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | ○ Alternatively like for like
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Survey Receipt
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Materials
checkpoint | 2 - Channel Level
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - VX0000
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Mesh & Steel
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - VX0000
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: 661 Mesh and/or D12 Bars to be installed if 4> dwellings or commercial crossing
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: FH concrete QA sheet, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Construction
checkpoint | 4a - Vehicle Crossing
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - VX103
label | FREQUENCY: Each VX
label | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3)
label | ○ Base course - 100mm min. thickness GAP40
label | ○ Clegg CIV > 15
label | ○ Surfacing - Concrete 150mm and 20 MPa @ 28 days. 4kg/m3 black oxide
label | ○ Exposed Finish
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4b - Commercial Crossing
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - VX0202
label | FREQUENCY: Each VX
label | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3)
label | ○ Base course - 100mm min. thickness GAP40
label | ○ Clegg CIV > 15
label | ○ Surfacing - Concrete 200mm and 20 MPa @ 28 days. 4kg/m3 black oxide
label | ○ Exposed Finish
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5 - Grass Berms
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 6 - As built information
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
note | Prepared by: Yeswanth
note | Approving Delegate: Sam
checklist | ITP - ETPO - Traffic Islands | itp |  |  |  |  | ITP - ETPO - Traffic Islands
section | Materials
checkpoint | 1 - Standard Mountable Kerb
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
label | HOLD POINT: Inprocess Inspection - Engineer to check kerb stringline before laying
label | RECORDS: FH concrete QA sheet, photos.
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2 - Mountable Kerb- TYPE 20 Extruded
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & KC0005
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Type 20 extruded mountable Kerb to be laid on site using machine and painted with two coats of reflective paint
label | HOLD POINT: Inprocess Inspection - Engineer to check kerb stringline before laying
label | RECORDS: FH concrete QA sheet, photos.
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 3 - Survey Setout
label | VERIFICATION ACTIVITY: Survey
label | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
label | FREQUENCY: Prior to commencement.
label | ACCEPTANCE CRITERIA: Survey
label | HOLD POINT: As per Construction Drawings
label | RECORDS: Survey Receipt.
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4 - Concrete Island
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5 - Standard Mountable Kerb
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 6 - Type 20 Extruded Mountable Kerb
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & KC0005
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Basecourse to be 300mm min thickness of GAP65
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 7 - Concrete Infil- Extruded Mountable Kerb
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish, unreinforced Concrete with 4kg/m3 Red oxide
label | ○ Cross Fall of 2% or max rise in centre of 180mm
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 8 - Concrete Infil- Standard Mountable Kerb
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: 150mm depth of 20MPa broom finish, unreinforced Concrete with 4kg/m3 Red oxide
label | ○ Cross Fall of 2% or max rise in centre of 150mm
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 9 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 10 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
note | Prepared by: Yeswanth Vemula
note | Approving Delegate: Sam
checklist | ITP - ETPO - Signage | itp |  |  |  |  | ITP - ETPO - Signage
section | Site Set Out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | ○ Alternatively like for like
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Survey Receipt
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Materials
checkpoint | 2 - Signs/Belisha Disk
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Pole, Impact recovery post and Ground Socket
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 4a - Ground Socket
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Each Socket
label | ACCEPTANCE CRITERIA: The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos with tape measurement
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4b - Pole and Impact recovery post
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Each Post or pole
label | ACCEPTANCE CRITERIA: All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent thr pole rotation.
label | ○ The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5 - Signs/Belisha Disk
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Each Sign
label | ACCEPTANCE CRITERIA: All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 6 - As built information
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
textbox | Prepared by:
note | Approving Delegate: Nithin Thomas
checklist | ITP - ETPO - Ducting & Traffic Signals | itp |  |  |  |  | ITP - ETPO - Ducting & Traffic Signals
section | Ducting
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Obtain Permits
label | FREQUENCY: As required
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Authorisation to work, dig permit and service provider permits
label | RECORDS: This ITP signed
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Design
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA:
label | RECORDS: Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Survey Setout (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Survey Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Survey Setout (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos / Engineers approval documentation
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Locate existing services by hand digging/ hydrovac
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
label | FREQUENCY: Prior to Installation
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
label | CONFORMANCE CRITERIA: All conflicts have been located and survey as built recorded
label | RECORDS: Digging/Excavating Control Checklist
checkpoint | 5 - Material Compliance (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure duct pipes and poles are as per drawings and specification
label | FREQUENCY: Upon delivery to site
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
label | CONFORMANCE CRITERIA:
label | RECORDS: Delivery Docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Material Compliance (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all concrete used is 20MPa mix
label | FREQUENCY: Upon delivery to site
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
label | CONFORMANCE CRITERIA:
label | RECORDS: Delivery Docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Trenching
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Inspect trench profile to ensure walls vertical, widths is 300mm max (single ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm (900mm cover when under road crossing)
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.1 - Trenching
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
label | CONFORMANCE CRITERIA: Ensure trench alignment and levels match the design drawings
label | RECORDS: Dipsheet & Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Duct Installation
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
label | FREQUENCY: Prior to Installation
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
checkpoint | 7.1 - Duct Installation
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.2 - Duct Installation
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Asbuilt Survey
label | FREQUENCY: 20m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Survey Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Bedding
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Lay min. 150mm gap20 or finer for bedding and haunching
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Warning Tape
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Traffic signal pole erection
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure Design engineer as inspected pole locations prior to proceeding
label | FREQUENCY: Per pole
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Sign off by design engineer
label | RECORDS: Engineer sign off
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10.1 - Traffic signal pole erection
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure Pot hole is as per design with required depths and widths
label | FREQUENCY: Per pole
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Dipsheet & Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10.2 - Traffic signal pole erection
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure Poles are plumb and within design tolerances
label | FREQUENCY: Per pole
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - As-builts & C&I Diagram
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: As-built as per ATOC requirements
label | FREQUENCY: At the completion of the Lot of work
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings
label | CONFORMANCE CRITERIA: As-built as per ATOC requirements
label | RECORDS: Asbuilt Drawing
holdpoint | AUTHORITY HOLDPOINT
section | ITP APPROVAL
checkpoint | ITP Approval
textbox | QA Compiled By:
textbox | QA checked By Project manager:
textbox | QA checked By Contract Manager:
textbox | Accepted By Design/AT Engineer:
checklist | ITP - ETPO - Asphalt Works | itp |  |  |  |  | ITP - ETPO - Asphalt Works
section | Materials
checkpoint | 1.1 - Bitumen
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: As per Design
label | FREQUENCY: Passing all tests listed in Table 1 of NZTA M/1
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Passing all tests listed in Table 1 of NZTA M1/A (2019) and pavement design
label | CONFORMANCE CRITERIA: Testing/Visual
label | RECORDS: IANZ Lab results
checkpoint | 1.2 - Asphalt Mix Design
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: JMF approved
label | FREQUENCY: JMF approved
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): AUSTROADS -PMB AC20 & PMB AC14
label | CONFORMANCE CRITERIA: Testing/Visual
label | RECORDS: IANZ Lab results
checkpoint | 1.3 - Production Tests
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: NZTA M/10 spec
label | FREQUENCY: 1 set every 300t
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): NZTA M/10
label | CONFORMANCE CRITERIA: Testing/Visual
label | RECORDS: IANZ Lab results
section | Left Turn Slip lane Wideneing and Wider traffic Island reinstatement Area (Detail 1) SUBGRADE
checkpoint | 2.1 - Cut to Waste (635mm)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Dip from stringline or survey as-built
label | FREQUENCY: 10m each lane
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): +0 / -20mm to design level
label | CONFORMANCE CRITERIA: Inprocess Inspection
label | RECORDS: Stringline Sheet
checkpoint | 2.2 - Insitu Subgrade Testing
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Scalar Testing, Shear vane testing and proof rolling if practical
label | FREQUENCY: 10m each lane
label | ○ Proof rolling - continuous
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): CBR greater than 1%
label | ○ No visual movement or cracking in the existing subgrade.
label | CONFORMANCE CRITERIA: The Scala Penetrometer testing shall be undertaken to a depth 1m below the design subgrade level. If CBR less than 3.5%:
label | RECORDS: Scalar sheet
checkpoint | 2.3 - Subgrade Improvement Layer
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: CBR test
label | FREQUENCY: Every 10m intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): CBR greater than 15%
label | CONFORMANCE CRITERIA: Granular subgrade improvement material such as sand, GAP40, GAP65 or GAP100 with a minimum 4 days soaked CBR of 15% may be used. All granular subgrade improvement layer shall be compacted in layer(s) with layer thickness between 2.5 and 4 times the norminal maximum aggregate size. The preferred sil material is geotextile warpped sand (Woodhill). Other granular sil material must be placed on CLass C geotextile and geogrid triax TX170 or similar equivalent and shall not be used unless accepted by the engineer.
label | RECORDS: Scala test sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3.1 - Geotextile or Geogrid
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Visual inspection
label | FREQUENCY: Throughout the surface
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Either Geo Textile or Geo grid can be placed below the Subgrade improvement layer
label | RECORDS: Photos
section | Concrete Subbase
checkpoint | 3.1 - Concrete Subbase
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Concrete Dockets
label | FREQUENCY: each truck
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): visual inspection
label | CONFORMANCE CRITERIA:
label | RECORDS: Concrete Dockets
section | Sealing - Grade 4 or Tack/Blind if paving on granular surface.
checkpoint | 4.1 - Emulsion tack coat
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Dip emulsion tank
label | FREQUENCY: each lot
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): CAT60 cationic emulsion or approved alternative
label | ○ 0.6 (minimum residual) to 0.9 lt/m2
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: Spray sheet
checkpoint | 4.2 - Blinding
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Aggregate Supply
label | FREQUENCY: each lot
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Even application of blinding where required in accordance with the design drawings.
label | CONFORMANCE CRITERIA: Blinding mix or chip
label | RECORDS: Spray sheet
checkpoint | 4.3 - Chipseal
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Bitumen Application
label | FREQUENCY: each lot
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Grade 4 membrane seal (minimum residual bitumen application of 1.0L/m2)
label | CONFORMANCE CRITERIA: Inprocess Inspection
label | RECORDS: Spray sheet
checkpoint | 4.4 - AC 14 RW 30 -PG 64 H - 65mm
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Forecast and thermometer
label | FREQUENCY: Daily
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Check weather reports
label | ○ No fog, rain or wet surface. Base temp ≥ 5o C
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: AC check sheet
checkpoint | 4.5 - AC 14 RW 30 -PG 64 H - 65mm
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Asphalt Trace Sheet as part of QA
label | FREQUENCY: During construction
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Asphalt Temperature
label | ○ Amount of asphalt laid average calcaulated asphalt thickness etc
label | CONFORMANCE CRITERIA: Inprocess Inspection
label | RECORDS: AC check sheet
checkpoint | 4.6 - AC 14 RW 30 -PG 64 H - 65mm
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Visual
label | FREQUENCY: Prior to starting
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure previous layer is broomed clean
label | ○ Free of detritius and loose material
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: AC check sheet
checkpoint | 4.7 - AC 14 RW 30 -PG 64 H - 65mm
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Grading, binder content, max density, temp
label | FREQUENCY: 1/300t
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Production tests NZTA M/10
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: Lab test
checkpoint | 4.8 - AC 14 RW 30 -PG 64 H - 65mm
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Visual inspection by the Engineer
label | FREQUENCY: Each lot
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Surface finish inspection
label | ○ Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate.
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: Inspection sheet
checkpoint | 4.9 - AC14 PMBRW15- PG 64 V (second layer)-55mm
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Forecast and thermometer
label | FREQUENCY: Daily
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Check weather reports
label | ○ No fog, rain or wet surface. Base temp ≥ 5o C
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: AC check sheet
checkpoint | 4.1 - AC14 PMBRW15- PG 64 V (second layer)-55mm
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Asphalt Trace Sheet as part of QA
label | FREQUENCY: During construction
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Asphalt Temperature
label | ○ Amount of asphalt laid average calcaulated asphalt thickness etc
label | CONFORMANCE CRITERIA: Inprocess Inspection
label | RECORDS: AC check sheet
checkpoint | 4.11 - AC14 PMBRW15- PG 64 V (second layer)-55mm
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Visual
label | FREQUENCY: Prior to starting
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure previous layer is broomed clean
label | ○ Free of detritius and loose material
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: AC check sheet
checkpoint | 4.12 - AC14 PMBRW15- PG 64 V (second layer)-55mm
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Grading, binder content, max density, temp
label | FREQUENCY: 1/300t
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Production tests NZTA M/10
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: Lab test
checkpoint | 4.13 - AC14 PMBRW15- PG 64 V (second layer)-55mm
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Visual inspection by the Engineer
label | FREQUENCY: Each lot
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Surface finish inspection
label | ○ Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate.
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: Inspection sheet
checkpoint | 4.14 - AC14 PMBRW15- PG 64 V (Top layer)-55mm
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Forecast and thermometer
label | FREQUENCY: Daily
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Check weather reports
label | ○ No fog, rain or wet surface. Base temp ≥ 5o C
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: AC check sheet
checkpoint | 4.15 - AC14 PMBRW15- PG 64 V (Top layer)-55mm
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Asphalt Trace Sheet as part of QA
label | FREQUENCY: During construction
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Asphalt Temperature
label | ○ Amount of asphalt laid average calcaulated asphalt thickness etc
label | CONFORMANCE CRITERIA: Inprocess Inspection
label | RECORDS: AC check sheet
checkpoint | 4.16 - AC14 PMBRW15- PG 64 V (Top layer)-55mm
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Visual
label | FREQUENCY: Prior to starting
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure previous layer is broomed clean
label | ○ Free of detritius and loose material
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: AC check sheet
checkpoint | 4.17 - AC14 PMBRW15- PG 64 V (Top layer)-55mm
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Grading, binder content, max density, temp
label | FREQUENCY: 1/300t
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Production tests NZTA M/10
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: Lab test
checkpoint | 4.18 - AC14 PMBRW15- PG 64 V (Top layer)-55mm
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Visual inspection by the Engineer
label | FREQUENCY: Each lot
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Surface finish inspection
label | ○ Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate.
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: Inspection sheet
checkpoint | 4.19 - AC14RW30 / AC14 PMB RW 15
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Dip from stringline or survey as-built
label | FREQUENCY: grid pattern
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): (+10 / -10mm)
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: Inspection sheet
checkpoint | 4.20 - AC14RW30 / AC14 PMB RW 15
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: NDM/Cores (Testing plan to be agreed with client)
label | FREQUENCY: 1/300m2 or min 8 cores
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Density testing
label | ○ Air voids to meet NZTA M/10:2020 +3% / -2%
label | CONFORMANCE CRITERIA: Paved Area: Air voids, in accordance with NZTA M/10 (2020)
label | ○ Testing undertaken in accordance with NZTA M/10
label | RECORDS: Core test report
checkpoint | 4.21 - AC14RW30 / AC14 PMB RW 15
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Cores depth (Location plan to be agreed with client)
label | FREQUENCY: 1/300m2 or min 8 cores
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Thickness
label | – Depth should not be less than design asphalt depth of thickness
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: Core test report
section | Trench Repair pavement and Right Turn Bay (Detail 2 & Detail 3) SUBGRADE
checkpoint | 5.1 - Cut to Waste
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Dip from stringline or survey as-built
label | FREQUENCY: 10m each lane
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): 740mm (Undercut areas ) and 490mm ( if existing pavement thickness is less than 300mm) and 190mm ( if existing pavment thickness is 300mm
label | ○ +0 / -20mm to design level
label | CONFORMANCE CRITERIA: Inprocess Inspection
label | RECORDS: Stringline Sheet
checkpoint | 5.2 - Insitu Subgrade Testing
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Scalar Testing, Shear vane testing and proof rolling if practical
label | FREQUENCY: 10m each lane
label | ○ Proof rolling - continuous
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): CBR greater than 3.5% below 490mm from the design level
label | ○ No visual movement or cracking in the existing subgrade.
label | CONFORMANCE CRITERIA: The Scala Penetrometer testing shall be undertaken to a depth 740mm below the design level. If CBR is less than 3.5%:
label | RECORDS: Scalar sheet
section | Subbase (IF the exixsting base or subbase material is less than 300mm)
checkpoint | 6.1 - Subgrade Improvement Layer
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: CBR test
label | FREQUENCY: Every 10m intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): CBR greater than 15%
label | CONFORMANCE CRITERIA: Granular subgrade improvement material such as sand, GAP40, GAP65 or GAP100 with a minimum 4 days soaked CBR of 15% may be used. All granular subgrade improvement layer shall be compacted in layer(s) with layer thickness between 2.5 and 4 times the nominal maximum aggregate size. The preffered sil material is geotextile wrapped sand (Woodhill). Other granular sil material must be placed on Class C geotextile and geogrid triax TX170 or similar equivalent and shall not be used unless accepted by the engineer.
label | RECORDS: Scala test sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 - Geotextile or Geogrid
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Visual inspection
label | FREQUENCY: Throughout the surface
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Either Geo Textile or Geo grid can be placed below the Subgrade improvement layer
label | RECORDS: Photos
section | Subbase (IF the exixsting base or subbase material is less than 300mm) Contingency plan
checkpoint | 6.3 - Concrete Subbase
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Concrete Dockets
label | FREQUENCY: each truck
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): visual inspection
label | CONFORMANCE CRITERIA:
label | RECORDS: Concrete Dockets
checkpoint | 6.4 - Geotextile or Geogrid
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Visual inspection
label | FREQUENCY: Throughout the surface
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Either Geo Textile or Geo grid can be placed below the concrete subbase
label | RECORDS: Photos
section | Sealing - Grade 4 or Tack/Blind if paving on granular surface.
checkpoint | 7.1 - Emulsion tack coat
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Dip emulsion tank
label | FREQUENCY: each lot
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): CAT60 cationic emulsion or approved alternative
label | ○ 0.6 (minimum residual) to 0.9 lt/m2
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: Spray sheet
checkpoint | 7.2 - Blinding
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Aggregate Supply
label | FREQUENCY: each lot
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Even application of blinding where required in accordance with the design drawings.
label | CONFORMANCE CRITERIA: Blinding mix or chip
label | RECORDS: Spray sheet
checkpoint | 7.3 - Chipseal
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Bitumen Application
label | FREQUENCY: each lot
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Grade 4 membrane seal (minimum residual bitumen application of 1.0L/m2)
label | CONFORMANCE CRITERIA: Inprocess Inspection
label | RECORDS: Spray sheet
checkpoint | 7.4 - AC 14 RW 30 -PG 64 H - 70mm
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Forecast and thermometer
label | FREQUENCY: Daily
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Check weather reports
label | ○ No fog, rain or wet surface. Base temp ≥ 5o C
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: AC check sheet
checkpoint | 7.5 - AC 14 RW 30 -PG 64 H - 70mm
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Asphalt Trace Sheet as part of QA
label | FREQUENCY: During construction
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Asphalt Temperature
label | ○ Amount of asphalt laid average calcaulated asphalt thickness etc
label | CONFORMANCE CRITERIA: Inprocess Inspection
label | RECORDS: AC check sheet
checkpoint | 7.6 - AC 14 RW 30 -PG 64 H - 70mm
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Visual
label | FREQUENCY: Prior to starting
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure previous layer is broomed clean
label | ○ Free of detritius and loose material
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: AC check sheet
checkpoint | 7.7 - AC 14 RW 30 -PG 64 H - 70mm
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Grading, binder content, max density, temp
label | FREQUENCY: 1/300t
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Production tests NZTA M/10
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: Lab test
checkpoint | 7.8 - AC 14 RW 30 -PG 64 H - 70mm
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Visual inspection by the Engineer
label | FREQUENCY: Each lot
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Surface finish inspection
label | ○ Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate.
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: Inspection sheet
checkpoint | 7.9 - AC 14 RW 30 -PG 64 H (second layer)-65mm
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Forecast and thermometer
label | FREQUENCY: Daily
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Check weather reports
label | ○ No fog, rain or wet surface. Base temp ≥ 5o C
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: AC check sheet
checkpoint | 7.1 - AC 14 RW 30 -PG 64 H (second layer)-65mm
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Asphalt Trace Sheet as part of QA
label | FREQUENCY: During construction
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Asphalt Temperature
label | ○ Amount of asphalt laid average calcaulated asphalt thickness etc
label | CONFORMANCE CRITERIA: Inprocess Inspection
label | RECORDS: AC check sheet
checkpoint | 7.11 - AC 14 RW 30 -PG 64 H (second layer)-65mm
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Visual
label | FREQUENCY: Prior to starting
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure previous layer is broomed clean
label | ○ Free of detritius and loose material
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: AC check sheet
checkpoint | 7.12 - AC 14 RW 30 -PG 64 H (second layer)-65mm
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Grading, binder content, max density, temp
label | FREQUENCY: 1/300t
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Production tests NZTA M/10
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: Lab test
checkpoint | 7.13 - AC 14 RW 30 -PG 64 H (second layer)-65mm
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Visual inspection by the Engineer
label | FREQUENCY: Each lot
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Surface finish inspection
label | ○ Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate.
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: Inspection sheet
checkpoint | 7.14 - AC14 PMBRW15- PG 64 V (Top layer)-55mm
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Forecast and thermometer
label | FREQUENCY: Daily
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Check weather reports
label | ○ No fog, rain or wet surface. Base temp ≥ 5o C
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: AC check sheet
checkpoint | 7.15 - AC14 PMBRW15- PG 64 V (Top layer)-55mm
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Asphalt Trace Sheet as part of QA
label | FREQUENCY: During construction
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Asphalt Temperature
label | ○ Amount of asphalt laid average calcaulated asphalt thickness etc
label | CONFORMANCE CRITERIA: Inprocess Inspection
label | RECORDS: AC check sheet
checkpoint | 7.16 - AC14 PMBRW15- PG 64 V (Top layer)-55mm
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Visual
label | FREQUENCY: Prior to starting
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure previous layer is broomed clean
label | ○ Free of detritius and loose material
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: AC check sheet
checkpoint | 7.17 - AC14 PMBRW15- PG 64 V (Top layer)-55mm
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Grading, binder content, max density, temp
label | FREQUENCY: 1/300t
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Production tests NZTA M/10
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: Lab test
checkpoint | 7.18 - AC14 PMBRW15- PG 64 V (Top layer)-55mm
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Visual inspection by the Engineer
label | FREQUENCY: Each lot
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Surface finish inspection
label | ○ Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate.
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: Inspection sheet
checkpoint | 7.19 - AC14RW30 / AC14 PMB RW 15
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Dip from stringline or survey as-built
label | FREQUENCY: grid pattern
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): (+10 / -10mm)
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: Inspection sheet
checkpoint | 7.20 - AC14RW30 / AC14 PMB RW 15
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: NDM/Cores (Testing plan to be agreed with client)
label | FREQUENCY: 1/300m2 or min 8 cores
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Density testing
label | ○ Air voids to meet NZTA M/10:2020 +3% / -2%
label | CONFORMANCE CRITERIA: Paved Area: Air voids, in accordance with NZTA M/10 (2020)
label | ○ Testing undertaken in accordance with NZTA M/10
label | RECORDS: Core test report
checkpoint | 7.21 - AC14RW30 / AC14 PMB RW 15
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Cores depth (Location plan to be agreed with client)
label | FREQUENCY: 1/300m2 or min 8 cores
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Thickness
label | – Depth should not be less than design asphalt depth of thickness
label | CONFORMANCE CRITERIA: Inprocess Testing
label | RECORDS: Core test report
section | ITP APPROVAL
checkpoint | ITP Approval
textbox | QA Compiled By:
textbox | QA checked By Project manager:
textbox | QA checked By Contract Manager:
textbox | Accepted By Design/AT Engineer: