## Table 1
Inspection Plan Checklist
Frame All Walls Doc.Ref-ITC-002-Rev1
Project Information
Name: |  | RAAFA Stirling Retirement Apartments – Stage 6 | [5 empty] | Work: |  |  |  |  | All applicable
Address: |  | 2 Bull Creek Drive, Bull Creek, WA, 6149 | [5 empty] | Location:
Head Contractor: |  | Georgiou Group Pty Ltd | [5 empty] | Drawing Ref. :
Details
PECOMMENCEMENT | [9 empty] | STATUS
SPECIFICATION / DRW No. | [9 empty] | OK | [5 empty] | N/A | DATE
DESIGN & COMPUTATIONS
SAMPLES
MATERIALS MEET SPECIFICATION REQUIREMENTS
CHECK FOR DAMAGE
MAINTAIN SUITABLE STORAGE
INSTALLATION REPORT
Item 1: ADDRESS SAFETY WITH SWMS
Item 2: SET OUT
Item 3: FURRING CHANNEL TO WALLS
Item 4: METAL STUD WALL FRAME
Item 5: NOGGINGS
Item 6: CHECK NO SCREWS IN DEFLECTION HEAD
Item 7: CLEAN UP
N.C.N. / C.A.R.
FINAL INSPECTION
WITNESSED BY: |  |  | NAME |  |  |  | SIGNATURE |  | POSITION | [6 empty] | DATE
SUBCONTRACTOR: | [8 empty] | Foreman
BUILDER:
OTHER:
COMMENTS:
Scope: Frame All Walls |  |  |  |  | ITP Document No.: 2 | [6 empty] | Revision No. C | [6 empty] | Date of Revision: 15/10/2024
Project Name: RAAFA Stirling Retirement Apartments – Stage 6 | [11 empty] | Organization Name: Georgiou Group Pty Ltd
Project Address: 2 Bull Creek Drive, Bull Creek, WA, 6149
Prepared by
Name: Caleb Chae |  |  |  |  | Position: Contract Administrator | [6 empty] | Signature: | [6 empty] | Date: 15/10/2024
Approved by
Name: ShuHan Hong |  |  |  |  | Position: Site Foreman | [6 empty] | Signature: | [6 empty] | Date: 15/10/2024
Level: | [11 empty] | Room No./Area:
Wall Type: | [11 empty] | DWG No: | [8 empty] | Rev:
Project Specification: Architectural Specification Rev 9 ¦ Australian Standards: AS2589 ¦ Project Drawings: Architectural Drawings A0001 A0040 A0041 A0060 A0061 Series and A0500 Series
W = Witness, HP = Hold Point, S = Surveillance, R = Review
Item | Activity |  |  | Reference Documents |  | Acceptance Criteria | [7 empty] | Frequency |  |  |  | Verification Records/Comments |  | Inspection By
[20 empty] | Subcontractor |  | Georgiou | Client
1 | Address Safety |  |  | SWMS |  | Safety Method Work Sheet approved by Georgiou Group Pty Ltd | [7 empty] | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos |  | S |  | S
2 | Set out walls |  |  | Architect drawings |  | Light Weight Wall Plan approved by Georgiou Group Pty Ltd Studco Wall design & installation manual Volume 3.2 | [7 empty] | Each unit |  |  |  | Visual Checklist Attached marked off drawings and photos |  | S |  | S
3 | Furring channel to walls |  |  | Architect drawings |  | Light Weight Wall Plan approved by Georgiou Group Pty Ltd Studco Wall design & installation manual Volume 3.2 | [7 empty] | Each unit |  |  |  | Visual Checklist Attached marked off drawings and photos |  | S |  | S
4 | Metal stud wall frame |  |  | Architect drawings |  | Light Weight Wall Plan approved by Georgiou Group Pty Ltd. Studco Wall design & installation manual Volume 3.2 | [7 empty] | Each unit |  |  |  | Visual Checklist Attached marked off drawings and photos |  | S |  | S
5 | Noggins |  |  |  |  | As per scope of work. Studco Wall design & installation manual Volume 3.2 | [7 empty] | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos |  | S |  | S
6 | Check no screws in deflection head |  |  |  |  | No screws in deflection head | [7 empty] | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos |  | S |  | S
7 | Clean up |  |  |  |  | Waste all cleaned. Tools and materials placed well. | [7 empty] | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos |  |  |  | R
Comments:
Date of Inspection: | [10 empty] | Carried out by:
Verification Statement This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s) | [14 empty] | Attachments  Checklists  Photos  Dockets  Sample Material  Drawings  Calibration Certificates  Test Results / Certificate  Others:  Inspection reports
Signed : | [14 empty] | Date: