## Table 1
Inspection Plan Checklist
Sheet All Walls & Frame ceiling Doc.Ref-ITC-003-Rev1
Project Information
Name: |  | RAAFA Stirling Retirement Apartments – Stage 6 |  |  |  |  | Work: |  |  |  | All applicable
Address: |  | 2 Bull Creek Drive, Bull Creek, WA, 6149 |  |  |  |  | Location:
Head Contractor: |  | Georgiou Group Pty Ltd |  |  |  |  | Drawing Ref. :
Details
PECOMMENCEMENT | [8 empty] | STATUS
SPECIFICATION / DRW No. | [8 empty] | OK |  |  |  | N/A | DATE
DESIGN & COMPUTATIONS
SAMPLES
MATERIALS MEET SPECIFICATION REQUIREMENTS
CHECK FOR DAMAGE
MAINTAIN SUITABLE STORAGE
INSTALLATION REPORT
Item 1: ADDRESS SAFETY WITH SWMS
Item 2: INSTALL INSULATION
Item 3: SIGN OFF FOR CLOSING WALL
Item 4: SHEETING FIRE WALLS
Item 5: CAULKING FIRE WALLS
Item 6: SHEET REMAINING WALLS
Item 7: FRAME CEILING
Item 8: TRIM OUT ACCESS HATCHES
Item 9: CLEAN UP
N.C.N. / C.A.R.
FINAL INSPECTION
WITNESSED BY: |  |  | NAME |  |  | SIGNATURE |  | POSITION |  |  |  |  | DATE
SUBCONTRACTOR: | [7 empty] | Foreman
BUILDER:
OTHER:
COMMENTS:
Scope: Sheet All Walls & Frame Ceiling |  |  |  |  | ITP Document No.: 3 | [7 empty] | Revision No. D |  |  |  |  | Date of Revision: 30/10/2024
Project Name: RAAFA Stirling Retirement Apartments – Stage 6 | [12 empty] | Organization Name: Georgiou Group Pty Ltd
Project Address: 2 Bull Creek Drive, Bull Creek, WA, 6149
Prepared by
Name: Caleb Chae |  |  |  |  | Position: Contract Administrator | [7 empty] | Signature: |  |  |  |  | Date: 30/10/2024
Approved by
Name: ShuHan Hong |  |  |  |  | Position: Site Foreman | [7 empty] | Signature: |  |  |  |  | Date: 30/10/2024
Level: | [9 empty] | Room No./Area:
Project Specification: Architectural Specification Rev 9 ¦ Australian Standards: AS2589 ¦ Project Drawings: Architectural Drawings A0000 Series and A500 Series
W = Witness, HP = Hold Point, S = Surveillance, R = Review
Item | Activity |  |  | Reference Documents | Acceptance Criteria | [6 empty] | Frequency |  |  |  | Verification Records/Comments | Inspection By
[17 empty] | Subcontractor |  | Georgiou | Client
1 | Address Safety |  |  | SWMS | Safety Method Work Sheet approved by Georgiou Group Pty Ltd | [6 empty] | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos | S |  | S
2 | Install insulation |  |  | Architect drawings | Light Weight Wall Plan approved by Georgiou Group Pty Ltd. EcoTherm & Ecowool insulation installation guide | [6 empty] | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos | S |  | S
3 | Sign off for closing wall by Georgiou Group Pty Ltd |  |  | Architect drawings | Light Weight Wall Plan approved by Georgiou Group Pty Ltd. Studco Wall design & installation manual Volume 3.2 | [6 empty] | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos | S |  | S, R
4 | Sheet fire walls |  |  | Architect drawings | Light Weight Wall Plan approved by Georgiou Group Pty Ltd. GTEK Ceiling & Wall Solutions Rev. Mar 2024 | [6 empty] | Each unit |  |  |  | Visual Checklist Attached marked off drawings and photos | S |  | HP
5 | Caulking fire walls |  |  | Architect drawings | GTEK Ceiling & Wall Solutions Rev. Mar 2024 | [6 empty] | Each unit |  |  |  | Visual Checklist Attached marked off drawings and photos | S |  | S
6 | Sheet remaining walls |  |  | Architect drawings | Light Weight Wall Plan approved by Georgiou Group Pty Ltd. GTEK Ceiling & Wall Solutions Rev. Mar 2024 Class 2-9 Building. EcoTherm & Ecowool insulation installation guide | [6 empty] | Each unit |  |  |  | Visual Checklist Attached marked off drawings and photos | S |  | HP
7 | Frame ceiling |  |  | Architect drawings | Architect RCP drawings approved by Georgiou Group Pty Ltd. Studco Wall design & installation manual Volume 3.2 | [6 empty] | Each unit |  |  |  | Visual Checklist Attached marked off drawings and photos | S |  | S
8 | Trim out access hatches |  |  | Architect drawings | Architect RCP drawings approved by Georgiou Group Pty Ltd. | [6 empty] | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos | S |  | S
9 | Clean up |  |  |  | Waste all cleaned. Tools and materials placed well. | [6 empty] | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos |  |  | R
Comments:
Date of Inspection: | [14 empty] | Carried out by:
Verification Statement This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s) | [12 empty] | Attachments  Checklists  Photos  Dockets  Sample Material  Drawings  Calibration Certificates  Test Results / Certificate  Others:  Inspection reports
Signed : | [12 empty] | Date: