## Table 1
Inspection Plan Checklist
Hang Ceilings and Stop, Sand Walls & Ceilings Doc.Ref-ITC-004-Rev1
Project Information
Name: |  | RAAFA Stirling Retirement Apartments – Stage 6 | [5 empty] | Work: |  |  | All applicable
Address: |  | 2 Bull Creek Drive, Bull Creek, WA, 6149 | [5 empty] | Location:
Head Contractor: |  | Georgiou Group Pty Ltd | [5 empty] | Drawing Ref. :
Details
PECOMMENCEMENT | [9 empty] | STATUS
SPECIFICATION / DRW No. | [9 empty] | OK |  |  | N/A | DATE
DESIGN & COMPUTATIONS
SAMPLES
MATERIALS MEET SPECIFICATION REQUIREMENTS
CHECK FOR DAMAGE
MAINTAIN SUITABLE STORAGE
INSTALLATION REPORT
Item 1: ADDRESS SAFETY WITH SWMS
Item 2: INSTALL INSULATION
Item 3: SIGN OFF FOR CLOSING CEILING
Item 4: SHEETING
Item 5: STOPPING TO WALLS & CEILINGS
Item 6: SANDING TO WALLS & CEILINGS
Item 7: FIT ACCESS HATCH FRAME
Item 8: CUT OUTS
Item 9: CLEAN UP
N.C.N. / C.A.R.
FINAL INSPECTION
WITNESSED BY: |  |  | NAME |  |  | SIGNATURE |  |  | POSITION |  |  |  | DATE
SUBCONTRACTOR: | [8 empty] | Foreman
BUILDER:
OTHER:
COMMENTS:
Scope: Hang ceilings and stop, sand walls & ceilings |  |  |  |  | ITP Document No.: 4 | [7 empty] | Revision No. B |  |  | Date of Revision: 15/10/2024
Project Name: RAAFA Stirling Retirement Apartments – Stage 6 | [12 empty] | Organization Name: Georgiou Group Pty Ltd
Project Address: 2 Bull Creek Drive, Bull Creek, WA, 6149
Prepared by
Name: Caleb Chae |  |  |  |  | Position: Contract Administrator | [7 empty] | Signature: |  |  | Date: 15/10/2024
Approved by
Name: ShuHan Hong |  |  |  |  | Position: Site Foreman | [7 empty] | Signature: |  |  | Date: 15/10/2024
Level: | [12 empty] | Room No./Area:
Project Specification: Architectural Specification REV 9¦ Australian Standards: AS2589 ¦ Project Drawings: A500 Series A600 Series A1000 Series
W = Witness, HP = Hold Point, S = Surveillance, R = Review
Item | Activity |  |  | Reference Documents |  |  | Acceptance Criteria |  |  |  |  | Frequency |  |  | Verification Records/Comments | Inspection By
[16 empty] | Subcontractor | Georgiou | Client
1 | Address Safety |  |  | SWMS |  |  | Safety Method Work Sheet approved by Georgiou Group Pty Ltd |  |  |  |  | Each location |  |  | Visual Checklist Attached marked off drawings and photos | S | S
2 | Insulation to ceilings |  |  | Architect drawings |  |  | Architect RCP drawings approved by Georgiou Group Pty Ltd EcoTherm & Ecowool insulation installation guide |  |  |  |  | Each unit |  |  | Visual Checklist Attached marked off drawings and photos | S | S
3 | Sign off for closing ceiling by Georgiou Group Pty Ltd |  |  | Architect drawings |  |  | Architect RCP drawings approved by Georgiou Group Pty Ltd |  |  |  |  | Each location |  |  | Visual Checklist Attached marked off drawings and photos | S | S, R
4 | Sheets to ceiling |  |  | Architect drawings |  |  | Architect RCP drawings approved by Georgiou Group Pty Ltd. GTEK Ceiling & Wall Solutions Rev. Mar.2024 |  |  |  |  | Each unit |  |  | Visual Checklist Attached marked off drawings and photos | S | HP
5 | Stopping to walls & ceilings |  |  | Architect drawings |  |  | GTEK Ceiling & Wall Solutions Rev. Mar.2024 |  |  |  |  | Each location |  |  | Visual Checklist Attached marked off drawings and photos | S | S
6 | Sanding to walls & ceilings |  |  | Architect drawings |  |  | GTEK Ceiling & Wall Solutions Rev. Mar.2024 |  |  |  |  | Each location |  |  | Visual Checklist Attached marked off drawings and photos | S | S
7 | Fit access hatch frame |  |  | Architect drawings |  |  | Architect RCP drawings approved by Georgiou Group Pty Ltd. |  |  |  |  | Each location |  |  | Visual Checklist Attached marked off drawings and photos | S | S
8 | Cut out for lights |  |  | Architect drawings |  |  | Architect RCP drawings approved by Georgiou Group Pty Ltd. |  |  |  |  | Each location |  |  | Visual Checklist Attached marked off drawings and photos | S | S
9 | Clean up | [5 empty] | Waste all cleaned. Tools and materials placed well. |  |  |  |  | Each location |  |  | Visual Checklist Attached marked off drawings and photos |  | R
Comments:
Date of Inspection: | [11 empty] | Carried out by:
Verification Statement This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s) | [12 empty] | Attachments  Checklists  Photos  Dockets  Sample Material  Drawings  Calibration Certificates  Test Results / Certificate  Others:  Inspection reports
Signed : | [12 empty] | Date: