## Table 1
Inspection Plan Checklist
Rigid Board Doc.Ref-ITC-006-Rev1
Project Information
Name: |  | RAAFA Stirling Retirement Apartments – Stage 6 |  |  |  |  | Work: |  |  | All applicable
Address: |  | 2 Bull Creek Drive, Bull Creek, WA, 6149 |  |  |  |  | Location:
Head Contractor: |  | Georgiou Group Pty Ltd |  |  |  |  | Drawing Ref. :
Details
PECOMMENCEMENT | [8 empty] | STATUS
SPECIFICATION / DRW No. | [8 empty] | OK |  |  | N/A | DATE
DESIGN & COMPUTATIONS
SAMPLES
MATERIALS MEET SPECIFICATION REQUIREMENTS
CHECK FOR DAMAGE
MAINTAIN SUITABLE STORAGE
INSTALLATION REPORT
Item 1: ADDRESS SAFETY WITH SWMS
Item 2: SET OUT
Item 3: RIGID BOARD INSTALLATION
Item 4: TAPE AND SEAL
Item 5: CLEAN UP
N.C.N. / C.A.R.
FINAL INSPECTION
WITNESSED BY: |  |  | NAME |  |  | SIGNATURE |  | POSITION |  |  |  | DATE
SUBCONTRACTOR: | [7 empty] | Foreman
BUILDER:
OTHER:
COMMENTS:
Scope: Rigid Board |  |  |  | ITP Document No.: 6 | [7 empty] | Revision No. B |  |  |  | Date of Revision: 15/10/2024
Project Name: RAAFA Stirling Retirement Apartments – Stage 6 | [11 empty] | Organization Name: Georgiou Group Pty Ltd
Project Address: 2 Bull Creek Drive, Bull Creek, WA, 6149
Prepared by
Name: Caleb Chae |  |  |  | Position: Contract Administrator | [7 empty] | Signature: |  |  |  | Date: 15/10/2024
Approved by
Name: ShuHan Hong |  |  |  | Position: Site Foreman | [7 empty] | Signature: |  |  |  | Date: 15/10/2024
Level: | [11 empty] | Room No./Area:
Specification: Architectural Specification Rev 9 ¦ Australian Standards: AS2589 ¦ Project Drawings: A0000, A0599, A0600, A0601, A0602, A0603, A0604, A0605
W = Witness, HP = Hold Point, S = Surveillance, R = Review
Item | Activity |  | Reference Documents |  | Acceptance Criteria |  |  |  |  | Frequency |  |  |  | Verification Records/Comments | Inspection By
[15 empty] | Subcontractor |  | Georgiou | Client
1 | Address Safety |  | SWMS |  | Safety Method Work Sheet approved by Georgiou Group Pty Ltd |  |  |  |  | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos | S |  | S
2 | Set out Rigid Board |  | Architect drawings |  | Reflected Ceiling Plan approved by Georgiou Group Pty Ltd |  |  |  |  | Each location |  |  |  | Visual Checklist | S |  | S
3 | Install Rigid Board |  | Architect drawings |  | Reflected Ceiling Plan approved by Georgiou Group Pty Ltd Kingspan Kooltherm K10 installation guide 2021 |  |  |  |  | Each location |  |  |  | Visual Checklist | S |  | S
4 | Tape & Seal |  |  |  | Kingspan Kooltherm K10 installation guide 2021 |  |  |  |  | Each location |  |  |  | Visual Checklist | S |  | S
5 | Clean up |  |  |  | Waste all cleaned. Tools and materials placed well. |  |  |  |  | Each location |  |  |  | Visual Checklist |  |  | R
Comments:
Date of Inspection: | [10 empty] | Carried out by:
Verification Statement This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s) | [11 empty] | Attachments  Checklists  Photos  Dockets  Sample Material  Drawings  Calibration Certificates  Test Results / Certificate  Others:  Inspection reports
Signed : | [11 empty] | Date: