## Sheet1
1 | Address Safety | SWMS | Safety Method Work Sheet approved by Georgiou Group Pty Ltd | Each location | Visual Checklist Attached marked off drawings and photos | S | S | 1 - Address Safety | Reference Documents - SWMS | Acceptance Criteria - Safety Method Work Sheet approved by Georgiou Group Pty Ltd | Frequency - Each location | Verification Records/Comments - Visual Checklist Attached marked off drawings and photos | Inspection By: Subcontractor - S | Inspection By: Georgiou - S | 1 - Address Safety
2 | Set out Rigid Board | Architect drawings | Reflected Ceiling Plan approved by Georgiou Group Pty Ltd | Each location | Visual Checklist | S | S | 2 - Set out Rigid Board | Reference Documents - Architect drawings | Acceptance Criteria - Reflected Ceiling Plan approved by Georgiou Group Pty Ltd | Frequency - Each location | Verification Records/Comments - Visual Checklist | Inspection By: Subcontractor - S | Inspection By: Georgiou - S | Reference Documents - SWMS
3 | Install Rigid Board | Architect drawings | Reflected Ceiling Plan approved by Georgiou Group Pty Ltd Kingspan Kooltherm K10 installation guide 2021 | Each location | Visual Checklist | S | S | 3 - Install Rigid Board | Reference Documents - Architect drawings | Acceptance Criteria - Reflected Ceiling Plan approved by Georgiou Group Pty Ltd Kingspan Kooltherm K10 installation guide 2021 | Frequency - Each location | Verification Records/Comments - Visual Checklist | Inspection By: Subcontractor - S | Inspection By: Georgiou - S | Acceptance Criteria - Safety Method Work Sheet approved by Georgiou Group Pty Ltd
4 | Tape CHAR(AMP) Seal |  | Kingspan Kooltherm K10 installation guide 2021 | Each location | Visual Checklist | S | S | 4 - Tape CHAR(AMP) Seal | Reference Documents - | Acceptance Criteria - Kingspan Kooltherm K10 installation guide 2021 | Frequency - Each location | Verification Records/Comments - Visual Checklist | Inspection By: Subcontractor - S | Inspection By: Georgiou - S | Frequency - Each location
5 | Clean up |  | Waste all cleaned. Tools and materials placed well. | Each location | Visual Checklist |  | R | 5 - Clean up | Reference Documents - | Acceptance Criteria - Waste all cleaned. Tools and materials placed well. | Frequency - Each location | Verification Records/Comments - Visual Checklist | Inspection By: Subcontractor - | Inspection By: Georgiou - R | Verification Records/Comments - Visual Checklist Attached marked off drawings and photos
Inspection By: Subcontractor - S
Inspection By: Georgiou - S
2 - Set out Rigid Board
Reference Documents - Architect drawings
Acceptance Criteria - Reflected Ceiling Plan approved by Georgiou Group Pty Ltd
Frequency - Each location
Verification Records/Comments - Visual Checklist
Inspection By: Subcontractor - S
Inspection By: Georgiou - S
3 - Install Rigid Board
Reference Documents - Architect drawings
Acceptance Criteria - Reflected Ceiling Plan approved by Georgiou Group Pty Ltd Kingspan Kooltherm K10 installation guide 2021
Frequency - Each location
Verification Records/Comments - Visual Checklist
Inspection By: Subcontractor - S
Inspection By: Georgiou - S
4 - Tape CHAR(AMP) Seal
Reference Documents -
Acceptance Criteria - Kingspan Kooltherm K10 installation guide 2021
Frequency - Each location
Verification Records/Comments - Visual Checklist
Inspection By: Subcontractor - S
Inspection By: Georgiou - S
5 - Clean up
Reference Documents -
Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
Frequency - Each location
Verification Records/Comments - Visual Checklist
Inspection By: Subcontractor -
Inspection By: Georgiou - R