## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITC&ITP No.1 - Speedpanel & Pre-hang Fire Rated Plasterboard | itp |  |  |  |  | ITC&ITP No.1 - Speedpanel & Pre-hang Fire Rated Plasterboard - Rev B
section | Speedpanel & Pre-hang Fire Rated Plasterboard
checkpoint | 1 - Address Safety
label | Reference Documents - SWMS
label | Acceptance Criteria - Safety Method Work Sheet approved by Georgiou Group Pty Ltd
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 2 - Set out Speedpanel walls
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Light Weight Wall Plan approved by Georgiou Group Pty Ltd Speedpanel installation guide revision 1
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 3 - Install Speedpanel
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Light Weight Wall Plan approved by Georgiou Group Pty Ltd. Speedpanel installation guide revision 1
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 4 - Caulking
label | Reference Documents -
label | Acceptance Criteria - Speedpanel installation guide revision 1
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 5 - Clean up
label | Reference Documents -
label | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor -
label | Inspection By: Georgiou - R
checkpoint | 6 - Pre-hang fire rated plasterboard
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Light Weight Wall Plan approved by Georgiou Group Pty Ltd. GTEK Ceiling & Wall Solution Rev. March 2024
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 7 - Taping and stopping
label | Reference Documents - Architect drawings
label | Acceptance Criteria - GTEK Ceiling & Wall Solution Rev. March 2024
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 8 - Clean up
label | Reference Documents -
label | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor -
label | Inspection By: Georgiou - R
checkpoint | Verification Statement
note | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
date | Date of Inspection:
textbox | Carried out by:
note | Attachments
tickbox | Checklists
tickbox | Photos
tickbox | Dockets
tickbox | Sample Material
tickbox | Drawings
tickbox | Calibration Certificates
tickbox | Test Results / Certificate
tickbox | Inspection reports
tickbox | Others:
textbox | Others
signoff | Signed:
checklist | ITC&ITP No.2 - Frame All Walls | itp |  |  |  |  | ITC&ITP No.2 - Frame All Walls - Rev C
section | Frame All Walls
checkpoint | 1 - Address Safety
label | Reference Documents - SWMS
label | Acceptance Criteria - Safety Method Work Sheet approved by Georgiou Group Pty Ltd
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 2 - Set out walls
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Light Weight Wall Plan approved by Georgiou Group Pty Ltd. Studco Wall design & installation manual Volume 3.2
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 3 - Furring channel to walls
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Light Weight Wall Plan approved by Georgiou Group Pty Ltd. Studco Wall design & installation manual Volume 3.2
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 4 - Metal stud wall frame
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Light Weight Wall Plan approved by Georgiou Group Pty Ltd. Studco Wall design & installation manual Volume 3.2
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 5 - Noggins
label | Reference Documents -
label | Acceptance Criteria - As per scope of work. Studco Wall design & installation manual Volume 3.2
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 6 - Check no screws in deflection head
label | Reference Documents -
label | Acceptance Criteria - No screws in deflection head
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 7 - Clean up
label | Reference Documents -
label | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor -
label | Inspection By: Georgiou - R
checkpoint | Verification Statement
note | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
date | Date of Inspection:
textbox | Carried out by:
note | Attachments
tickbox | Checklists
tickbox | Photos
tickbox | Dockets
tickbox | Sample Material
tickbox | Drawings
tickbox | Calibration Certificates
tickbox | Test Results / Certificate
tickbox | Inspection reports
tickbox | Others:
textbox | Others
signoff | Signed:
checklist | ITC&ITP No.3 - Sheet All Walls & Frame Ceiling | itp |  |  |  |  | ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D
section | Sheet All Walls & Frame Ceiling
checkpoint | 1 - Address Safety
label | Reference Documents - SWMS
label | Acceptance Criteria - Safety Method Work Sheet approved by Georgiou Group Pty Ltd
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 2 - Install insulation
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Light Weight Wall Plan approved by Georgiou Group Pty Ltd. EcoTherm & Ecowool insulation installation guide
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 3 - Sign off for closing wall by Georgiou Group Pty Ltd
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Light Weight Wall Plan approved by Georgiou Group Pty Ltd. Studco Wall design & installation manual Volume 3.2
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S, R
checkpoint | 4 - Sheet fire walls
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Light Weight Wall Plan approved by Georgiou Group Pty Ltd. GTEK Ceiling & Wall Solutions Rev. Mar 2024
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - HP
holdpoint | HOLD POINT
checkpoint | 5 - Caulking fire walls
label | Reference Documents - Architect drawings
label | Acceptance Criteria - GTEK Ceiling & Wall Solutions Rev. Mar 2024
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 6 - Sheet remaining walls
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Light Weight Wall Plan approved by Georgiou Group Pty Ltd. GTEK Ceiling & Wall Solutions Rev. Mar 2024 Class 2-9 Building. EcoTherm & Ecowool insulation installation guide
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - HP
holdpoint | HOLD POINT
checkpoint | 7 - Frame ceiling
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Architect RCP drawings approved by Georgiou Group Pty Ltd. Studco Wall design & installation manual Volume 3.2
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 8 - Trim out access hatches
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Architect RCP drawings approved by Georgiou Group Pty Ltd.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 9 - Clean up
label | Reference Documents -
label | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor -
label | Inspection By: Georgiou - R
checkpoint | Verification Statement
note | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
date | Date of Inspection:
textbox | Carried out by:
note | Attachments
tickbox | Checklists
tickbox | Photos
tickbox | Dockets
tickbox | Sample Material
tickbox | Drawings
tickbox | Calibration Certificates
tickbox | Test Results / Certificate
tickbox | Inspection reports
tickbox | Others:
textbox | Others
signoff | Signed:
checklist | ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings | itp |  |  |  |  | ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B
section | Hang Ceilings and Stop, Sand Walls & Ceilings
checkpoint | 1 - Address Safety
label | Reference Documents - SWMS
label | Acceptance Criteria - Safety Method Work Sheet approved by Georgiou Group Pty Ltd
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 2 - Insulation to ceilings
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Architect RCP drawings approved by Georgiou Group Pty Ltd. EcoTherm & Ecowool insulation installation guide
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 3 - Sign off for closing ceiling by Georgiou Group Pty Ltd
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Architect RCP drawings approved by Georgiou Group Pty Ltd
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S, R
checkpoint | 4 - Sheets to ceiling
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Architect RCP drawings approved by Georgiou Group Pty Ltd. GTEK Ceiling & Wall Solutions Rev. Mar.2024
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - HP
holdpoint | HOLD POINT
checkpoint | 5 - Stopping to walls & ceilings
label | Reference Documents - Architect drawings
label | Acceptance Criteria - GTEK Ceiling & Wall Solutions Rev. Mar.2024
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 6 - Sanding to walls & ceilings
label | Reference Documents - Architect drawings
label | Acceptance Criteria - GTEK Ceiling & Wall Solutions Rev. Mar.2024
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 7 - Fit access hatch frame
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Architect RCP drawings approved by Georgiou Group Pty Ltd.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 8 - Cut out for lights
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Architect RCP drawings approved by Georgiou Group Pty Ltd.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 9 - Clean up
label | Reference Documents -
label | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor -
label | Inspection By: Georgiou - R
checkpoint | Verification Statement
note | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
date | Date of Inspection:
textbox | Carried out by:
note | Attachments
tickbox | Checklists
tickbox | Photos
tickbox | Dockets
tickbox | Sample Material
tickbox | Drawings
tickbox | Calibration Certificates
tickbox | Test Results / Certificate
tickbox | Inspection reports
tickbox | Others:
textbox | Others
signoff | Signed:
checklist | ITC&ITP No.5 - Patching | itp |  |  |  |  | ITC&ITP No.5 - Patching - Rev B
section | Patching
checkpoint | 1 - Address Safety
label | Reference Documents - SWMS
label | Acceptance Criteria - Safety Method Work Sheet approved by Georgiou Group Pty Ltd
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 2 - Check ceilings
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Architect RCP drawings approved by Georgiou Group Pty Ltd.
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 3 - Check walls
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Architect GA plan & wall type drawings approved by Georgiou Group Pty Ltd.
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 4 - Clean up
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor -
label | Inspection By: Georgiou - R
checkpoint | Verification Statement
note | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
date | Date of Inspection:
textbox | Carried out by:
note | Attachments
tickbox | Checklists
tickbox | Photos
tickbox | Dockets
tickbox | Sample Material
tickbox | Drawings
tickbox | Calibration Certificates
tickbox | Test Results / Certificate
tickbox | Inspection reports
tickbox | Others:
textbox | Others
signoff | Signed:
checklist | ITC&ITP No.6 - Rigid Board | itp |  |  |  |  | ITC&ITP No.6 - Rigid Board - Rev B
section | Rigid Board
checkpoint | 1 - Address Safety
label | Reference Documents - SWMS
label | Acceptance Criteria - Safety Method Work Sheet approved by Georgiou Group Pty Ltd
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 2 - Set out Rigid Board
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Reflected Ceiling Plan approved by Georgiou Group Pty Ltd
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 3 - Install Rigid Board
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Reflected Ceiling Plan approved by Georgiou Group Pty Ltd. Kingspan Kooltherm K10 installation guide 2021
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 4 - Tape & Seal
label | Reference Documents -
label | Acceptance Criteria - Kingspan Kooltherm K10 installation guide 2021
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Georgiou - S
checkpoint | 5 - Clean up
label | Reference Documents -
label | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor -
label | Inspection By: Georgiou - R
checkpoint | Verification Statement
note | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
date | Date of Inspection:
textbox | Carried out by:
note | Attachments
tickbox | Checklists
tickbox | Photos
tickbox | Dockets
tickbox | Sample Material
tickbox | Drawings
tickbox | Calibration Certificates
tickbox | Test Results / Certificate
tickbox | Inspection reports
tickbox | Others:
textbox | Others
signoff | Signed: