## struct
resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
| step |  |  | Tier 1: Level Ground
| step |  |  | Tier 2: Whole Level
ITC&ITP No.1 - Speedpanel & Pre-hang Fire Rated Plasterboard - Rev B | checklist |  |  | Tier 3: ITP.01 Speedpanel & Pre-hang Fire Rated Plasterboard
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
ITC&ITP No.6 - Rigid Board - Rev B | checklist |  |  | Tier 3: ITP.06 Rigid Board
| step |  |  | Tier 1: Level 1
| step |  |  | Tier 2: APT 400
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 401
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 402
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 403
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 404
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 405
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 406
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 407
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 408
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 409
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 410
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 411
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: Corridor
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: Whole Level
ITC&ITP No.1 - Speedpanel & Pre-hang Fire Rated Plasterboard - Rev B | checklist |  |  | Tier 3: ITP.01 Speedpanel & Pre-hang Fire Rated Plasterboard
| step |  |  | Tier 1: Level 2
| step |  |  | Tier 2: APT 412
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 413
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 414
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 415
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 416
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 417
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 418
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 419
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 420
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 421
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 422
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 423
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: Corridor
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: Whole Level
ITC&ITP No.1 - Speedpanel & Pre-hang Fire Rated Plasterboard - Rev B | checklist |  |  | Tier 3: ITP.01 Speedpanel & Pre-hang Fire Rated Plasterboard
| step |  |  | Tier 1: Level 3
| step |  |  | Tier 2: APT 424
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 425
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 426
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 427
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 428
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 429
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 430
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 431
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 432
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 433
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 434
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 425
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: Corridor
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: Whole Level
ITC&ITP No.1 - Speedpanel & Pre-hang Fire Rated Plasterboard - Rev B | checklist |  |  | Tier 3: ITP.01 Speedpanel & Pre-hang Fire Rated Plasterboard
| step |  |  | Tier 1: Level 4
| step |  |  | Tier 2: APT 436
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 437
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 438
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 439
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 440
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 441
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 442
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 443
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 444
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 445
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 446
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 447
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: Corridor
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: Whole Level
ITC&ITP No.1 - Speedpanel & Pre-hang Fire Rated Plasterboard - Rev B | checklist |  |  | Tier 3: ITP.01 Speedpanel & Pre-hang Fire Rated Plasterboard
ITC&ITP No.6 - Rigid Board - Rev B | checklist |  |  | Tier 3: ITP.06 Rigid Board
| step |  |  | Tier 1: Level 5
| step |  |  | Tier 2: APT 448
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 449
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 450
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 451
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 452
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 453
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 454
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 455
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: Corridor
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: Whole Level
ITC&ITP No.1 - Speedpanel & Pre-hang Fire Rated Plasterboard - Rev B | checklist |  |  | Tier 3: ITP.01 Speedpanel & Pre-hang Fire Rated Plasterboard
| step |  |  | Tier 1: Level 6
| step |  |  | Tier 2: APT 456
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 457
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 458
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 459
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 460
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 461
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 462
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: APT 463
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: Corridor
ITC&ITP No.2 - Frame All Walls - Rev C | checklist |  |  | Tier 3: ITP.02 Frame All Walls
ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | checklist |  |  | Tier 3: ITP.03 Sheet All Walls & Frame Ceiling
ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | checklist |  |  | Tier 3: ITP.04 Hang Ceilings and Stop, Sand Walls & Ceilings
ITC&ITP No.5 - Patching - Rev B | checklist |  |  | Tier 3: ITP.05 Patching
| step |  |  | Tier 2: Whole Level
ITC&ITP No.1 - Speedpanel & Pre-hang Fire Rated Plasterboard - Rev B | checklist |  |  | Tier 3: ITP.01 Speedpanel & Pre-hang Fire Rated Plasterboard
ITC&ITP No.6 - Rigid Board - Rev B | checklist |  |  | Tier 3: ITP.06 Rigid Board