## Project Breakdown
CHECKLISTS
Job Name |  | 1087 - Creenslade Crescent, Northcote
Job Details |  |  | prepopulate | Job Details Checklist
Precast Manufacture |  |  | ability to add
| Level 1 |  | Ability to add | Add 1. Standard
|  | 1GS01 | prepopulate | Add 1. Standard
|  | 1GS02 | prepopulate | Add 1. Standard
|  | 1GS03 | prepopulate | Add 1. Standard
|  | 1GS04 | prepopulate | Add 1. Standard
|  | 1GS05 | prepopulate | Add 1. Standard
|  | 1GS06 | prepopulate | Add 1. Standard
|  | 1GS07 | prepopulate | Add 1. Standard
|  | 1GS08 | prepopulate | Add 1. Standard
|  | 1GS09 | prepopulate | Add 1. Standard
|  | 1GS10 | prepopulate | Add 1. Standard
|  | 1GS11 | prepopulate | Add 1. Standard
|  | 1GS12 | prepopulate | Add 1. Standard
|  | 1GS13 | prepopulate | Add 1. Standard
|  | 1GS14 | prepopulate | Add 1. Standard
|  | 1GS15 | prepopulate | Add 1. Standard
|  | 1GS16 | prepopulate | Add 1. Standard
|  | 1GS17 | prepopulate | Add 1. Standard
|  | 1GS18 | prepopulate | Add 1. Standard
|  | 1GS19 | prepopulate | Add 1. Standard
|  | 1GS20 | prepopulate | Add 1. Standard
|  | 1GS21 | prepopulate | Add 1. Standard
|  | 1GS22 | prepopulate | Add 1. Standard
|  | 1GS23 | prepopulate | Add 1. Standard
|  | 1GS24 | prepopulate | Add 1. Standard
|  | 1GS25 | prepopulate | Add 1. Standard
|  | 1GS26 | prepopulate | Add 1. Standard
|  | 1GS27 | prepopulate | Add 1. Standard
|  | 1GS28 | prepopulate | Add 1. Standard
|  | 1GS29 | prepopulate | Add 1. Standard
|  | 1GS30 | prepopulate | Add 1. Standard
|  | 1GS31 | prepopulate | Add 1. Standard
|  | 1GS32 | prepopulate | Add 1. Standard
|  | 1GS33 | prepopulate | Add 1. Standard
|  | 1GS34 | prepopulate | Add 1. Standard
|  | 1GS35 | prepopulate | Add 1. Standard
|  | 1GS36 | prepopulate | Add 1. Standard
|  | 1GS37 | prepopulate | Add 1. Standard
|  | 1GS38 | prepopulate | Add 1. Standard
|  | 1GS39 | prepopulate | Add 1. Standard
|  | 1GS40 | prepopulate | Add 1. Standard
|  | 1GS41 | prepopulate | Add 1. Standard
|  | 1GS42 | prepopulate | Add 1. Standard
|  | 1GS43 | prepopulate | Add 1. Standard
|  | 1GS44 | prepopulate | Add 1. Standard
|  | 1GS45 | prepopulate | Add 1. Standard
|  | 1GS46 | prepopulate | Add 1. Standard
|  | 1GS47 | prepopulate | Add 1. Standard
|  | 1GS48 | prepopulate | Add 1. Standard
|  | 1GS49 | prepopulate | Add 1. Standard
|  | 1GS50 | prepopulate | Add 1. Standard
|  | 1GS51 | prepopulate | Add 1. Standard
|  | 1GS52 | prepopulate | Add 1. Standard
|  | 1GS53 | prepopulate | Add 1. Standard
|  | 1GS54 | prepopulate | Add 1. Standard
|  | 1GS55 | prepopulate | Add 1. Standard
|  | 1GS56 | prepopulate | Add 1. Standard
|  | 1GS57 | prepopulate | Add 1. Standard
|  | 1GS58 | prepopulate | Add 1. Standard
|  | 1GS59 | prepopulate | Add 1. Standard
|  | 1GS60 | prepopulate | Add 1. Standard
|  | 1GS61 | prepopulate | Add 1. Standard

## 1.Standard
type | name | values | prefix
checklist | ""
section | Precast Element Details (Project Manager)
checkpoint | Concrete Details Complete
text | Concrete Volume
text | Concrete Strength
text | Enter Drawing Revision Number
text | Cast Date
text | Admixture Required
section | Reinforcing Yard Checks (Reinforcing Supervisor)
checkpoint | Reinforcing details checked/highlighted off against shop drawing (Bar sizes, grades and spacings)
checkpoint | Cast in Items coordinated and marked on cage (Dross Ducts, Inserts Weld Plates)
checkpoint | Overall cage dimensions in plan checked and there will be sufficent concrete cover to edges
checkpoint | Overall cage thickness checked and there will be sufficient cover to MF and TF
checkpoint | There is sufficient cover to rebates around openings or weatherproofing details
section | Formwork Set Up Checks (QA)
checkpoint | Length/Width/Thickness/Cutouts/Diagonals
checkpoint | Edge Details & Rebates
checkpoint | Inserts on MF (Weld plates, RB's, TIM's, Penetrations, DB Bottoms)
checkpoint | MF roughening's
checkpoint | Sides Straight & Magnets Fastened
checkpoint | Mould Face Clean
section | Prepour Checks (QA)
checkpoint | Mould Cleaned & Oiled
checkpoint | Check covers on all sides, MF and TF, openings
checkpoint | Starters (Size, Grade, Setout and Length)
Checkpoint | Inserts on TF (Weld plates, RB's, TIM's, Penetrations, DB's, Rebates)
checkpoint | Lifters
checkpoint | Tie wire Trimmed
checkpoint | Panel fully clean
checkpoint | General Photos Attached
checkpoint | Concrete Docket Attached
checkpoint | Shop Drawing Checked Off (attach photo)
section | Post Pour (QA)
checkpoint | Confirm formwork has not shifted during placing of concrete
checkpoint | Face lifters placed in correct location
checkpoint | Roughening Lines Correct
section | Demould Inspection (Yard Supervisor)
checkpoint | Mould Face Acceptable?
checkpoint | Trowel Face acceptable?
checkpoint | Item Labelled?
checkpoint | Drossbachs cleaned out and clear?
checkpoint | Top lifters are cleared out and eyes are free of concrete?
checkpoint | Drossbachs drilled ?
checkpoint | Nail plates removed?
checkpoint | Jet washed?
checkpoint | Weld plates are cleaned and free of concrete?
checkpoint | Starter bars bent for transportation?
checkpoint | Structural repair required?
checkpoint | Chamfer Inspection
checkpoint | Silicone Inspection
checkpoint | Honey combing from Vibrating
checkpoint | Final check with drawing
section | Loading Out (Yard Supervisor)
checkpoint | Photo taken of Panel on Truck
checkpoint | No remedial work required on site
section | Painting (Remedial manager)
checkpoint | Primer
checkpoint | Base
checkpoint | Top Coat
section | Test Results, Certificates and Documentation (QA)
checkpoint | Upload reinforcing detail sheets
checkpoint | Upload Photo of Reinforcing Stock Bundle Tags (Cast # Tracking)
checkpoint | Upload Concrete test results
checklist | Site Works Defect #1 (Siteworks Manager)
section | Details
checkpoint-no-value | Site Works Defect #1
date | Date when scoping document was created
checkpoint | What is the Defect (Take photo of defect, highlight area of repair and add description where required on the photo or comment)
checkpoint | Remedial required
tickbox | Grind
tickbox | Sand
tickbox | Fill
tickbox | Drill
tickbox | Plaster
tickbox | Paint
tickbox | colour match
tickbox | Epoxy Reo
dropdown | PHQ, Dayworks,
checkpoint | NCR Raised if Required
checkpoint | Remedial completed (Take photo to evidence)
date | Date remedial completed
signoff | Remedial acceptable and signed off by client
checklist | Site Works Defect #2 (Siteworks Manager)
section | Details
checkpoint-no-value | Site Works Defect #2
date | Date when scoping document was created
checkpoint | What is the Defect (Take photo of defect, highlight area of repair and add description where required on the photo or comment)
checkpoint | Remedial required
tickbox | Grind
tickbox | Sand
tickbox | Fill
tickbox | Drill
tickbox | Plaster
tickbox | Paint
tickbox | colour match
tickbox | Epoxy Reo
dropdown | PHQ, Dayworks,
checkpoint | NCR Raised if Required
checkpoint | Remedial completed (Take photo to evidence)
date | Date remedial completed
signoff | Remedial acceptable and signed off by client
checklist | Site Works Defect #3 (Siteworks Manager)
section | Details
checkpoint-no-value | Site Works Defect #3
date | Date when scoping document was created
checkpoint | What is the Defect (Take photo of defect, highlight area of repair and add description where required on the photo or comment)
checkpoint | Remedial required
tickbox | Grind
tickbox | Sand
tickbox | Fill
tickbox | Drill
tickbox | Plaster
tickbox | Paint
tickbox | colour match
tickbox | Epoxy Reo
dropdown | PHQ, Dayworks,
checkpoint | NCR Raised if Required
checkpoint | Remedial completed (Take photo to evidence)
date | Date remedial completed
signoff | Remedial acceptable and signed off by client
checklist | Site Works Defect #4 (Siteworks Manager)
section | Details
checkpoint-no-value | Site Works Defect #4
date | Date when scoping document was created
checkpoint | What is the Defect (Take photo of defect, highlight area of repair and add description where required on the photo or comment)
checkpoint | Remedial required
tickbox | Grind
tickbox | Sand
tickbox | Fill
tickbox | Drill
tickbox | Plaster
tickbox | Paint
tickbox | colour match
tickbox | Epoxy Reo
dropdown | PHQ, Dayworks,
checkpoint | NCR Raised if Required
checkpoint | Remedial completed (Take photo to evidence)
date | Date remedial completed
signoff | Remedial acceptable and signed off by client
checklist | Site Works Defect #5 (Siteworks Manager)
section | Details
checkpoint-no-value | Site Works Defect #5
date | Date when scoping document was created
checkpoint | What is the Defect (Take photo of defect, highlight area of repair and add description where required on the photo or comment)
checkpoint | Remedial required
tickbox | Grind
tickbox | Sand
tickbox | Fill
tickbox | Drill
tickbox | Plaster
tickbox | Paint
tickbox | colour match
tickbox | Epoxy Reo
dropdown | PHQ, Dayworks,
checkpoint | NCR Raised if Required
checkpoint | Remedial completed (Take photo to evidence)
date | Date remedial completed
signoff | Remedial acceptable and signed off by client