## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | 1. Standard |  | 1.Standard |  | d2b2529c-9aa7-4b6a-927f-7fea06d84ba1
| section | Precast Element Details (Project Manager)
| checkpoint | Concrete Details Complete
48b4964b-4f5e-5a73-8202-8376847b9b0a | textbox | Concrete Volume
dd5cca62-e351-59f6-9513-d2041b663d88 | textbox | Concrete Strength
282f747d-a59e-5507-a595-4cc49537cf92 | textbox | Enter Drawing Revision Number
1126ee27-7e41-5708-a871-f4a717b28a72 | textbox | Cast Date
3525fb4a-ef83-5945-bae7-4b0d0272c87d | textbox | Admixture Required
| section | Reinforcing Yard Checks (Reinforcing Supervisor)
| checkpoint | Reinforcing details checked/highlighted off against shop drawing (Bar sizes, grades and spacings)
| checkpoint | Cast in Items coordinated and marked on cage (Dross Ducts, Inserts Weld Plates)
| checkpoint | Overall cage dimensions in plan checked and there will be sufficent concrete cover to edges
| checkpoint | Overall cage thickness checked and there will be sufficient cover to MF and TF
| checkpoint | There is sufficient cover to rebates around openings or weatherproofing details
| section | Formwork Set Up Checks (QA)
| checkpoint | Length/Width/Thickness/Cutouts/Diagonals
| checkpoint | Edge Details & Rebates
| checkpoint | Inserts on MF (Weld plates, RB's, TIM's, Penetrations, DB Bottoms)
| checkpoint | MF roughening's
| checkpoint | Sides Straight & Magnets Fastened
| checkpoint | Mould Face Clean
| section | Prepour Checks (QA)
| checkpoint | Mould Cleaned & Oiled
| checkpoint | Check covers on all sides, MF and TF, openings
| checkpoint | Starters (Size, Grade, Setout and Length)
| checkpoint | Inserts on TF (Weld plates, RB's, TIM's, Penetrations, DB's, Rebates)
| checkpoint | Lifters
| checkpoint | Tie wire Trimmed
| checkpoint | Panel fully clean
| checkpoint | General Photos Attached
| checkpoint | Concrete Docket Attached
| checkpoint | Shop Drawing Checked Off (attach photo)
| section | Post Pour (QA)
| checkpoint | Confirm formwork has not shifted during placing of concrete
| checkpoint | Face lifters placed in correct location
| checkpoint | Roughening Lines Correct
| section | Demould Inspection (Yard Supervisor)
| checkpoint | Mould Face Acceptable?
| checkpoint | Trowel Face acceptable?
| checkpoint | Item Labelled?
| checkpoint | Drossbachs cleaned out and clear?
| checkpoint | Top lifters are cleared out and eyes are free of concrete?
| checkpoint | Drossbachs drilled ?
| checkpoint | Nail plates removed?
| checkpoint | Jet washed?
| checkpoint | Weld plates are cleaned and free of concrete?
| checkpoint | Starter bars bent for transportation?
| checkpoint | Structural repair required?
| checkpoint | Chamfer Inspection
| checkpoint | Silicone Inspection
| checkpoint | Honey combing from Vibrating
| checkpoint | Final check with drawing
| section | Loading Out (Yard Supervisor)
| checkpoint | Photo taken of Panel on Truck
| checkpoint | No remedial work required on site
| section | Painting (Remedial manager)
| checkpoint | Primer
| checkpoint | Base
| checkpoint | Top Coat
| section | Test Results, Certificates and Documentation (QA)
| checkpoint | Upload reinforcing detail sheets
| checkpoint | Upload Photo of Reinforcing Stock Bundle Tags (Cast # Tracking)
| checkpoint | Upload Concrete test results