## MC Floor Handover
16123 - DOMINION RD. HOUSING DEV'T QA - Check Sheet
Check list: | OPENING READINESS
Main Contractor Handover | Status | Note
QA check sheet/marked up plan or elev. drawing received from Main Contractor for the whole floor. | Pass / Fail
Grid-lines (minimum 3-lines per work face) clearly marked on floor by maincon. | Pass / Fail
RLs to be provided at two (2) locations on each level. | Pass / Fail
Structural opening within tolerance (as per standard) | Pass / Fail
Gap for sealant joints within tolerance as shown in shop dwgs. | Pass / Fail
All substrates compatible with Sika AT Façade sealant. | Pass / Fail | IF NOT - Separation tape must be applied by Maincon
Concrete rebates made as per approved dwg. | Pass / Fail / NA
Waterproofing / membrane applied as per approved dwg. | Pass / Fail / NA
All timber framing completed & weather-proofed | Pass / Fail / NA
Flashing tapes applied as per approved dwg. | Pass / Fail / NA
Sill flashing installed (by other trades) | Pass / Fail / NA
Wall face aligned at head-sill-jambs as per approved drawing setout. | Pass / Fail
Work face is clean, accessible and free from any obstructions. | Pass / Fail
Has Allwin team checked and accepted | Pass / Fail

## Hinge Door
16123 - DOMINION RD. HOUSING DEV'T QA - Check Sheet
Check list: | Hinged Door / Fix Panel
Pre-Installation QA Check | Inspection Status | Note
Handover QA check sheet received from maincon | Yes / No
Agreed structural opening within tolerance as per dwg. "IF NOT" - How wide is the sealant joint around? | Yes / No
Substrate waterproofing membrane/flashing tape applied completely & compatible with Sika AT Façade sealant. | Pass / Fail | Record of Peel Adhesion Test Required
Concrete rebate as per dwg & waterproofing applied | Pass / Fail
Alum. frame and panel received in good condition with protection tape applied. | Pass / Fail
Timber liners complete & securely fixed. | Pass / Fail
Sufficient drain holes & caps applied. | Pass / Fail
Ironmongery/Trickle vent/gaskets/mohair complete and secured in place. Replace "IF ANY" gasket or mohair ran short. | Pass / Fail
Installation QA Check | Inspection Status | Note
Wanz support bar installed as per dwg. | Pass / Fail
Door frame installed (plumb/level) | Pass / Fail
Mechanical fixings complete as per schedule | Pass / Fail
HD packers appllied at fixing points | Pass / Fail
Screws over-sealed as per detail | Pass / Fail
Sealant neatly applied at external/internal as per detail & ratio | Pass / Fail
Door panel aligned, leveled & plumbed. | Pass / Fail
Door hardware installed and working e.g. handle / lock | Pass / Fail
Door opening & closing smoothly not touching the floor or threshold. | Pass / Fail
Door closer installed and functioning | Pass / Fail
Glazing beads & rubbers installed properly. | Pass / Fail
Glass free from any defect/scratch. | Pass / Fail
Removal of protection tape & trade clean done. | Pass / Fail
Final QA checks completed & no defects found. | Pass / Fail
Window handed over by Allwin to Main Contractor. | Accepted / Rejected / Commented

## Sliding Door
16123 - DOMINION RD. HOUSING DEV'T QA - Check Sheet
Check list: | Sliding Door / Awning Window
Pre-Installation QA Check | Inspection Status | Note
Handover QA check sheet received from maincon | Yes / No
Agreed structural opening within tolerance as per dwg. "IF NOT" - How wide is the sealant joint around? | Yes / No
Substrate waterproofing membrane/flashing tape applied completely & compatible with Sika AT Façade sealant. | Pass / Fail | Record of Peel Adhesion Test Required
Concrete rebate as per dwg & waterproofing applied | Pass / Fail
Alum. frame and panel received in good condition with protection tape applied. | Pass / Fail
Timber liners complete & securely fixed. | Pass / Fail
Sufficient drain holes & caps applied. | Pass / Fail
Glazing beads & rubbers installed properly. | Pass / Fail
Glass free from any defect/scratch. | Pass / Fail
Ironmongery/Trickle vent/gaskets/mohair complete and secured in place. Replace "IF ANY" gasket or mohair ran short. | Pass / Fail
Installation QA Check | Inspection Status | Note
Slider frame/track installed (align/level) | Pass / Fail
Mechanical fixings complete as per schedule | Pass / Fail
HD packers appllied at fixing points | Pass / Fail
All the screws over-sealed as per detail | Pass / Fail
Sealant neatly applied at external/internal as per detail & ratio | Pass / Fail
Door panel installed as per drawing | Pass / Fail
Sliding panel aligned, leveled, run smoothly. | Pass / Fail
Pull handle installed/open/close properly | Pass / Fail
Awning sashes installed as per drawing | Pass / Fail
Sash aligned with the frame | Pass / Fail
Sash operating (open/close) & locking properly. | Pass / Fail
Restrictor stays installed to 100mm max. opening | Pass / Fail
Wedge rubber / hole caps / been installed to the frame | Pass / Fail
Door stop installed ar per detail | Pass / Fail
Interlocker end cap installed | Pass / Fail
Omega head flashing installed as per drawing | Pass / Fail
Removal of protection tape & trade clean done. | Pass / Fail
Final QA checks completed & no defects found. | Pass / Fail
Window handed over by Allwin to Main Contractor. | Accepted / Rejected / Commented

## Parapet Cladding (hidden)
RISLAND APARTMENT - MUNROE LANE QA - Check Sheet
Check list: | Parapet Cladding
Main Contractor (CMP) Handover | Inspection Status | Note
QA check sheet received from CMP for the whole floor level | Pass / Fail
Pre-Installation QA Check | Inspection Status | Note
Has the structure been completed by Main Contractor | Pass / Fail
Has the timber been installed and wrapped with waterproof | Pass / Fail
Parapet cladding received in good condition | Pass / Fail
Installation QA Check | Inspection Status | Note
Has the roof panels installed line leveled | Pass / Fail
Has the omega channel been installed | Pass / Fail
Parapet cladding installed and leveled | Pass / Fail
Has the silicon been applied completely | Pass / Fail
Has the Wall Parapet Cladding been check by CMP accepted preliminary handover | Yes / No

## Awning wdw
16123 - DOMINION RD. HOUSING DEV'T QA - Check Sheet
Check list: | Awning Window / Fix Panel
Pre-Installation QA Check | Inspection Status | Note
Handover QA check sheet received from maincon | Yes / No
Agreed structural opening within tolerance as per dwg. "IF NOT" - How wide is the sealant joint around? | Yes / No
Substrate waterproofing membrane/flashing tape applied completely & compatible with Sika AT Façade sealant. | Pass / Fail | Record of Peel Adhesion Test Required
Sub-sill flashing installed (by other trades) | Pass / Fail
Alum. frame and sash received in good condition with protection tape applied. | Pass / Fail
Timber liners complete & securely fixed. | Pass / Fail
Sufficient drain holes & hood applied. | Pass / Fail
Condensation holes & cover applied | Pass / Fail
Condensation tray installed at locations. | Pass / Fail
Corner soakers applied & sealed | Pass / Fail
Mitre joints applied with Galva-seal | Pass / Fail
Ironmongery/Trickle vent/Gaskets installed properly. | Pass / Fail
Installation QA Check | Inspection Status | Note
Window frame installed plumb, level and square. | Pass / Fail
HD packers/shims are not expose with allowance for silicon as per detail. | Pass / Fail
All the screws over-sealed as per detail | Pass / Fail
Sealant neatly applied at external/internal as per detail & ratio | Pass / Fail
Omega head flashing installed as per drawing | Pass / Fail
Sash operating (open/close) & locking properly. | Pass / Fail
Restrictor stays installed to 100mm max. opening | Pass / Fail
Glazing beads & rubbers installed properly. | Pass / Fail
Glass free from any defect/scratch. | Pass / Fail
Removal of protection tape & trade clean done. | Pass / Fail
Final QA checks completed & no defects found. | Pass / Fail
Window handed over by Allwin to Main Contractor. | Accepted / Rejected / Commented

## Full Ht. PW
16123 - DOMINION RD. HOUSING DEV'T QA - Check Sheet
Check list: | Full Ht. Window / Hinge Door / Awning
Pre-Installation QA Check | Inspection Status | Note
Agreed structural opening within tolerance as per dwg. "IF NOT" - How wide is the silicon joint around? | Yes / No
Substrate waterproofing membrane/flashing tape applied completely & compatible with Sika AT Façade sealant. | Pass / Fail | Record of Peel Adhesion Test Required
Wind beam installed at correct level. | Pass / Fail
Alum. Frames/sashes received in good condition with protection tape applied. | Pass / Fail
Sufficient drain holes & caps applied. | Pass / Fail
Ironmongery/Gaskets installed properly. | Pass / Fail
Installation QA Check | Inspection Status | Note
Wanz support bar installed as per dwg. | Pass / Fail
Window frame installed plumb, level and square. | Pass / Fail
HD packers/shims are not expose with allowance for silicon as per detail. | Pass / Fail
All the screws over-sealed as per detail | Pass / Fail
Sealant neatly applied at external/internal as per detail. | Pass / Fail
Omega head flashing installed. | Pass / Fail
Door panel aligned, leveled & plumbed. | Pass / Fail
Door hardware installed and working e.g. handle/lock | Pass / Fail
Door opening & closing smoothly without scratching the floor or sill. | Pass / Fail
Door closer installed and functioning | Pass / Fail
Glazing beads & rubbers installed properly. | Pass / Fail
Glass free from any defect/scratch. | Pass / Fail
Awning sashes installed as per drawing | Pass / Fail
Window sash open/close properly | Pass / Fail
Restrictor stays installed to 100mm max. opening | Pass / Fail
Timber liners complete & securely fixed. | Pass / Fail
Removal of protection tape & trade clean done. | Pass / Fail
Final QA checks completed & no defects found. | Pass / Fail
Window handed over by Allwin to Main Contractor. | Accepted / Rejected / Commented

## Punch window
16123 - DOMINION RD. HOUSING DEV'T QA - Check Sheet
Check list: | Fixed Window
Pre-Installation QA Check | Inspection Status | Note
Agreed structural opening within tolerance as per dwg. "IF NOT" - How wide is the silicon joint around? | Yes / No
Substrate waterproofing membrane/flashing tape applied completely & compatible with Sika AT Façade sealant. | Pass / Fail | Record of Peel Adhesion Test Required
Sub-sill flashing installed (by other trades) | Pass / Fail
Alum. frame received in good condition with protection tape applied. | Pass / Fail
Timber liners complete & securely fixed. | Pass / Fail
Sufficient drain holes & hood applied. | Pass / Fail
Condensation holes & cover applied | Pass / Fail
Condensation tray installed at locations. | Pass / Fail
Corner soakers applied & sealed | Pass / Fail
Mitre joints applied with Galva-seal | Pass / Fail
Ironmongery/Trickle vent/Gaskets installed properly. | Pass / Fail
Installation QA Check | Inspection Status | Note
Window frame installed plumb, level and square. | Pass / Fail
HD packers/shims are not expose with allowance for silicon as per detail. | Pass / Fail
All the screws over-sealed as per detail | Pass / Fail
Sealant neatly applied at external/internal as per detail. | Pass / Fail
Omega head flashing installed. | Pass / Fail
Glazing beads & rubbers installed properly. | Pass / Fail
Glass free from any defect/scratch. | Pass / Fail
Removal of protection tape & trade clean done. | Pass / Fail
Final QA checks completed & no defects found. | Pass / Fail
Window handed over by Allwin to Main Contractor. | Accepted / Rejected / Commented