## Master List Templates
Id | Type | Name | Values | Prompting Name
76db49ac-5e1a-5455-bb7d-2c1ca1d03789 | checklist | FEL SM Weekly Site Checklist |  | FEL SM Weekly Site Checklist
faabc0c7-4eac-56dd-8e45-119398605c17 | section | Monday
d9ef3b66-289c-5ec5-814d-b31c5ce6231c | checkpoint | Prestart Meeting with Team
e7e04e0b-02db-5df0-afe8-ff472e1c0ae2 | checkpoint | Health Check
8e933b49-533f-5572-b799-08d5163b49df | checkpoint | Review Tasks for the week
42ba3e30-c064-5624-b8bc-63fefc94cbec | checkpoint | Identify Targets Including Hours
323689f6-118c-579f-b9e0-6eda3785e211 | checkpoint | Approve hours by 9AM for previous week
cd4cce66-0077-5123-9fef-76ff22ac0e01 | checkpoint | Sign off Subcontractor Hours & Submit
09a758bd-9043-5018-87c7-4ac5cadb970a | checkpoint | Review SWMS
b01a3a27-5b0d-5e56-a009-3994429cc5b1 | checkpoint | Site Toolbox Meeting
975fac91-2feb-512d-bb58-490030503f08 | checkpoint | SSSP in Order
20d15687-fda7-5302-b5fb-1b81a3a0855a | section | Tuesday
9b9713c8-02b8-5378-a1fb-25e090430988 | checkpoint | Follow up outstanding RFI's with PM
533d49a3-8d0a-52bc-b21f-e2d043c050e2 | section | Wednesday
0d2d3979-996d-50de-95a3-ba07b7fc8de7 | checkpoint | Review Roadblocks & Follow Up if still unresolved
0dda5344-fcc2-546a-9144-96a5d2cbf641 | checkpoint | QAs up to date
80324655-0b8b-5c16-8f7a-13b640706321 | section | Thursday
60951f9d-3a26-5722-8980-9c75b07c5c60 | checkpoint | Weekly planner filled out for week ahead
efaf0d3d-ea0d-555f-ba82-25cabab32beb | checkpoint | Roadblocks identified and actioned
a3bdf6dd-7b40-5f57-8dc5-96b0e2e55c86 | checkpoint | Materials organized for week ahead
a6b98e16-fe02-51fb-a0f7-e785906bf6f8 | checkpoint | Plans printed with any relevant notes added
9943046c-8a97-537b-aa69-7e5a4f7f4a1d | section | Friday
a6138ac9-c922-53cb-840d-603ea545867e | checkpoint | Submit Toolbox minutes to main contractor and FEL office
312656a7-0089-53cb-a229-52f3dfdcdac3 | checkpoint | Job Cards up to date and submitted
0f27cdb7-a1a3-536b-8484-54979c908d9e | checkpoint | Team tasks for week ahead filled out on whiteboard
b5ef7da7-c7bd-5981-bfed-f8fb8c0ffe4c | checklist | QA - Cable Tray |  | Cable Tray
9d0908a8-1e88-5428-b64b-c0f535bda802 | checkpoint | Unistrutt Filed & Painted
73610f6a-4f96-506f-b0f4-8078df01ca55 | checkpoint | Hangers Spaced as Specified
5996a500-1faf-5f4c-a1c6-f91369c113a9 | checkpoint | Correct Size Tray Installed
8e0edf51-d460-52ec-9171-92a3b4bd02f1 | checkpoint | Tray Joined Correctly
735a95ff-7b3f-53ea-8576-6f4e454f7324 | checkpoint | Hangers Seismically Restrained as per Design
6928fd03-644b-5126-942f-c590868189d8 | checkpoint | Tray Fastened to Hangers
c7cf2e61-2cca-5585-9ec1-4bbbc6259e1f | checkpoint | Correct Anchors used fixing to Ceiling
6a409734-163a-56a2-9db8-28ce09bf27f5 | checkpoint | Cable Tray Bonded
2b861131-7b9e-51e9-95bf-a57d2d62e13a | checkpoint | Photos
3200509c-b399-523c-b7c2-d64202225ec1 | checklist | QA - Catenary Wires |  | Catenary Wires
64cda29b-1ed4-5b92-8d0a-7bf6a8851896 | checkpoint | 300mm Separation Between Power & Data
d28ab349-7df2-5664-b01c-6cbda1f3b24e | checkpoint | Supported every 6 Meters or Adequately to avoid Sagging
ae7ce183-36b3-5b28-a14d-71bf3c4de41f | checkpoint | Correctly Secured at Each End
7ec8579a-1f8d-5d20-a6d5-ae881967deab | checkpoint | Turn Buckle Installed and Accessible
2b861131-7b9e-51e9-95bf-a57d2d62e13a | checkpoint | Photos
d3aa0606-ef8b-514b-bb01-310729270b72 | checklist | QA - Completion |  | QA - Completion
70c4ef94-351b-550a-a811-35238312a4e4 | checkpoint | All Areas Defected by SM & Feisst Team prior to PC
096d08c3-e2f5-5e2a-af8c-cc9833eafafe | checkpoint | All DBs Tested, results uploaded to Drive on iPad and sent to Project Admin
1539d7f8-e2ba-56d9-8cfc-8ef0886d198d | checkpoint | PS3 Completed & Signed for Emergency Lighting
748b8113-7fa3-52d2-b136-1ae31a033aef | checkpoint | PS3 Completed & Signed for Seismic Bracing of Electrical Fixtures
5e9c87ff-8fa5-511a-969f-d460ae556ce6 | checkpoint | All COCs completed and Submitted to Julia
072a123e-f7c6-5815-baff-19d2c50ebb2f | checkpoint | "Clean" As Built Set of Drawings Completed and Submitted to Julia
8dc96404-2272-5d7b-80ac-7263d01634af | checkpoint | All excess material removed from site and returned to wholesalers
f06374e0-4249-5f21-81f0-e77c89fc0b16 | checkpoint | All assets accounted for and removed from site
6890dfce-bbc0-59ef-9445-80d742cf0c98 | checklist | QA - First Fix |  | QA - First Fix
74cc4423-86c8-5778-99c1-2c5a4be5fbaa | section | Flush Boxes
52546dd7-225b-5be6-85f7-d75e5d59b0e7 | checkpoint | Fire Rated or Acoustic
ad283cb8-49d1-5c6b-b467-e0da63393b86 | checkpoint | Height as per plan
ed944af7-9ea5-58e9-822f-1533976dad8e | checkpoint | Location as per plan
83602173-c4f8-5812-9cab-55fd97112080 | checkpoint | Intumescent Pad In Place
3646e0a8-f58f-5bd3-abc6-b21eaace4d83 | checkpoint | Flush Boxes Not back to back on Acoustic Walls
a1596c2a-5d45-5fea-8352-c94c52f08b6b | section | Cabling
8111ace1-1386-5c1f-8290-3df28e3c8d3f | checkpoint-no-value | Details
eb4f8ba9-a4a5-5b28-8713-d53348fd297e | textbox | Type
7b274a21-45c3-5097-9f9a-9ff8d64358f5 | textbox | Size
22f1b90e-4d4f-5dbb-ba65-12d806ae629b | checkpoint | Circuits clearly labelled
cd85af68-21a8-5f01-a7d6-3723a9b67d9b | checkpoint | No Horizontal cabling
b42d7e0f-fcc7-54e1-a3e6-fe8e5468074f | checkpoint | Separation between Data and Power at 300mm or as specified
9cbcf738-eff9-550b-a074-4eb38a6d246a | checkpoint | Light Control cabling Required
4ce425f3-2a24-595d-a708-54d59af12362 | section | Cat Wires
64cda29b-1ed4-5b92-8d0a-7bf6a8851896 | checkpoint | 300mm Separation Between Power & Data
d28ab349-7df2-5664-b01c-6cbda1f3b24e | checkpoint | Supported every 6 Meters or Adequately to avoid Sagging
ae7ce183-36b3-5b28-a14d-71bf3c4de41f | checkpoint | Correctly Secured at Each End
7ec8579a-1f8d-5d20-a6d5-ae881967deab | checkpoint | Turn Buckle Installed and Accessible
36df8d94-2c85-5183-b9e0-9d30853edee2 | checkpoint | Number of cables per cat wire. 8 maximum or as per electrical spec
477710ac-b787-5d38-ab51-6ceabb415341 | checkpoint | Separation between services maintained
e0c8cf84-13c0-5506-89b6-d6af251287d2 | checkpoint | All cables secured via cable ties with ends cut
0d1abcf6-77f5-5780-b1b2-1abfc5315199 | section | Cable Tray
f2e95e7b-f52a-532b-bb9b-44b519704b90 | checkpoint | Minimum 25% spare capacity left on cable tray
aea99ad1-df5b-5a82-a33f-f1f325cc89fa | section | Lights
4dbc0e5c-8c1c-5096-9bb5-e94136fa1ee2 | checkpoint | Setout Correct
0444dc2b-09fe-56ba-8179-479d1ee41c3b | checkpoint | Cabling in correct location
c5b1d0c8-e679-5493-b11c-2233dd1f6d1d | checkpoint | Control Cabling installed
86776a76-4f23-5726-948f-d2424efd88bf | checkpoint | PIR Sensors
61b30a0f-48a9-52a7-9f6b-f19ec402cc6b | checkpoint | Occupancy Sensors
ad99da00-e908-52e9-a822-5afe19aaa647 | checkpoint | Light Level Sensors
ef0c1437-4a66-55e2-986b-5bbf90072fd8 | checkpoint | Emergency/ Exit Lighting
a5765791-ceea-5e14-907a-17b6be2d048e | checkpoint | Nogging installed for Electrical Services
fd247d33-fae7-567e-8354-5cc82760690e | section | Seismic Bracing
c4f3a10b-01e9-5914-a9af-be632719c000 | checkpoint | For Lighting
06527449-0976-44ed-9348-24f8b6c29d2a | checkpoint | Cable Tray
7c255091-ff19-5694-8a1d-f231ebcf05b9 | checkpoint | Switchboard
deda8c9f-3533-5b29-977c-92bb6a449d03 | section | Ducts and Conduits
5568af26-98ae-541d-b469-da4d352199d3 | checkpoint | Correct size installed
6a178efc-5cb3-4c13-8e36-8f17521e9d45 | checkpoint | Location as per plan
78ea28d9-3eaf-58df-afb6-ccc274394479 | checkpoint | separation from other services
eefd18e7-65bc-5b74-81bb-29901edb235c | checkpoint | Clean inside and in good condition
2b861131-7b9e-51e9-95bf-a57d2d62e13a | checkpoint | Photos
8af74cce-7665-5c60-b27d-540eb3efc834 | checklist | QA - Inground Services |  | Inground Services
deda8c9f-3533-5b29-977c-92bb6a449d03 | section | Ducts and Conduits
5568af26-98ae-541d-b469-da4d352199d3 | checkpoint | Correct size installed
022a724f-d05a-56ad-b1b5-fdc16b00e1dd | checkpoint | Start and finish locations correct as per plan
78ea28d9-3eaf-58df-afb6-ccc274394479 | checkpoint | separation from other services
eefd18e7-65bc-5b74-81bb-29901edb235c | checkpoint | Clean inside and in good condition
42bed097-8269-5887-ad2d-a9f1a3bfb31e | section | Electrical Pits
de4f9100-b144-506e-85c4-cd341134813d | checkpoint | Set out correct
37c143f7-c3c3-45df-8625-06875c9ac9d7 | checkpoint | Correct size installed
db07a1c8-f1b9-52b6-b82d-eaac409e0dfb | checkpoint | Duct entry holes sealed / water proofed
3433c7dd-551d-5436-bb31-a535c449f671 | checkpoint | Pits installed to correct height and level
9c7abd4a-a90b-4f68-8485-05fb13fa5a05 | checkpoint | Clean inside and in good condition
5a64a111-e54b-5dfd-8e6f-d1a1e5b79060 | section | Light Pole Foundations
36a4444b-535c-4778-ac99-a778e56574ae | checkpoint | Set out correct
6676597f-496d-54df-8b60-2e2d77c3c14d | checkpoint | Ducting in correct position - centre of cage
195bbc6c-5bd7-502b-bad2-9b0ca6b0efb2 | checkpoint | Correct Cage Installed
def23b42-2281-57da-8da5-912fa614d1fb | checkpoint | Cage installed to correct height / level
634c21b9-2b04-53ae-b15d-b2b9d504f50d | checkpoint | Ground Plant pole installed to correct height / level
2b861131-7b9e-51e9-95bf-a57d2d62e13a | section | Photos
dba5361d-cea2-47e2-9b9b-441a03c4b5eb | checkpoint-no-value | Photos
1d65dc1e-799b-5aeb-a9d5-f473b9cb6d70 | checklist | QA - Second fix |  | QA - Second fix
bfe4e06e-4e40-5a8d-85e8-e8e8254488f2 | section | Power Outlets
e95a9eb2-e5eb-58ff-8f85-17dd59c068e2 | checkpoint | Weekly Toolbox
3298937e-20b0-52b8-8b4e-434f7b4be4e6 | checkpoint | Correctly installed with terminations all secured properly
6a8158a2-5b34-537a-b528-d09802c47170 | checkpoint | Outlet Installed level
83602173-c4f8-5812-9cab-55fd97112080 | checkpoint | Intumescent Pad In Place
0c328804-43d9-5c18-80a8-408b2e468b81 | checkpoint | Circuit Tested and results recorded
131c116d-e873-596d-a61c-7e2193dfd453 | checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
49360234-28cf-5b0a-807d-5276cdbc0d57 | section | Light Switches
4b138861-6eeb-5cd4-9bdb-c87d4a6cb7d3 | checkpoint | Correct type installed
9b3da9b8-ef80-4ec6-87da-acc2f885306b | checkpoint | Correctly installed with terminations all secured properly
82420f52-05e4-4b05-aa05-32b92bd759ea | checkpoint | Outlet Installed level
f8171c67-50f4-4f78-87d9-d70c2f6ee41f | checkpoint | Intumescent Pad In Place
7aec7cbd-3fbd-4156-9ce2-0e140022815c | checkpoint | Circuit Tested and results recorded
9952c68c-2177-4295-9c02-d3416a701b68 | checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
7a400d23-e5f0-5542-9699-7c5109fab00a | section | Light Fixtures
8db25628-a808-4f1f-8b40-70670db79dc0 | checkpoint | Correct type installed
01f49a00-0a90-448b-9d96-c805fc6e46b3 | checkpoint | Correctly installed with terminations all secured properly
337c6eb0-9078-5c56-b36e-2b7537aa048a | checkpoint | Seismic braces installed.
29da3a61-2d18-50bf-be8d-e857a855410b | checkpoint | Insulation removed from over downlights and drivers
791184d6-bd15-5aea-9453-f7d6c7d5679c | checkpoint | Tested for operation
2b861131-7b9e-51e9-95bf-a57d2d62e13a | checkpoint | Photos
3fc35bdb-b201-50aa-9daa-6b2132e363f3 | checklist | Switchboard |  | Switchboard
5bb2f6d6-c31d-52dd-a3a1-dc24f1ba78af | checkpoint | Spatial certificate signed if required
6535d7df-da02-5fa7-a5b2-a99c7ba1b1c0 | checkpoint | Fixings installed in wall correctly if board is wall mounted
c37ef787-f8f3-54a2-bdab-39a8a931f4c0 | checkpoint | All clearances sighted to ensure location is compliant
a4b89ca4-91fc-5fb1-b350-9e1c104cdfa6 | checkpoint | All cables correctly installed in protection device and earth and neutral bars and fully secured
ed0e0ff7-9fe7-59b5-a98f-3f511c88f2f6 | checkpoint | Cables neatly dressed
982c962c-002f-5fda-ba0d-d1c8db378bbe | checkpoint | Phase tabs on chassy covered
4f6f60f9-c7ad-573b-bb2d-9a2239e38951 | checkpoint | All earths and neutrals labelled to match phase numbers
aeb9155d-136e-5e62-b406-b4d144555671 | checkpoint | Switchboard is clean on the inside and outside
5ea902af-d91b-51e9-bf79-ae06752e856a | checkpoint | Masking blanks installed
6d51a3ea-7313-5767-83b1-d1896d519583 | checkpoint | DB legend installed
c1f61027-892d-5ab2-aad1-8ce298c57a67 | checkpoint | Feisst label on the door installed
2b861131-7b9e-51e9-95bf-a57d2d62e13a | checkpoint | Photos