## Master List Templates
Id | Type | Name | Values | Prompting Name
b50b4219-6b87-4d5a-89ca-e197c43e791e | checklist | Precast Concrete Pour Checklist |  | Precast Concrete Pour Checklist
f4cc8da1-2dec-44d0-8029-334237dd1055 | section | Details
5d9695df-c193-4701-a8f5-4c2f629684e7 | checkpoint | Details
bddd4fcf-5277-4fb9-b2b9-0269dd63f0bd | checkpoint | Attached detail sheet latest revision
28ccba30-459a-4a3a-a2e7-b994277c430d | checkpoint | Photo taken of hard-copy title block to confirm revision
7c861cac-2648-43c4-a75f-9b8a810d503e | checkpoint | Details filled out below
8c1f0f61-f487-5ee4-b400-01324d4b5f33 | textbox | Table Number
| button | Is this a Pre-stressed concrete panel? | YES, NO
af298c2c-5fef-5b2f-ae7d-cf7033f70e37 | button | Engineer's prepour inspection required | YES, NO, N/A
2c3a0641-9ad7-511a-bc7f-189ec2765d3e | textbox | Team on table
15d6c6a4-07d2-41a1-85cd-62d87aee6a11 | section | Pre-Pour
2b9a2b4f-de6c-4430-8725-ba4939724841 | checkpoint | Make sure table face and angles are clean.
b26feff5-d5e7-408d-813d-03cf1521dfd7 | checkpoint | Mark out 3, 4, 5 triangle to one side and check
a46888cf-dc94-4872-9d7b-1469e67f4ccc | checkpoint | Mark out and check dimensions of panel and diagonals
bf44178e-e5e7-4747-9aef-85329d11e05c | checkpoint | Place side and blockouts
| checkpoint | (pre-stress panels only) Strand location checked?
de3b0fc8-79b0-4b24-ae90-828e9ec11dd2 | checkpoint | Check all side are straight, block & line/straightedge along line of side
c7e27b7e-3a1d-4ca7-9bd9-12e1cf9c596a | checkpoint | Check any table surface finish required
300ee19a-3f20-452e-a2ee-7d6ce341121a | checkpoint | Clean table thoroughly
208d6b08-1fd5-4cc7-965d-b293066182fe | checkpoint | Apply silicone and form release
b04747e4-b43d-424f-b8bd-b9e4a7be9854 | signoff | Manager Checked and signed
1da7fb4c-4839-4f42-93f3-3e78763a202e | checkpoint | Check reo cage is correct and as specified
| checkpoint | (pre-stress panels only) Check if strand size and quantity are as per detail drawing?
| checkpoint | (pre-stress panels only) Run strand from the stressing head to the fixed head
| checkpoint | (pre-stress panels only)Terminate strand 350mm past stressing head and 150mm past the fixed head
| signoff | (pre-stress panels only) Fully trained employee for stressing methodology to sign here before proceding
0e5f952d-b7a0-4e95-a1b9-f1a92a846502 | checkpoint | Check all cast-in items, size, quantity, location and secured correctly
1d0bc3c2-b9d1-4bba-81c9-5b459a5333cc | checkpoint | Check concrete cover to cast in items and reo
7df0213a-86ca-48c8-92aa-8b4a611a2557 | checkpoint | Check table face is clean from dirt, marks, tie wire, footprints, tools, etc.
de9ffae8-eb88-4c78-8371-48cfa0f4d817 | checkpoint | Photo taken of circled hard-copy detail drawing
e3ed066a-d9b9-4c93-a2bb-ddea54d73393 | checkpoint | Attached Pre-pour photos INTERNAL
3f8b6ba7-6e35-4128-9859-e74fbae10e50 | signoff | INTERNAL Inspection Completed
2521cbfd-6dcb-4220-ad70-3055d36d1957 | checkpoint | Attached Pre-pour photos ENGINEER
0ea675c0-4124-468e-ac7b-60675a2ba1b2 | signoff | ENGINEER Inspection Completed
be48ea89-05fe-4f6c-8b45-b3cc68476d63 | checkpoint | Truck Arrival Time
359f9294-be24-56d5-9755-24b568562d08 | textbox | Arrival Time
56dfcb41-7cb8-4334-b6f1-30715625b18b | checkpoint | Concrete Docket Attached (photo)
ac697300-b4da-46dc-81c5-f0758055ceb6 | signoff | Check concrete docket, additive/colour/mpa
8d57fb10-4dac-40ae-8351-55f9a91ca7d4 | checkpoint | Slump Test Completed (Attach Photo)
11f90875-8321-49b6-8118-746f758023d8 | checkpoint | Have pre-pour meeting/who is doing what? (Pouring Methodology)
27398955-6804-59ac-9f9c-6d07758a86de | textbox | Note any water/pre-pour additives
cdd3fe48-6d7b-4c77-9fa1-5c153b6cfa89 | checkpoint | Check concrete placement is to spec: Finished, Exposed AGG, U3, U6, etc.
97340e0c-5859-4b09-a0b9-e423d69fcd75 | checkpoint | Check for post-pour installed items/rebates, float face lifting eyes, inserts, etc.
5ccd9bc8-c1ab-4840-9b7f-f85464cd4c2e | checkpoint | Clean tools and tidy work
7a96e205-8066-4a2e-9f77-14c32d97c8a9 | checkpoint | Check table heating is on
79247cdb-ac8f-49ac-b413-85de7c0a9bb3 | signoff | Leading Hand to Sign for final checks
47292def-5450-4411-b217-5d953408da0b | section | Post-Pour
2f5634d1-6543-4db1-9acb-cd3934ef739b | checkpoint | Post-Pour Details
50adbd34-5b4f-5176-a6b4-214ddb3dd6c9 | date | Date
0d40e3be-8d10-574a-ac6a-1da452ecc18a | textbox | Team stripping
dcdbf1ae-e41c-5501-8716-d5c43ad2c3fc | textbox | Schmidt Hammer serial Number
4a8edb9b-873f-5ffc-8942-c23791c0085a | textbox | Concrete lift strength
| checkpoint | (pre-stress panels only) Strenght 30 mpa or over
| signoff | (pre-stress panels only) Fully trained employee for stressing methodology to sign here before de-stressing
e651a070-45d7-478f-a3b8-9717f20eb44e | checkpoint | Strip mould, clean and tidy formwork
d7cb7246-c354-460a-a34d-3a5d9a81afd9 | checkpoint | All lifters, inserts, weld plates are cleaned out
9cbf1297-16ef-437d-ae37-619379415287 | checkpoint | All edges cupstoned
ac018f48-9789-4d5e-b808-4b15a685ba83 | checkpoint | Waterblast Panel. Has waterblast left marks?
| checkpoint | (pre-stress panels only) All exposed strand-ends coated with BlackSeal
7b550316-43c4-49bf-8299-4965afb5eaf3 | checkpoint | Place panel identification label (on unseen edge)
17acc657-eb13-4b64-b5e1-f5a987435c69 | checkpoint | Remedial Required
c7f2ac26-cdad-4581-8cce-685f6cbae53a | checkpoint | Photo evidence uploaded
fdc1558d-2d0a-5eb3-b7d7-5db14d76e175 | button | Photo of Float Face finish to Standard | YES, NO, N/A
4fe5cde7-36b9-5f02-b1df-23c0b8a87a9c | button | Photo of TableFace finish to Standard | YES, NO, N/A
8e128157-a143-554a-81b0-14d59c3b60e9 | button | Photo of Inserts & Lifters Cleaned out | YES, NO, N/A
c81ba846-6898-55a3-9e05-ca389deca71e | button | Photo of Panel Placement with Correct dunnage | YES, NO, N/A
5eb58995-ea9c-486e-833e-85eaa9e1ba4e | checkpoint | Inspection
22c09663-b8fa-4302-8069-18c6851531cc | signoff | Manager Checked and signed
ce9f7492-5373-4265-b027-01c8f8019053 | checkpoint | Completion of product
8b6ee052-71e7-4cf7-b729-d55c62c8809b | signoff | CLICK TO INFORM PM OF COMPLETION OF PRODUCT
de020313-d6ce-4e85-95de-466f7fe787bc | section | Load-out
7e68562d-e3ff-41a6-8482-b29c0ed9ddf7 | checkpoint | Load out list received
f42f045a-3f76-49b1-8697-8af8b4f877d5 | checkpoint | Panel orientation agreed upon (head of panel to back of truck)
de018f72-edc1-4d9e-976b-0fb8de684cd9 | checkpoint | Panel in good condition before load-out
ac3efe1e-0915-4946-8835-0fcfc70d3272 | checkpoint | Panel landed on suitable dunnage / packers
ef39ac0f-dbee-4137-a718-2b86f488cb2b | checkpoint | Panel in good condition after load-out (note any damage and add photos)
a253fcce-fa52-4ced-b32b-8427190d2e18 | signoff | Load handed over to driver
d0e53cd2-a743-4586-9766-aa22d27b5abc | section | Installation
51a515d7-36e6-4644-8af6-c8373795121a | checkpoint | Latest drawings available, checked and referenced
30edf5fc-836b-4be0-9762-fbb6e4d4cd28 | checkpoint | Set out checked and done
3019e8e1-d05d-4ca0-92cf-f44f1f1c22f6 | checkpoint | Starter Bars checked
6b3dae72-dce4-4fed-8551-96202bba9da2 | checkpoint | Timber Blocks Installed
aaa7c22a-9a3d-4051-91f6-31c427605622 | checkpoint | Packers installed on correct RL
8d2e6f05-e4e5-4aae-bd35-65fa58cfed72 | checkpoint | Lift plan and lift design checked
7b258271-7eb1-4e88-8411-534b8bd3f28b | checkpoint | Check dimensions of panels - on delivery
3e1318fe-e764-40b2-a1c5-741930db8128 | checkpoint | Panel props installed with the correct top and bottom fixings (pins installed and clipped)
990c1de3-4cee-4e1f-a424-faf577a04657 | checkpoint | Verticality checked
e7dda24b-58cf-41f9-a3e0-07a828e20c31 | checkpoint | Panel placed in correct place
f0095aed-2ab4-470b-8440-6fcdada4fc42 | checkpoint | Panel aligned and secured
281d5380-4c27-41d5-9558-c44e8f91115a | checkpoint | Final check - Panel installation complete and ready for sign off
940c288d-4b03-5efe-9e42-29e60e0cd55a | note | Marked up drawing photographed if applicable
9b511bc0-2848-4d07-ac25-92e1dda7e0fc | signoff | Request Review