## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
2193ccb0-1fcb-4af9-b353-462533d5adf1 | checklist | Precast Beams |  | Precast Beams
2f986980-d138-43a2-976f-249abe109269 | section | Pre-Pour Checklist
c8f332a5-6207-4f55-af2f-e4be6954da2a | checkpoint | Details
51fe276f-75c0-512a-90d1-c830f26b8d92 | textbox | Cast Number | 1
7231fcd8-3616-5b64-bac9-342f9a8b687c | textbox | Bridge Name | 3
cd1840fa-d2c3-5cc8-950f-9dc1fead816b | textbox | Precast Parapet 1 | 4
80857ceb-ad59-52fc-8bf1-def2a1f0aea0 | textbox | Precast Parapet 2 | 5
c5b18121-bc8c-4869-8487-9398891e1b0f | checkpoint | Shop Drawings approved for Works
ddccebf1-8af9-4020-9c3d-3a2a890c1036 | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
4c37eb0c-fb3d-5882-b981-f7b5d5dae043 | note | Length
2bbdf1d0-a0df-57c8-a909-1dce3e679840 | note | Width
4a989feb-b448-5b4f-8724-9c2c4b2b61bf | note | Height
ace9da04-a93a-5329-8a56-a90b7a9d71c1 | note | Straightness
2a5e9979-665e-5a01-9567-1633dec3af4e | note | Cross-section
fb4d6b9b-6973-4895-8262-a721fee5cded | checkpoint | Mould Surface Checked
7099e6c7-319a-5a26-9bc4-af7474c00c0f | note | Cleaned
1af80a5e-df59-5f1a-b42a-ccbe3429e008 | note | Sealed
8a1e2267-cd9a-5010-8539-c4a7907b3106 | note | Rubbers in Place
f0d97fc7-2571-5966-84df-17d51cf22bd2 | note | Oiled
84f19e08-aa2f-54a2-b40c-e9bd088b3b1a | note | Chamfers in Place
bff43a15-a9d5-457b-ab57-e8a7791d852e | checkpoint | Reinforcement in Accordance with Drawings
6bf4b403-bc1c-5737-8ddb-321fa25e6896 | note | Reinforcement size
220cc815-79e1-5a43-ad71-76359864c3bd | note | Lap Length
f8c53adb-b452-5d8d-863b-d54f19ef8e53 | note | Splicing
cc53755b-7614-5d5d-99f6-7200397d8162 | note | Bar Chairs
c2915700-0faa-42a1-9c20-d5940e4274f6 | checkpoint | Cover maintained and within tolerance
73ef14e8-2cce-414e-84f4-07c8a92e47a2 | checkpoint | All Cast-in Items are installed in accordance with Drawings
dad94fc3-9f80-55f6-8283-4746612810a3 | note | Cast-in Items
351d5d6c-7b64-540b-a4fc-ebf8cb6ed9c2 | note | Fittings
e37c80ff-8c51-5f66-b163-799d3ff7525e | note | Lifters Position and Type
db158a45-ce57-4d2b-a1c4-f9a10b328451 | checkpoint | QA Engineer Check Completed by
3648b05a-2f27-474d-923a-84895a53e051 | checkpoint | Client Inspector (if present)
840faa4e-f65f-4bfb-88f5-0b990e847278 | section | Supervisor Release
15be12d5-3433-44e7-add0-96b4c5b1428c | checkpoint | Supervisor Release to Engineering Team
5754fcb7-0491-43a1-afc6-65c4725525cc | section | Casting Checklist
f500ca16-4050-4d6f-9447-974d028d16c5 | checkpoint | Casting Information
3e748fb5-ecbe-5084-9aa0-9350952b98e6 | textbox | Cast Date | 2
6e75a19c-25a9-4c69-9e7b-3b03ac0397f5 | checkpoint | Concrete Delivery Dockets
0ca17b05-b390-5e03-97f6-53bf5d9a1880 | textbox | Concrete Delivery Dockets | 8
50763b82-90bd-47ba-a4b8-a1d1652bad78 | checkpoint | Total Concrete Volume
4c7595a6-f3c6-5a7a-9ef6-7628c2ac59c6 | textbox | Volume (m3) | 7
5545b4f0-169b-40ff-b23d-44224a9ca7d9 | checkpoint | Mix Design Verified: WS501MB01 (S50/10/200)
91313c05-78c5-5d8b-94fc-c2d8649fc5b8 | note | Concrete Mix Strength (Mpa) | 6
cbeb6bd6-bb4a-468e-8335-913ea0dee869 | checkpoint | Ambient Temperature within Limits
f7cf5fca-002a-598c-b141-45098f783ad7 | note | 5 - 38°C
d9663593-7a2a-4c91-b3b2-6ae0a715a0c7 | checkpoint | Concrete Temperature
56e8e424-a3da-5b18-a69d-e0e4d5d495f7 | note | max 32°C
6c930ef2-fb24-4d3a-a24e-036292ce2f66 | checkpoint | Slump within Allowable Tolerance
fbd06fc0-dff1-5a61-9343-5dabb12012da | textbox | Slump 1 | 14
d557832e-f872-58c6-9b7d-2daa2c3b1ab3 | textbox | Slump 2 | 15
117d8729-14f1-5ccd-bead-f4794e980bbd | note | Holcim S50/10/200 (Design Slump 200)
2d5ca02d-57a6-4531-adfe-b62ca7a31c6b | checkpoint | Truck Tested for strength
96d44b9a-e54f-5097-b3b4-f58d882c68c4 | textbox | Test Report Reference Number 1
e20f6247-9830-505e-9e27-3dcd4e3cdab4 | textbox | Test Report Reference Number 2
eba4973a-834c-486e-91ce-d61ce0f88c95 | checkpoint | Time Lag Between Trucks (< 20min)
bcbdddf4-aaac-40f0-9b8c-0506e3a82300 | checkpoint | Concrete Placed within 90min from Batching Plant
23c2588a-f777-4019-9b31-35739f9737ea | checkpoint | No Free Fall During Pour (< 2m)
a1f48dc3-b4a0-430a-ab4b-b98e7a660663 | checkpoint | Required Finish Applied as per Drawings
09ce96c7-486c-483a-9866-eb8626c8c335 | checkpoint | Concrete Covered Overnight
74bd9313-606a-445b-9a0d-416aca332551 | checkpoint | Cylinders Stored next to Bed
58e2048a-6ed6-498b-8107-2ebb1b2bd40a | section | Stripping Checklist
8d7d413b-fef3-4a46-a689-fc2c908cf597 | checkpoint | Date Stripped
404d774a-c3a4-59bc-a519-61c2d6f6879b | textbox | Enter Date
f29521d0-3ad7-5eb4-8bbc-728259598d93 | textbox | Stripping Strength | 16
05034373-125c-5dec-a935-757f5616fc3c | note | Strength = Reading / 7.851
c2a4ee7a-b606-4a2a-baf6-9a9d0a4995c0 | signoff | Concrete Cylinders Crushed and Submitted to Client
f9a49329-5e46-472e-95d2-be8beec39669 | checkpoint | Lifting Strength Achieved
eafa6f09-2898-48f7-b22c-4199d9729e47 | checkpoint | Product Clearly Labelled
e62349cc-df91-494a-be7b-ebf761d877d7 | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
43f3972a-15c6-5d4b-af32-083db3fe599e | note | Length
cce12ad2-cc12-547c-806a-8df7fdb79cf7 | note | Width
442277fb-26b1-5c45-b313-2a1f3c8bcabb | note | Height
e05b0a6d-1c31-5a4f-9512-5c00ef90b50c | note | Straightness
199f60d3-96ec-5688-b9e5-08964511bf3f | note | Cross-section
d462759e-7ca2-4ee3-be5c-dbe3bdb10c11 | checkpoint | Specified Finish Achieved
1e1cfbc5-7ae0-4d05-a386-5f9b8ccc22fc | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
ff63e9eb-ae3f-5820-a1cf-6fd84e0783e6 | note | Cast-in Items
400fe668-3bbe-5c6e-ba5b-ae114c990a12 | note | Fittings
f2d97c26-b3bc-5877-a79a-6d4399af887a | note | Lifters Position and Type
640aabc1-d227-4763-afb6-aeaa448e6041 | checkpoint | Lifted and Handled as per Drawings
72782b92-50bf-44c9-9b60-df8ca35966ff | checkpoint | Storage/Stacking as per Approved Plan
be73c218-4467-46b1-98fb-4af6fcb219e9 | checkpoint | Curing as per Approved Methodology
62de2b48-8463-4b1e-b0e6-4466a55def39 | checkpoint | Post-Pour Works Completed (As Required)
7db53572-cc0c-5d2e-8a10-a9031ab6216a | textbox | All Miscellaneous Items are Completed
83973693-a907-44be-b43d-cf9b142c0312 | section | Any Defect Identified
1c5f7451-4724-4135-8000-367935ce0c61 | checkpoint | Punchlisting Completed
5ce1cf89-e2a8-40c9-a78d-a48a91ce2cbf | checkpoint | Repairs Required (if applicable)
32f6b524-443a-4eba-bb57-7fc309e0dfd9 | checkpoint | Repairs Completed as per approved WMS (if applicable)
fc6709d6-a2f2-420e-94b7-25a92d3f54ac | checkpoint | Any NCR Required (if applicable)
8a0b3d3b-ecd3-4452-9213-7b7a5f856889 | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
16d64479-5b92-4b3f-b291-f5567ff6a981 | section | As-Built Drawings
ab9f6733-3fec-431c-a980-93455981227e | checkpoint | As-Built Drawings Completed, Stamped and Attached
0243e2eb-6fb6-41c5-b3e7-97451f3dc1e3 | section | Concrete Strength Test Report
aea11013-a5e1-4a33-a8b3-4b1104bff84a | checkpoint | Concrete Strength Test Report Received
05292874-0e93-52c4-92ad-b7ebcde47cec | textbox | Concrete Test Report Number 1
b5ae2a0a-496f-5798-ac69-6343908a6cea | textbox | 7 Day Strength (1) | 17
cb3e2aeb-fb6b-5bb6-b0e8-2fdd4558d11d | textbox | 7 Day Strength (2) | 18
2e01bf67-cf31-5f6d-bebb-d823d175db54 | textbox | 28 Day Strength (3) | 19
717f8dcc-919d-5184-90f0-5715942b3220 | textbox | 28 Day Strength (4) | 20
c8c3b9bf-6d71-536b-a448-ee517df8abb6 | textbox | 28 Day Strength (5) | 21
430dc950-f667-5b46-a68f-552d39bc1322 | textbox | 28 Day Strength (6) | 22
a19dda5b-190e-47d1-b9b8-60cd1ea1d388 | section | Transportation Requirements
82b26c0a-9c8e-470f-990a-42503bcf33f5 | checkpoint | Certificate of Conformance
bafc30bf-711e-43d3-9c72-4bc98e418fa0 | checkpoint | Inspection Release Certificate
ed3b64c4-854d-4b43-a10e-6f153d5a4f5e | checkpoint | Delivery Notes
831cbc80-c98f-449a-8dc7-182729a2e851 | checkpoint | Delivery Dockets
4f405567-0b36-47a5-a508-f9d8cfbb4420 | section | Final Acceptance (Conforming to all Requirements and is Ready for Transport)
6a922e9a-8a3a-46ba-a2f7-d5642991449d | checkpoint | Completed by
e4e2800f-7fee-40be-a6f9-6aec7cb61a40 | checkpoint | Reviewed by
20af1ebf-5b54-4338-b11a-636a953f31c7 | signoff | (INTERNAL HOLD POINT)
| checkpoint | Client Representative (if applicable)
| signoff | (EXTERNAL HOLD POINT)