## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checkpoint-status |  |  | checklist | Reviewed and Checked by (Allwin Facade Ltd.) |  |  |  |  | Yes | _TEMP - Allwin | 16e83d49-2d65-45e6-8bdd-78b6a1b5e75d
holdpoint |  |  | signoff | Signature
checklist-flat | 44bffba5-6552-4635-ba5a-4e6433ec0ce9 |  | checklist | Gutter Splices & Drainage |  |  |  |  | Yes | SYS - Gutter Splices & Drainage (old version) | 29a77d9c-e357-4026-863f-9dbb99f14bb6
checkpoint-status | 7d5f622f-1e8d-495e-875c-14ad926f6e1c |  | checkpoint | The aluminium surface was cleaned and applied with primer.
checkpoint-status | a0ca9cdd-b344-490a-9e64-e14345f9f653 |  | checkpoint | The rear splice bed is sealed to the gutter and not fillet-sealed at the end
checkpoint-status | 27358367-eac9-4df0-ab60-fe511e5eae0e |  | checkpoint | Real splice seal complete
checkpoint-status | 4de5c953-bc49-4898-8ef4-b473d1399e2b |  | checkpoint | Front splice installed.
checkpoint-status | 2c6474d2-c3a2-4b00-bc76-f76f6aa7a76f |  | checkpoint | Weep hole clear/correct
checkpoint-status | b1e0bc41-8892-4d33-8270-50fef70d56cf |  | checkpoint | Weep hole not filled/blocked
checkpoint-status | 21c74dd6-7291-4859-b2b6-6c92dc38a885 |  | checkpoint | 10 ga S/S Screw installed into male mullion side for both front and rear splice
checkpoint-status | 1002cda1-cca0-4d42-9e8e-5507eee5a245 |  | checkpoint | Front splice bed sealed to the gutter, and fillet sealed at the end
checkpoint-status | 432fe84f-a232-4c2a-9a73-015ecae0f644 |  | checkpoint | The correct type of sealant used (DC 791)
checkpoint-status | 06f18721-69a0-4a86-9300-a4213f8a6d5f |  | checkpoint | A site water test on the gutter was performed.
checklist-flat | b419ea9b-eff3-4fa3-ba78-78b0a37bda8a |  | checklist | Brackets, Bolts & Nuts |  |  |  |  | Yes | SYS - Brackets, Bolts & Nuts (old version) | 2d733a56-5941-45cd-b938-37a5daf2bde4
checkpoint-status | ca4ad3bb-7e77-4f3c-a51c-8be073f63d3c |  | checkpoint | The correct grade of fixing, i.e., stainless steel, galv. Etc
checkpoint-status | 98a4ad6e-f3cb-4a95-b2ed-43702851982b |  | checkpoint | The correct type of nut used, i.e., Nyloc, half nut
checkpoint-status | a3ebd3cb-bebf-454a-af5b-a1b4eecb4dcf |  | checkpoint | The correct type of washer was used.
checkpoint-status | 100d2b0c-f649-43c7-9ab5-76412fca0487 |  | checkpoint | Thread protruding through the nut to a minimum of 1 thread
checkpoint-status | 0fc59122-6e1d-4f54-aa00-4c17effd08a7 |  | checkpoint | Correct diameter of fixing used
checkpoint-status | adbd98f6-6d32-4258-96b3-194399f3322c |  | checkpoint | Seismic screw fixed
checkpoint-status | cbc24c30-c3d2-45fd-9d68-018a6d1a8069 |  | checkpoint | Correct bracket used
checkpoint-status | a6115f41-2e65-4ee2-9f04-99c9f58c6429 |  | checkpoint | Bracket not damaged
checkpoint-status | 516d1bb9-7423-46d3-aad2-002a469c423e |  | checkpoint | Shims are properly installed if you need to.
checkpoint-status | 9dc29d3c-6368-497c-abb2-1b9c9bcd0eda |  | checkpoint | The bracket was installed according to the drawings.
checkpoint-status | a9fcfb08-1934-48a7-b1b2-085f165fff78 |  | checkpoint | Separator installed
checkpoint-status | 4cef0461-3abc-4a2f-8e2a-efe305666f38 |  | checkpoint | Flat / O-ring washer installed to bolt.
checkpoint-status | 64b9c28d-1a84-4d49-9c4f-c287d0f19600 |  | checkpoint | Steel brackets and washers were cleaned and touched up with zinc paint.
checklist-flat | 6ff24f01-6604-4b51-9e45-1d56ed3a2263 |  | checklist | SILL FLASHING, SILL TRAY, & SEISMIC HEAD |  |  |  |  | Yes | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | 2e3e3f5a-ab65-49ea-ab43-4d58e56852ee
checkpoint-status | 8fe473a9-c731-4781-acbf-0848a64d92d8 |  | checkpoint | Sill flashing install.
checkpoint-status | 8c18c610-9635-4e0b-b900-1763d2a7d4eb |  | checkpoint | Sill tray install in the correct RL & GL
checkpoint-status | b9c68c32-ce75-487f-be4c-49719163e6bd |  | checkpoint | Drainage slots / Weep holes do not block, clear, and correct.
checkpoint-status | 886066ed-d184-45f2-b54c-56a87ba23abc |  | checkpoint | Aluminum surface cleaned and applied with primer prior to sealant works.
checkpoint-status | e5e86fdf-aca4-423a-a4fa-5038d64a2561 |  | checkpoint | The number of rear splices installed correctly, seal complete, bed sealed to the gutter, and fillet sealed at the end
checkpoint-status | 9e37c0c5-35f5-4930-84d2-05daff594953 |  | checkpoint | Front splice installed, seal complete, bed sealed to the gutter, and fillet sealed at the end.
checkpoint-status | 7014c66b-a187-4fe8-8335-a4d3af8e03a2 |  | checkpoint | The correct type of sealant used (DC 791)
checkpoint-status | dc692512-4e43-4ba7-bb13-42deaade6e6d |  | checkpoint | Site water test on the gutter, performed
checkpoint-status | 6e935172-1217-4990-97f3-17fe4d24c7e6 |  | checkpoint | Seismic Head installed in the correct RL & GL.
checkpoint-status | 829de8fc-ffce-43b6-b2b2-626147af9fd2 |  | checkpoint | Hed splice installed correctly, seal complete, bed sealed to the seismic Head, and fillet sealed at the end.
checkpoint-status | bc95c14e-bca9-4249-af16-d893f08e50a2 |  | checkpoint | Drilling, cleaning, fixing screws, applying sealant in the hole, and cap sealing the heads of fixings.
checkpoint-status | 5964fe05-fc50-4ae9-84ca-f70fa699532a |  | checkpoint | Complete sealant on all perimeters including air seal.
checklist-flat | 8ffb2fb4-69c9-43b2-b24c-5639a4d197f1 |  | checklist | Rockwool & Fireseal |  |  |  |  | Yes | SYS - Rockwool & Fireseal (old version) | 439c553f-4bdd-47e4-98d6-79768a523ea5
checkpoint-status | 98ea5bf0-b0c8-4d54-b286-f0710085bad8 |  | checkpoint | Z clips at 450 nom. Centers
checkpoint-status | 27a402ce-aa82-4035-8cfb-1a8cc1756d2d |  | checkpoint | Z clips fixed to the top of the slab.
checkpoint-status | c19e1ac7-efb9-4c24-9688-13b46551f0ef |  | checkpoint | GMS fixed as per drawing
checkpoint-status | 8d700fbe-e55d-4fe7-bb97-93269e4ab2a6 |  | checkpoint | Galv sheet sealed at joint
checkpoint-status | c9280848-5fe7-4d98-82d9-cd95c6ee2307 |  | checkpoint | Fixing screws sealed
checklist-flat | f7535c5d-47f3-4f4e-8daf-391931e8e392 |  | checklist | Project Details |  |  |  |  | Yes | SYS - Project Details (old version) | 545ac23d-c08f-4cd0-b73a-a8b0230904d5
checkpoint-status | c9546a01-4cab-46a4-a88b-27c9ad744dde |  | checkpoint | Details
text | 2147e777-a659-5bfc-bb76-6838da88380c |  | textbox | Site Address:
text | d4f474b3-04f2-583e-b5ec-348a272bd03f |  | textbox | Main Contractor Detail:
text | c3dc2351-96e7-58ad-894a-1c0abde3dd1b |  | textbox | Project Manager Details
text | afa31abb-378b-5a66-8d2d-2a52c58ba582 |  | textbox | Site Manager:
text | 71810904-8894-52ed-ba63-157c1381bf88 |  | textbox | Sub Contractor:
checkpoint-status | c5d23d5d-3a1d-4ba6-93b0-a92f6045d064 |  | checkpoint | Latest for Construction Drawing (attachment)
checkpoint-status | 525078f5-c3cc-4044-a04f-05aaecac6647 |  | checkpoint | Scope of Work (attachment)
checkpoint-status | e5d70318-53e2-446f-a11b-a77a355f3144 |  | checkpoint | Additional Pre Start Doc
checklist-flat | b7aa2d92-8c6e-44c5-ab9d-ade222502097 |  | checklist | Aluminum Cladding |  |  |  |  | Yes | SYS - Aluminum Cladding (old version) | 565d34c4-052e-47ac-9842-14f0923787f7
checkpoint-status | ce9d08e2-e392-43be-9d85-647e124cbbc9 |  | checkpoint | Silicone seal on the Head installed during installation
checkpoint-status | 8a6c3c6b-5744-413b-bf72-8b28759d9c72 |  | checkpoint | Angle bracket/subframe to fit
checkpoint-status | a9d413e4-4ceb-4371-b547-6ddcea49c939 |  | checkpoint | Alum cladding installed in the correct level and plumb.
checkpoint-status | de56ecff-2eeb-42d8-9a25-8c222ac9f385 |  | checkpoint | The drain hole is not blocked
checkpoint-status | e0b315e0-4945-4bee-8693-9ca2aed0df74 |  | checkpoint | Sealant complete
checkpoint-status | 66ec88c6-6548-4f37-83b5-596c0f98d3b8 |  | checkpoint | Scratches to aluminum
checkpoint-status | 8e2684d8-50e1-4c1f-af78-40f570875208 |  | checkpoint | Protecting tape not removed
text | 00aab036-c139-51cd-bde9-8f986969e435 |  | textbox | Other:
checklist-flat | c7cd8cbc-520e-4ee8-b528-9690c5b5355c |  | checklist | Structural Opening Handover Checklist |  |  |  |  | Yes | SYS - Structural Opening Handover Checklist (old version) | 83457882-c90d-4c8d-bf40-0a42b9f5fd22
checkpoint-status | 2716304b-b166-48ef-adb6-44ab3ead12d2 |  | checkpoint | Access to the floor/s?
checkpoint-status | 66b94fc4-499e-42aa-819d-de623588c859 |  | checkpoint | Handrails / Edge Protection/s?
checkpoint-status | 86951eea-6bcf-4b56-b2c9-7bc5c96c45e5 |  | checkpoint | Safety Line?
checkpoint-status | 116e9631-3aa7-48d5-86d9-1c57b5f5b758 |  | checkpoint | Are concrete/opening surfaces clear for work?
checkpoint-status | a68ec291-a8a6-4b8e-be21-cf4c7fef553c |  | checkpoint | Surface Preparation (Inc. Vapor Shield and Waterproofing)?
checkpoint-status | ef3f5cf5-d004-4f02-a2f9-6d5d76012aee |  | checkpoint | Electricity/Power Supply / Lights (1-Phase and/or 3-Phase)?
checkpoint-status | 702947b2-f0df-4483-9169-e412a5881456 |  | checkpoint | Access provided?
checkpoint-status | f2262186-4552-438f-ab07-c10078134ad2 |  | checkpoint | Are gridlines visible and accessible (datum marked and confirmed)?
checkpoint-status | dd103984-cf20-4ba4-a9d4-d4fd58c76c2f |  | checkpoint | Structure complete and built as per approved Shop Drawing?
checkpoint-status | 7c84dcdf-4289-4a7a-a5a5-4cecfd080829 |  | checkpoint | Structural fagade opening within tolerance (+/- 10mm total in each direction)?
checkpoint-status | 60dc84b6-5043-4199-83c6-2f7f96fb94f6 |  | checkpoint | Floor slabs pan tolerance max. +/- 20mm over the height of the building?
checkpoint-status | 46c383d1-732c-4543-88ec-9b6304bcf13c |  | checkpoint | Has there been any opening not handover at this level/elevation?
checkpoint-status | fdd0b5ca-a623-4ec3-a924-3f3c39ff93cb |  | checkpoint | Handover
text | 188b99e8-5f04-51c4-8cd5-8574ba77d5cd |  | textbox | Structure Handed-over by:
checklist-flat | 16fff156-ad1f-45ff-90db-fff21732f57b |  | checklist | Fixing of CW Panel |  |  |  |  | Yes | SYS - Fixing of CW Panel (old version) | 8f2f9aa8-efd0-4606-b118-39b58b6342ec
checkpoint-status | 25aff99e-1218-4665-8535-9ba8c6e225e3 |  | checkpoint | The panel within tolerance in Hor, Vert, and Plumb Plane (H, V, P)
checkpoint-status | 9d2f7abb-bac5-437a-a2d7-3f50a729bae6 |  | checkpoint | RL to top of panel correct; refer to set-out tag drawings
checkpoint-status | 4028375a-2fbc-4aa1-81a0-7ebc45dd9730 |  | checkpoint | The mullion joint at the back of the panel is within tolerance.
checkpoint-status | 2ebd66ff-e764-425e-bb48-3a25d897665c |  | checkpoint | Mullion gaskets not missing, cut, or damaged
checkpoint-status | 70c87b92-14d2-430e-bc00-b002ea5edd58 |  | checkpoint | Sub-gutter cut, damaged, short or missing gasket.
checkpoint-status | 80d20ed5-5c73-416c-a449-be8cc9036b97 |  | checkpoint | The foam block at the base of the mullion is on.
checkpoint-status | 1ea3846e-09e1-4453-bae8-938c2804d571 |  | checkpoint | The correct type of sealant used (DC-791 Silicone)
checkpoint-status | a8770e04-7ce6-4be1-920d-93ca282e06d4 |  | checkpoint | The correct panel is installed in a location; please take a look at the tag drawing for reference.
checkpoint-status | 5d70ea13-5f7e-48b2-a13c-a3d05d626aeb |  | checkpoint | No damage to Backpan/insulation
checkpoint-status | e2c3624d-afcc-4de2-83f3-e97ab499a127 |  | checkpoint | No damage to aluminium
checkpoint-status | 650a01d0-7282-4fd5-83aa-e54541aefdbc |  | checkpoint | No damage to the Glass
checkpoint-status | dbcb72e1-ac4d-4a45-90b2-a27e819f58b7 |  | checkpoint | Cruciform seal at mullion/gutter sufficient; should be 50mm above and below transom line.
checkpoint-status | 738cc52a-fb4b-45fb-80fe-c10cbe4201a5 |  | checkpoint | The panel was cleaned before installation (trade clean).
checklist-flat | d9853331-4e40-4fe6-80a2-81be089053cf |  | checklist | FIXING OF PANEL |  |  |  |  | Yes | SYS - FIXING OF PANEL (old version) | 954fd69a-d01f-45c2-bc00-4de0d9b03957
checkpoint-status | 640762eb-2c7c-4d7d-a490-d8f0e78b32f3 |  | checkpoint | Silicon seal on bolt/screw head installed during installation.
checkpoint-status | ff3d3585-7888-4167-8232-b8fd1a50c909 |  | checkpoint | Sub-gutter has not been damaged short or missing gasket.
checkpoint-status | 4cf5494b-0fa3-4b0c-99e2-0a412b0ea482 |  | checkpoint | The foam block at the base of the mullion is on
checkpoint-status | 9c175d54-f6e2-488e-b34a-ccaf02fc4abf |  | checkpoint | The correct type of sealant used (DC-791 Silicone)
checkpoint-status | febaa163-922d-4ba1-a889-610fb6da06b5 |  | checkpoint | The panel within tolerance in Hor, Vert, and Plumb Plane (H,V,P)
checkpoint-status | 99b7e105-adeb-4b28-bb9f-6a965131d94d |  | checkpoint | RL to top of panel correct, refer set-out tag drawings
checkpoint-status | 2968b441-f888-46d5-a2ac-18c655d65acc |  | checkpoint | Correct panel installed in the location
checkpoint-status | cf3eecf4-60e9-45c4-9676-6cf19c2dafbb |  | checkpoint | Head mullion bracket installed bead seal and silicone seal on a head screw.
checkpoint-status | 7cf70cfe-e9e8-4d9e-ba71-f5f69d5e09be |  | checkpoint | The mullion joint at the back of the panel is within tolerance
checkpoint-status | 311e6b4f-1c36-457a-a174-9980aee3fc29 |  | checkpoint | Mullion gaskets not missing, cut, or damaged
checkpoint-status | a49162b6-33ea-44ef-a16e-fd578066cfef |  | checkpoint | No damage to Backpan/insulation
checkpoint-status | 9c48da0c-3421-4da3-9d34-5b433d94e150 |  | checkpoint | No damage to aluminium
checkpoint-status | b30349fd-870a-4072-847d-9b982fdbd76e |  | checkpoint | No damage to the Glass
checkpoint-status |  |  | checklist | Reviewed and Checked by (CMP) |  |  |  |  | Yes | _TEMP - CMP | b4a9b54c-437f-49b6-9173-30ebd2d896e7
holdpoint |  |  | signoff | Signature