## Allwin Facade__Haining St. Apar
Step Id | Warnings | Rich Type | State | resource | type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4
a8b8f596-d862-4c05-9df8-c8c71f3d99c9 |  | checklist-flat | work-in-progress | Project Details | checklist-flat | FALSE | FALSE | Project Details
e702c6b6-35cf-48b8-b61d-3307227c77a7 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Factory QA
89d06b5a-4365-4239-9369-f5085e9d3b25 |  | folder-normal | fail |  | step | TRUE | FALSE | Site QA
47efa84c-a4fc-4aa1-a172-ae421110d6e7 |  | folder-normal | fail |  | step | TRUE | FALSE | Site QA | Ground Floor
3b0a2ff6-4661-4c32-9e0e-85659648c864 |  | folder-normal | pass |  | step | TRUE | FALSE | Site QA | Ground Floor | North Elevation
8f1558b8-7223-410a-87d2-ece9612b84cb |  | checklist-flat | pass | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Ground Floor | North Elevation | Structural Opening Handover Checklist
b8f730a2-5360-4086-bfa6-4b8b636b0a4d |  | checklist-flat | pass | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Ground Floor | North Elevation | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
b8398df8-18d1-40ef-8a5c-f0918ba0376b |  | checklist-flat | pass | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Ground Floor | North Elevation | FIXING OF PANEL
f92dbc31-e25e-4076-8fa2-05717cf59969 |  | checklist-flat | pass | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Ground Floor | North Elevation | Fixing of CW Panel
c3c33955-cc4a-4657-8860-24c56c0470ab |  | folder-normal | fail |  | step | TRUE | FALSE | Site QA | Ground Floor | West Elevation
0f7f8fb4-cc0c-4eb6-901c-83f0fa148b84 |  | checklist-flat | pass | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Ground Floor | West Elevation | Structural Opening Handover Checklist
0cd2e0c5-48f1-40a2-ab4e-8a179f719752 |  | checklist-flat | fail | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Ground Floor | West Elevation | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
5ace1476-143c-4a5c-9d40-07151255555e |  | checklist-flat | pass | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Ground Floor | West Elevation | FIXING OF PANEL
fe55563d-0570-4a45-9233-add34229712f |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Ground Floor | South Elevation
b11b9f64-2954-463c-82b2-bdd21c37e04e |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Ground Floor | South Elevation | Structural Opening Handover Checklist
41ed17a4-a6b6-4eef-b5f0-be962c2329e2 |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Ground Floor | South Elevation | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
348405e4-2dc9-44bc-9dbd-35767d3850c5 |  | checklist-flat | pass | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Ground Floor | South Elevation | FIXING OF PANEL
aa7952bd-3325-45b4-84e3-663f6c2bba83 |  | folder-normal | fail |  | step | TRUE | FALSE | Site QA | Ground Floor | East Elevation
af56e127-1993-43ca-8d2b-ca1cd185a123 |  | checklist-flat | work-in-progress | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Ground Floor | East Elevation | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
ca5cd406-57a1-4812-9025-620a477d2d84 |  | checklist-flat | pass | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Ground Floor | East Elevation | Structural Opening Handover Checklist
ee3c39ba-cca5-4ed7-a72f-99390425c706 |  | checklist-flat | fail | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Ground Floor | East Elevation | Fixing of CW Panel
86533520-6be6-4cea-a9e8-b9f1ebd2d5ba |  | folder-normal | fail |  | step | TRUE | FALSE | Site QA | Level 1
2c49eb36-79bd-4eb6-abf5-53fe1d4c1f34 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 1 | North Elevation
51c96b8f-1d83-4bf1-8d39-d90cb92c789a |  | folder-normal | pass |  | step | TRUE | FALSE | Site QA | Level 1 | North Elevation | Curtain Wall
7cfddd82-e45e-41a6-a505-1456aa0015f1 |  | checklist-flat | pass | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | North Elevation | Curtain Wall | FIXING OF PANEL
8c61bf28-df63-4e8e-981c-7dd41a2731e8 |  | checklist-flat | pass | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | North Elevation | Curtain Wall | Brackets, Bolts & Nuts
d9e6a950-ab13-4b23-91d3-c8379798ac1b |  | checklist-flat | pass | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | North Elevation | Curtain Wall | Gutter Splices & Drainage
f9de5e98-b8fe-4548-9e14-4d3aa2b81055 |  | checklist-flat | pass | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | North Elevation | Curtain Wall | Rockwool & Fireseal
55bc8c2f-3afa-4fbd-a7c7-23cee14e905a |  | checklist-flat | pass | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | North Elevation | Curtain Wall | Fixing of CW Panel
8e3f3a75-6f23-4f90-b594-c12613597219 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 1 | North Elevation | Balcony Area
457aaa4d-ec0e-4c8c-9d1c-a88535e9b62c |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | North Elevation | Balcony Area | Structural Opening Handover Checklist
1f18f7b4-c2a2-4db4-9366-2f33f390d54b |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | North Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
2bd78240-d2e9-4ad2-97e1-c7df3ba1f200 |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | North Elevation | Balcony Area | FIXING OF PANEL
bd78c3dc-b3ab-45f7-b790-0ecd496de06a |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | North Elevation | Balcony Area | Aluminum Cladding
f3c96884-e909-4007-a224-90f6fc3273fb |  | checklist-flat | pass | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | North Elevation | Structural Opening Handover Checklist
1004d803-7bb3-4c56-8676-302da18c78ae |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Site QA | Level 1 | North Elevation | Cast-ins pull up test
80ced9be-320b-4a60-b275-5685d7f3a9f9 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 1 | West Elevation
9fbd4384-1adb-4882-a929-7be3bbd5426f |  | checklist-flat | pass | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | West Elevation | Structural Opening Handover Checklist
0a7e83d6-3a33-45d2-b459-63671b4efb0a |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 1 | West Elevation | Curtian Wall
681f111e-a0f4-48d0-8de1-6ad2a7c38350 |  | checklist-flat | work-in-progress | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | West Elevation | Curtian Wall | Brackets, Bolts & Nuts
420b5c56-493e-4a1a-9766-39b676c7c973 |  | checklist-flat | not-started | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | West Elevation | Curtian Wall | Fixing of CW Panel
0d8bb6f7-1b89-44a9-b828-c0cf1f3d5894 |  | checklist-flat | not-started | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | West Elevation | Curtian Wall | Gutter Splices & Drainage
9a3b63e7-88a0-4139-93f2-b9a7f48ae7f0 |  | checklist-flat | pass | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | West Elevation | Curtian Wall | Rockwool & Fireseal
572c10dc-cae3-431e-8003-4784c03748ee |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 1 | West Elevation | Balcony Area
ce5aba14-2666-4704-9650-5972226215f1 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | West Elevation | Balcony Area | Structural Opening Handover Checklist
901b9e93-ef6c-4e38-abc1-75714f209028 |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | West Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
1e2e3ff7-99ff-4215-b6b2-b58f10db95f8 |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | West Elevation | Balcony Area | FIXING OF PANEL
c7c67066-01c9-47b9-9a03-5ef13fdc4816 |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | West Elevation | Balcony Area | Aluminum Cladding
74f67a0b-695e-4b83-b80b-25ee660b9f3f |  | folder-normal | fail |  | step | TRUE | FALSE | Site QA | Level 1 | South Elevation
a9e84fb9-cb61-45a0-a2b7-d9b20076f3fe |  | checklist-flat | pass | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | South Elevation | Structural Opening Handover Checklist
0478dcb1-5d1c-4434-8b26-3c1ef713b0a4 |  | checklist-flat | pass | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | South Elevation | FIXING OF PANEL
757e1055-275c-458a-8eaf-7a423177871d |  | folder-normal | fail |  | step | TRUE | FALSE | Site QA | Level 1 | South Elevation | Curtian Wall
b2445657-0fdd-453f-b534-a567806c78cd |  | checklist-flat | fail | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | South Elevation | Curtian Wall | Brackets, Bolts & Nuts
425c3227-a99b-4128-a859-2672cb4ca66a |  | checklist-flat | pass | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | South Elevation | Curtian Wall | Fixing of CW Panel
5d1c2708-bb80-4807-929f-44290b7ed398 |  | checklist-flat | pass | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | South Elevation | Curtian Wall | Gutter Splices & Drainage
55943884-266d-44f2-8590-e3027212d92d |  | checklist-flat | pass | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | South Elevation | Curtian Wall | Rockwool & Fireseal
4c95c08d-34a5-4f6c-b90c-e2db869e6109 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 1 | South Elevation | Balcony Area
5dbbd491-cfe6-42c6-839f-ddecbd2ccd7e |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | South Elevation | Balcony Area | Structural Opening Handover Checklist
b949a9f3-a843-48dc-a1d1-1688dbe67f85 |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | South Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
20c42f29-30c2-45a5-bed1-f8395dd6c91e |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | South Elevation | Balcony Area | FIXING OF PANEL
0f584288-9961-4b80-9797-0f5105734110 |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | South Elevation | Balcony Area | Aluminum Cladding
fe2d027e-839e-4712-9e69-f159bfea750f |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 1 | East Elevation
0abf5dc0-dc03-4619-8952-2131f26ce6e7 |  | checklist-flat | pass | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | East Elevation | Structural Opening Handover Checklist
34c450f6-1303-4d2a-b9bb-b05ebbf61a9a |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 1 | East Elevation | Curtian Wall
f3c91331-af97-45aa-b06e-b3506fe47a72 |  | checklist-flat | work-in-progress | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | East Elevation | Curtian Wall | Brackets, Bolts & Nuts
e94ae85a-8a7c-4f3c-bece-4bea23521bd9 |  | checklist-flat | not-started | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | East Elevation | Curtian Wall | Fixing of CW Panel
0ee48b96-1d69-4077-82be-addfaef5c255 |  | checklist-flat | not-started | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | East Elevation | Curtian Wall | Gutter Splices & Drainage
76944a11-0588-415c-901b-8f287a7cbd7d |  | checklist-flat | work-in-progress | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | East Elevation | Curtian Wall | Rockwool & Fireseal
508811a9-5082-400d-8dff-90ac00f2f3c3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 1 | East Elevation | Balcony Area
6f78052b-a64e-4416-a10b-49b593820188 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | East Elevation | Balcony Area | Structural Opening Handover Checklist
c745e189-1bc3-46ad-a701-1346603b198d |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | East Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
fac9bd06-9a37-46b1-998f-bd7aa99ccb39 |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | East Elevation | Balcony Area | FIXING OF PANEL
13c094bd-895f-4275-b043-5c2d804ae7cb |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 1 | East Elevation | Balcony Area | Aluminum Cladding
2585e89a-addb-47e1-a791-14b7eddd135d |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 2
4f107fe7-82b7-4462-8d6d-440c5e426617 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 2 | North Elevation
a5e2bbe2-4c41-4ef7-9c16-6762536abecb |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 2 | North Elevation | Curtian Wall
32957c7f-20f5-44bb-9fd4-4feb98872a39 |  | checklist-flat | work-in-progress | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | North Elevation | Curtian Wall | Structural Opening Handover Checklist
22491e41-e1e5-4aa4-9602-2a96b10e0c26 |  | checklist-flat | work-in-progress | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | North Elevation | Curtian Wall | Brackets, Bolts & Nuts
6570e190-8e13-4fb7-9973-cac1ae47e532 |  | checklist-flat | pass | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | North Elevation | Curtian Wall | Fixing of CW Panel
9cfaa77e-ff7c-4526-8edb-98b4858cf8aa |  | checklist-flat | work-in-progress | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | North Elevation | Curtian Wall | Gutter Splices & Drainage
6c0b7402-ba61-460c-9492-d536c5f128c5 |  | checklist-flat | pass | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | North Elevation | Curtian Wall | Rockwool & Fireseal
3d273854-d75f-43aa-a228-b28178e88780 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 2 | North Elevation | Balcony Area
c9856c95-6768-4def-8a7b-eec79321a70d |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | North Elevation | Balcony Area | Structural Opening Handover Checklist
b88af607-8689-4bf8-989b-161c5c6f0103 |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | North Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
a2fc5e47-dd9b-440c-a2f7-94ee75ec09e9 |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | North Elevation | Balcony Area | FIXING OF PANEL
0abea422-060e-46b2-86ab-4da40269fcec |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | North Elevation | Balcony Area | Aluminum Cladding
dde1fd51-c6ff-427a-8744-15652d2baf34 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 2 | West Elevation
c7845f29-957a-4d10-89e4-f1b22e36f1c6 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 2 | West Elevation | Curtian Wall
53a5b1e8-f34c-4e29-8afd-1e2b2f3c859c |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | West Elevation | Curtian Wall | Structural Opening Handover Checklist
0ac2111e-5d34-4409-b22b-a5e1e0fb976a |  | checklist-flat | work-in-progress | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | West Elevation | Curtian Wall | Brackets, Bolts & Nuts
1b420e2d-f2df-44ad-9031-38b556791d5a |  | checklist-flat | work-in-progress | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | West Elevation | Curtian Wall | Fixing of CW Panel
05e21d79-e0f3-455c-ac22-219ab175efb1 |  | checklist-flat | pass | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | West Elevation | Curtian Wall | Gutter Splices & Drainage
2813e4e1-ba5d-42fb-9732-8f480ff2df59 |  | checklist-flat | pass | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | West Elevation | Curtian Wall | Rockwool & Fireseal
589af1f5-038a-42f3-834d-f0f2ebb319b2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 2 | West Elevation | Balcony Area
bb7884de-5a6f-492f-8f3e-7b3d53b89f95 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | West Elevation | Balcony Area | Structural Opening Handover Checklist
87287726-7ca0-451c-90e4-9ccd17a64833 |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | West Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
3f7b1622-914d-4e48-88c4-338795376176 |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | West Elevation | Balcony Area | FIXING OF PANEL
db1aaf14-e285-4e80-ae31-7afe59a9fdea |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | West Elevation | Balcony Area | Aluminum Cladding
9b469aea-29a5-4e02-b0be-3b45c4493c2d |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 2 | South Elevation
df586f14-4fef-4273-86e5-07e958b565bc |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 2 | South Elevation | Curtian Wall
cceb02a9-41de-4ff0-bfa5-e0c45cb1ad5b |  | checklist-flat | work-in-progress | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | South Elevation | Curtian Wall | Structural Opening Handover Checklist
c68a4f82-f3e8-4717-8ead-bcbcf1e42854 |  | checklist-flat | work-in-progress | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | South Elevation | Curtian Wall | Brackets, Bolts & Nuts
ca9568be-e47b-4af1-883a-d0ea6f822b7e |  | checklist-flat | not-started | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | South Elevation | Curtian Wall | Fixing of CW Panel
5315ec4b-8062-461e-a748-3d7ea95c852d |  | checklist-flat | pass | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | South Elevation | Curtian Wall | Gutter Splices & Drainage
0f464cc2-9fdf-45f4-a53b-654b9d04f823 |  | checklist-flat | pass | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | South Elevation | Curtian Wall | Rockwool & Fireseal
6d82287f-62eb-45b6-bb55-9019a29ddbe7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 2 | South Elevation | Balcony Area
1256f007-c7f1-4c79-b7be-0d4e86d36e9d |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | South Elevation | Balcony Area | Structural Opening Handover Checklist
3fd543da-df4c-42f8-a239-255154b630b0 |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | South Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
27313870-15d3-464f-9cfb-fe4f379506f8 |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | South Elevation | Balcony Area | FIXING OF PANEL
632d6ad1-36dd-4654-a503-1db6360132bb |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | South Elevation | Balcony Area | Aluminum Cladding
fc491924-f6ed-4833-9553-927ade11828c |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 2 | East Elevation
6cb0025e-1687-4a11-9bbc-bab54515ce81 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 2 | East Elevation | Curtian Wall
8c782354-5828-4da7-9321-44c28b75fc1a |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | East Elevation | Curtian Wall | Structural Opening Handover Checklist
f24ee00b-567c-4001-bbc3-cc9c909897e4 |  | checklist-flat | work-in-progress | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | East Elevation | Curtian Wall | Brackets, Bolts & Nuts
92fdf78e-69e5-45fa-a21b-3495979b4a2b |  | checklist-flat | pass | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | East Elevation | Curtian Wall | Fixing of CW Panel
c0a8b4ea-d144-4e3b-bf68-5d3224b3d933 |  | checklist-flat | not-started | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | East Elevation | Curtian Wall | Gutter Splices & Drainage
62e87186-3d48-463c-b864-86dcfedc0622 |  | checklist-flat | pass | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | East Elevation | Curtian Wall | Rockwool & Fireseal
5a1b34e1-176c-4638-8895-cac5b1f3d2e4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 2 | East Elevation | Balcony Area
4ab1e2d4-8640-46ab-bb54-4578fa26bf71 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | East Elevation | Balcony Area | Structural Opening Handover Checklist
9fd095a6-7161-4f5c-965e-7adb5f060014 |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | East Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
32906b11-20aa-4e58-83cb-b4a06961f27a |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | East Elevation | Balcony Area | FIXING OF PANEL
3a016f95-db2b-43a8-b6eb-bf9b436f08a4 |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 2 | East Elevation | Balcony Area | Aluminum Cladding
03129808-6745-49b7-b3d9-5bc9ff4fda4d |  | folder-normal | fail |  | step | TRUE | FALSE | Site QA | Level 3
b353f119-af2b-4161-a62f-546008008902 |  | folder-normal | fail |  | step | TRUE | FALSE | Site QA | Level 3 | North Elevation
f8845f24-ce3d-4ab1-b511-3efe954e56f5 |  | folder-normal | fail |  | step | TRUE | FALSE | Site QA | Level 3 | North Elevation | Curtian Wall
e89e6464-a401-4808-9415-00078fe4b154 |  | checklist-flat | pass | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | North Elevation | Curtian Wall | Structural Opening Handover Checklist
5e4afe54-b7f4-41ef-b4cc-d5033e0e8c0d |  | checklist-flat | fail | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | North Elevation | Curtian Wall | Brackets, Bolts & Nuts
e9ca18ad-c58c-415c-bb41-3f3569f2599f |  | checklist-flat | pass | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | North Elevation | Curtian Wall | Fixing of CW Panel
25838951-d978-47a0-b86b-3abf3f3df976 |  | checklist-flat | work-in-progress | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | North Elevation | Curtian Wall | Gutter Splices & Drainage
34ce805d-2596-4a33-b33c-dc851c483aad |  | checklist-flat | pass | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | North Elevation | Curtian Wall | Rockwool & Fireseal
5615e956-131c-44d0-85ab-a7b21f0af33c |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 3 | North Elevation | Balcony Area
cf813d02-82a5-44b0-8518-900fd0747c04 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | North Elevation | Balcony Area | Structural Opening Handover Checklist
2da98617-4f13-4eff-b669-432a229ddd0e |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | North Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
cd22aab8-a667-4917-a87e-2e06d8cc3e14 |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | North Elevation | Balcony Area | FIXING OF PANEL
3825ad2f-e7af-4a41-a5cb-d5c176c42731 |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | North Elevation | Balcony Area | Aluminum Cladding
499d1ced-9898-4470-ab4c-8ed00192e4f8 |  | folder-normal | fail |  | step | TRUE | FALSE | Site QA | Level 3 | West Elevation
ccf77be1-85d6-4549-8da0-f7793c386beb |  | checklist-flat | fail | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | West Elevation | Brackets, Bolts & Nuts
4a3ccf22-3e4f-4b26-81f9-93751fd661dc |  | checklist-flat | pass | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | West Elevation | Structural Opening Handover Checklist
189b0d05-e66b-4218-a873-f66bfc019634 |  | checklist-flat | pass | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | West Elevation | Gutter Splices & Drainage
81cd77df-3cf5-4e57-8e84-58d8de36caae |  | checklist-flat | pass | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | West Elevation | FIXING OF PANEL
423b45d7-bfca-41fc-8ee0-a36cd0ea89b8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 3 | West Elevation | Balcony
e9fc3817-5260-4cfc-9d2a-109e5085630d |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | West Elevation | Balcony | Structural Opening Handover Checklist
b5925389-c703-4560-a284-59c077a6dbb6 |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | West Elevation | Balcony | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
8b95f905-d2bf-4d6e-aeba-b5e72906fe4b |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | West Elevation | Balcony | FIXING OF PANEL
037f530e-a43f-4462-9146-f9706f665773 |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | West Elevation | Balcony | Aluminum Cladding
a0f0d66d-9835-49fe-8d9f-438cfb8427a5 |  | folder-normal | fail |  | step | TRUE | FALSE | Site QA | Level 3 | South Elevation
e642ad90-6bfd-4f59-9d17-6b9a7bc98a40 |  | folder-normal | fail |  | step | TRUE | FALSE | Site QA | Level 3 | South Elevation | Curtian Wall
307edb38-e140-4c63-ab01-569614e27305 |  | checklist-flat | pass | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | South Elevation | Curtian Wall | Structural Opening Handover Checklist
e3c6b6ba-7884-4383-88ff-47b1764abbf7 |  | checklist-flat | fail | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | South Elevation | Curtian Wall | Brackets, Bolts & Nuts
35aef432-a53e-4bf7-80c6-ff4d905741c4 |  | checklist-flat | pass | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | South Elevation | Curtian Wall | Fixing of CW Panel
417bcbd1-1288-4c41-83e4-0c1d5c4a1099 |  | checklist-flat | pass | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | South Elevation | Curtian Wall | Gutter Splices & Drainage
c5468280-add6-4fb3-af18-bbf2dcb35501 |  | checklist-flat | fail | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | South Elevation | Curtian Wall | Rockwool & Fireseal
43551d3c-ac16-413c-a8e9-79a8a66741bb |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 3 | South Elevation | Balcony Area
a3a32cde-b412-4e4a-bec2-9141f6b3ec6d |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | South Elevation | Balcony Area | Structural Opening Handover Checklist
4f0a6eaf-6bfc-4554-9dd1-bb0eadaf7f9f |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | South Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
61b50653-2723-4332-8696-aa26358b0616 |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | South Elevation | Balcony Area | FIXING OF PANEL
d012a4fd-19bb-42be-8153-8e71801a41a4 |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | South Elevation | Balcony Area | Aluminum Cladding
20992b12-c8ad-4544-a0c3-6070120931b5 |  | folder-normal | fail |  | step | TRUE | FALSE | Site QA | Level 3 | East Elevation
f5c0ef90-144f-4021-9608-db4868e03356 |  | folder-normal | fail |  | step | TRUE | FALSE | Site QA | Level 3 | East Elevation | Curtian Wall
9908976a-8f22-4400-9960-2b70cd8f8a22 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | East Elevation | Curtian Wall | Structural Opening Handover Checklist
1e7d12d0-3fcc-4ad0-8363-8eb1e774dcd5 |  | checklist-flat | fail | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | East Elevation | Curtian Wall | Brackets, Bolts & Nuts
617e6bdb-7cf8-4774-965f-7d1c65bb1396 |  | checklist-flat | work-in-progress | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | East Elevation | Curtian Wall | Fixing of CW Panel
816b4776-4bef-487d-a654-00ce3a774002 |  | checklist-flat | not-started | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | East Elevation | Curtian Wall | Gutter Splices & Drainage
868113f5-354d-44b9-9b69-1f50076a3861 |  | checklist-flat | pass | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | East Elevation | Curtian Wall | Rockwool & Fireseal
e4985368-6c44-4c7b-8281-3f0cbdc4d146 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 3 | East Elevation | Balcony Area
fd1ee440-a870-434c-8f92-5ae6ed7e2bfe |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | East Elevation | Balcony Area | Structural Opening Handover Checklist
2490e5df-bd7c-4aad-9cce-090999688dde |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | East Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
fc184c34-5cc8-4c91-8238-080ed116325c |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | East Elevation | Balcony Area | FIXING OF PANEL
df312d52-ef27-4b89-bd02-94ce3029a76f |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 3 | East Elevation | Balcony Area | Aluminum Cladding
2ed4b6c4-ef70-47a7-8e14-9d300d16d2b3 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 4
7f9791e7-2300-4e1e-ad63-5f4f2bbc677f |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 4 | North Elevation
82b9d79e-8d8c-45cf-be3b-028cc6dba3eb |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 4 | North Elevation | Curtian Wall
5f320a4d-c06a-4250-af71-e90449a5d03f |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | North Elevation | Curtian Wall | Structural Opening Handover Checklist
898b9138-918b-4a80-aa4c-de63a2747a53 |  | checklist-flat | not-started | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | North Elevation | Curtian Wall | Brackets, Bolts & Nuts
5d8382bb-089a-457d-abee-f5e363d930c5 |  | checklist-flat | work-in-progress | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | North Elevation | Curtian Wall | Fixing of CW Panel
aa1914c4-284b-4495-8861-bf4df916ab67 |  | checklist-flat | not-started | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | North Elevation | Curtian Wall | Gutter Splices & Drainage
4852b328-33a9-4c26-8d09-624b497fbd48 |  | checklist-flat | not-started | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | North Elevation | Curtian Wall | Rockwool & Fireseal
d28c80c8-5999-4fd3-ad22-311de325ebdb |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 4 | North Elevation | Balcony Area
92978ffd-5144-4366-bcc0-a1d1c08a0407 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | North Elevation | Balcony Area | Structural Opening Handover Checklist
6300c9d3-8c06-4147-8123-119af16ec851 |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | North Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
81706ce5-b6da-4973-8002-89fadd9e5a3d |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | North Elevation | Balcony Area | FIXING OF PANEL
f335cb81-6241-40ff-9780-ba189c3207ac |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | North Elevation | Balcony Area | Aluminum Cladding
cefdff86-50ed-4064-a937-0046f7b56174 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 4 | West Elevation
1a024dd6-a1d8-4a2d-92e4-8f695b017273 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 4 | West Elevation | Curtian Wall
8862dd71-105b-4adc-928f-af8dc972037c |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | West Elevation | Curtian Wall | Structural Opening Handover Checklist
de56227d-e80a-4ac9-87e7-3845d416e865 |  | checklist-flat | pass | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | West Elevation | Curtian Wall | Brackets, Bolts & Nuts
fc87627c-a563-4c32-8dd9-fd06aa33979c |  | checklist-flat | work-in-progress | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | West Elevation | Curtian Wall | Fixing of CW Panel
4959ff4f-006f-425f-9877-df0dff1c7567 |  | checklist-flat | not-started | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | West Elevation | Curtian Wall | Gutter Splices & Drainage
8e7690c0-1cd5-4d65-a261-68f66937e6ed |  | checklist-flat | not-started | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | West Elevation | Curtian Wall | Rockwool & Fireseal
e03cf178-78a4-4eca-8eb9-0010d755148e |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 4 | West Elevation | Balcony Area
f2f181a8-fdc7-43c6-a6d7-3debe8fd9825 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | West Elevation | Balcony Area | Structural Opening Handover Checklist
2d959a05-a7af-4e9d-ae39-83d3fe115b2c |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | West Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
c1cec701-f6dd-42ec-9ff7-6fd8afdee862 |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | West Elevation | Balcony Area | FIXING OF PANEL
4f38329e-01d9-4f82-9be8-16455828ab7e |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | West Elevation | Balcony Area | Aluminum Cladding
d89a1268-61d7-4262-bcf1-136c039ab5e0 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 4 | South Elevation
fde7b277-5509-4e13-be98-cf452fb7ba83 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 4 | South Elevation | Curtian Wall
1fc1bb11-d792-418a-b523-8bd8ff8f7344 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | South Elevation | Curtian Wall | Structural Opening Handover Checklist
04bfb36a-8681-455d-be6c-3645196f5f52 |  | checklist-flat | pass | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | South Elevation | Curtian Wall | Brackets, Bolts & Nuts
1d7c5358-b3a1-4829-b70e-fb668d7cdd07 |  | checklist-flat | pass | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | South Elevation | Curtian Wall | Fixing of CW Panel
f962b588-0f2e-49a1-8e26-c6d016df40a8 |  | checklist-flat | work-in-progress | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | South Elevation | Curtian Wall | Gutter Splices & Drainage
4a9fe36b-da88-4abd-a52e-b76766f4d137 |  | checklist-flat | pass | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | South Elevation | Curtian Wall | Rockwool & Fireseal
3172409d-61ac-430a-9a80-6d87e182525c |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 4 | South Elevation | Balcony Area
bda0880e-fd15-404d-a9a9-0459d86a154f |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | South Elevation | Balcony Area | Structural Opening Handover Checklist
a6602c28-42ca-4e4f-aa89-8116c0f8ec33 |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | South Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
7d03bc06-53b3-4f66-9c88-356806d39523 |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | South Elevation | Balcony Area | FIXING OF PANEL
68686a33-3569-4f44-b7f3-f98db5e1b6d3 |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | South Elevation | Balcony Area | Aluminum Cladding
18a46b74-61aa-4927-9cf3-2a5ef226e334 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 4 | East Elevation
eee0cc7f-f20b-49a9-b4eb-70fddac989ce |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 4 | East Elevation | Curtian Wall
1817bd4b-3cf1-4526-9ffb-614403166ef0 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | East Elevation | Curtian Wall | Structural Opening Handover Checklist
3a6aed17-01c5-4702-9341-4aea7072e7d0 |  | checklist-flat | not-started | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | East Elevation | Curtian Wall | Brackets, Bolts & Nuts
c63e1102-1236-4fde-a448-6602bf1144a4 |  | checklist-flat | not-started | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | East Elevation | Curtian Wall | Fixing of CW Panel
8ecbe0bd-ec6c-475c-8cfc-bb59e0a5baca |  | checklist-flat | not-started | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | East Elevation | Curtian Wall | Gutter Splices & Drainage
9dc59585-dcd1-42a6-9eef-5708d6a62b57 |  | checklist-flat | not-started | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | East Elevation | Curtian Wall | Rockwool & Fireseal
039b9a14-3e03-4934-95cf-4346fe7c884f |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 4 | East Elevation | Balcony Area
e3d31a14-a547-4071-89a0-0f2cfb571893 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | East Elevation | Balcony Area | Structural Opening Handover Checklist
c30aabab-d725-48bf-8ffa-4be619a76d46 |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | East Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
cf7a1146-23c9-4a02-a913-62dacb9402ad |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | East Elevation | Balcony Area | FIXING OF PANEL
ceb4e5bb-b0c2-4418-aec8-c537758b397f |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 4 | East Elevation | Balcony Area | Aluminum Cladding
95bfcbf7-83e8-4364-a895-0f30fc9d3b3d |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 5
69d95169-e1bd-4ea3-9abd-7e04c212348f |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 5 | North Elevation
843f325b-872b-4896-9a6f-7e87159f2974 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 5 | North Elevation | Curtian Wall
3115cc97-43bb-4738-b598-b37def0b715c |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | North Elevation | Curtian Wall | Structural Opening Handover Checklist
64bf6e9e-75d5-43f6-86d2-166b4475ed2d |  | checklist-flat | not-started | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | North Elevation | Curtian Wall | Brackets, Bolts & Nuts
01f6d245-4a25-4b24-8ac6-83449324f0de |  | checklist-flat | not-started | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | North Elevation | Curtian Wall | Fixing of CW Panel
bab13933-69d1-499d-9877-3b1faa22b139 |  | checklist-flat | not-started | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | North Elevation | Curtian Wall | Gutter Splices & Drainage
a130acf9-daec-4cc0-a1e6-b6f4bbc3f032 |  | checklist-flat | not-started | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | North Elevation | Curtian Wall | Rockwool & Fireseal
06da3d33-6679-45e8-ae9b-4e52b6e9b97b |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 5 | North Elevation | Balcony Area
583f6d67-9b78-44a3-9eb9-a3b9d700fb67 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | North Elevation | Balcony Area | Structural Opening Handover Checklist
94b50cff-fca5-4b28-9da9-66831935c01b |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | North Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
caaea92f-e470-4e16-89ae-0ef5c5146d37 |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | North Elevation | Balcony Area | FIXING OF PANEL
0f7fce09-90da-44f8-a6cf-8999e0360e2d |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | North Elevation | Balcony Area | Aluminum Cladding
8db186e7-21d9-4269-8e5a-c0462741f4b8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 5 | West Elevation
83d2b736-95d8-4257-878d-61ba7adf744c |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 5 | West Elevation | Curtian Wall
6206f15f-802e-4949-83f9-2a0aa3209f91 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | West Elevation | Curtian Wall | Structural Opening Handover Checklist
b1a5a8aa-5dde-40ff-80fb-03d9b159a66c |  | checklist-flat | not-started | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | West Elevation | Curtian Wall | Brackets, Bolts & Nuts
9a4372ee-ad19-4a5f-a347-0612532846e8 |  | checklist-flat | not-started | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | West Elevation | Curtian Wall | Fixing of CW Panel
cb5d1937-25c8-46dc-ba17-591370c119c4 |  | checklist-flat | not-started | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | West Elevation | Curtian Wall | Gutter Splices & Drainage
9b988f7f-1290-466b-bba0-fc0a3a61c3d2 |  | checklist-flat | not-started | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | West Elevation | Curtian Wall | Rockwool & Fireseal
c8cfac31-0cfa-4aad-81a1-32c4bb4275e4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 5 | West Elevation | Balcony Area
8c97a05d-064c-48ed-a65b-872629ad45fa |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | West Elevation | Balcony Area | Structural Opening Handover Checklist
d5803b10-5dce-4343-b189-1a757b12f2a0 |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | West Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
a494abef-aee9-400b-a54e-48a2413a1481 |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | West Elevation | Balcony Area | FIXING OF PANEL
48bdd39c-5874-46af-9d20-b8cd87032986 |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | West Elevation | Balcony Area | Aluminum Cladding
c8b02add-72b8-4169-be9e-f7a080466fe3 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 5 | South Elevation
93f541a5-d8b9-455f-981c-78e7afc4d266 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site QA | Level 5 | South Elevation | Curtian Wall
76f4129b-87f2-406d-9e56-bb7315f16e5c |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | South Elevation | Curtian Wall | Structural Opening Handover Checklist
f18fa616-7561-43a1-9114-2dd9e7f5f843 |  | checklist-flat | work-in-progress | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | South Elevation | Curtian Wall | Brackets, Bolts & Nuts
3df5cdc6-3559-4a2a-a109-64723ea0910b |  | checklist-flat | not-started | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | South Elevation | Curtian Wall | Fixing of CW Panel
ed29e7b5-85e1-4a36-b324-7676761cf732 |  | checklist-flat | work-in-progress | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | South Elevation | Curtian Wall | Gutter Splices & Drainage
73670580-3ed9-4dff-b83c-4020d6c12627 |  | checklist-flat | not-started | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | South Elevation | Curtian Wall | Rockwool & Fireseal
d97a3025-a1a4-4738-86c2-0ecff0f716b0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 5 | South Elevation | Balcony Area
669e1c95-facb-465a-9dd9-ae78636ce050 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | South Elevation | Balcony Area | Structural Opening Handover Checklist
a4f42fad-795e-49c1-8ee2-3d07b2b6f8a6 |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | South Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
db914f37-d319-4c58-899b-3e9ca1baa47c |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | South Elevation | Balcony Area | FIXING OF PANEL
991ee375-8752-4871-95bb-19ed32fadcec |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | South Elevation | Balcony Area | Aluminum Cladding
a012044b-84b6-4be9-850f-c1596c857d5a |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 5 | East Elevation
d64624ad-59c6-4f01-8abe-c91f65adceb1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 5 | East Elevation | Curtian Wall
03a2b742-77c3-46cd-a254-0ecf2d5be29b |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | East Elevation | Curtian Wall | Structural Opening Handover Checklist
ae17e048-6a54-46b7-ad4f-fce8f8167777 |  | checklist-flat | not-started | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | East Elevation | Curtian Wall | Brackets, Bolts & Nuts
d8054ed2-55e4-4b0e-b320-3e61e1ddce10 |  | checklist-flat | not-started | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | East Elevation | Curtian Wall | Fixing of CW Panel
25bb5db3-6d58-46e6-abe4-8124f453217c |  | checklist-flat | not-started | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | East Elevation | Curtian Wall | Rockwool & Fireseal
924f4e86-4d38-4983-9cb0-5835679cfbf1 |  | checklist-flat | not-started | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | East Elevation | Curtian Wall | Gutter Splices & Drainage
f401a99f-b78d-487a-9e36-e72fc4dc4e4b |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 5 | East Elevation | Balcony Area
a9ee47f9-dc42-480d-949a-98d0244dabe6 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | East Elevation | Balcony Area | Structural Opening Handover Checklist
0deeb979-5d97-4e16-9c55-1c5c9f8be9b2 |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | East Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
c7870f4b-9006-44da-8937-c2268ecbe6f4 |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | East Elevation | Balcony Area | FIXING OF PANEL
43e30968-dbbf-4dd9-9f18-b1285cb9593f |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 5 | East Elevation | Balcony Area | Aluminum Cladding
ce289c70-5eb7-4807-a153-ea121a0866e9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 6
003046ed-0349-4ea8-9467-e23f4311f07d |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 6 | North Elevation
e8e7cc59-b08f-413d-ad8c-a0942c765c1f |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 6 | North Elevation | Curtain Wall
81d804d2-64ea-484c-9442-619942f400f6 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | North Elevation | Curtain Wall | Structural Opening Handover Checklist
59e16ed6-df78-41b0-8074-4bbbb19ffa04 |  | checklist-flat | not-started | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | North Elevation | Curtain Wall | Brackets, Bolts & Nuts
c810a4f3-bf0b-4a09-90d3-4221d464a54f |  | checklist-flat | not-started | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | North Elevation | Curtain Wall | Fixing of CW Panel
9b46e0e9-c9cf-44ad-8caf-5a0b7d1e355f |  | checklist-flat | not-started | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | North Elevation | Curtain Wall | Gutter Splices & Drainage
f94979e6-0640-4929-9792-39ea155b175a |  | checklist-flat | not-started | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | North Elevation | Curtain Wall | Rockwool & Fireseal
86cd0582-e025-4389-a0d2-cc68afc9c0a7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 6 | North Elevation | Balcony Area
5efb2c3c-60b1-4347-b2ee-17458d7c34ae |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | North Elevation | Balcony Area | Structural Opening Handover Checklist
9cb3b13d-ebee-4297-9f62-16769f9c2ace |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | North Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
1679c668-c2e2-4c78-8113-41eb11dff433 |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | North Elevation | Balcony Area | FIXING OF PANEL
be1e6184-8b32-4fc2-b7ff-f8c146ecbbed |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | North Elevation | Balcony Area | Aluminum Cladding
68f55df2-6ab6-454c-a5c4-f771c848d2c6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 6 | West Elevation
5729911f-ec13-4d9f-bce2-77496b52c9c3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 6 | West Elevation | Curtain Wall
f3ddc72f-71d7-4aef-8a73-a90363d5d94c |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | West Elevation | Curtain Wall | Structural Opening Handover Checklist
507cad0d-d9a1-4a96-903e-b39cf2f98288 |  | checklist-flat | not-started | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | West Elevation | Curtain Wall | Brackets, Bolts & Nuts
402aa028-b226-41fc-8bef-3a4fbbf3dd51 |  | checklist-flat | not-started | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | West Elevation | Curtain Wall | Fixing of CW Panel
c7704bc1-8883-4561-8ac2-c7a413838754 |  | checklist-flat | not-started | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | West Elevation | Curtain Wall | Gutter Splices & Drainage
6d1fdbaa-5959-4548-9a88-543e0afb371a |  | checklist-flat | not-started | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | West Elevation | Curtain Wall | Rockwool & Fireseal
ae38ccc4-6490-4e46-b7fe-e8ff381f32ec |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 6 | West Elevation | Balcony Area
f8307945-859e-46c5-8c10-411c01d237c9 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | West Elevation | Balcony Area | Structural Opening Handover Checklist
00006161-7c6f-412f-a7fc-262a4e1ab537 |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | West Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
07fbfc41-cd89-4803-a8bc-280b3e20cc4f |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | West Elevation | Balcony Area | FIXING OF PANEL
8675afca-e9af-45d1-aa84-c24bdf8da8c8 |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | West Elevation | Balcony Area | Aluminum Cladding
2fc3e8c8-4bdb-4b80-8f33-7a95389a971f |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 6 | South Elevation
78807512-a709-491c-90f2-6297554bb88f |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 6 | South Elevation | Curtain Wall
8635e177-2eb8-4340-ae18-a25f5985c220 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | South Elevation | Curtain Wall | Structural Opening Handover Checklist
71e1a33d-2abd-4c0a-9abb-368fcdeb9f7b |  | checklist-flat | not-started | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | South Elevation | Curtain Wall | Brackets, Bolts & Nuts
da2d72cb-041c-4643-854d-fd77a8e850d4 |  | checklist-flat | not-started | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | South Elevation | Curtain Wall | Fixing of CW Panel
d70eff36-09d5-4faf-95e5-30c2dbdc45a2 |  | checklist-flat | not-started | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | South Elevation | Curtain Wall | Gutter Splices & Drainage
7c2194b9-118d-4b92-94ad-86c4d52266af |  | checklist-flat | not-started | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | South Elevation | Curtain Wall | Rockwool & Fireseal
07dbceae-1d6d-4a31-8e0c-ca3bc55e93a8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 6 | South Elevation | Balcony Area
6c513682-6afd-4218-9eb5-8b6e3e87f419 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | South Elevation | Balcony Area | Structural Opening Handover Checklist
7eb8e985-8022-4f07-8aa9-70fd9e20a038 |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | South Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
271df7df-7fd5-431e-8cfa-214025f60ea2 |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | South Elevation | Balcony Area | FIXING OF PANEL
67da9f8f-f5c2-4ef4-aad5-884c0b077730 |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | South Elevation | Balcony Area | Aluminum Cladding
cba70653-1301-4e45-a1ed-3ad3e2b51371 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 6 | East Elevation
ac310dce-71a4-428d-8eab-c3cb0c55b35d |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 6 | East Elevation | Curtain Wall
9c9dc97b-3dfe-4b40-aee0-98345bcc082e |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | East Elevation | Curtain Wall | Structural Opening Handover Checklist
2df68ce3-99d0-4f09-82d5-f26bf6a0ee52 |  | checklist-flat | not-started | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | East Elevation | Curtain Wall | Brackets, Bolts & Nuts
f48639a4-6e86-4095-94f5-b0d093418197 |  | checklist-flat | not-started | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | East Elevation | Curtain Wall | Fixing of CW Panel
0cdb801d-7ea7-4429-b339-86196ba4da43 |  | checklist-flat | not-started | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | East Elevation | Curtain Wall | Gutter Splices & Drainage
d38958eb-c267-4af5-8ec4-1433c086227d |  | checklist-flat | not-started | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | East Elevation | Curtain Wall | Rockwool & Fireseal
afd2628e-91dc-4f4f-aa9c-83aa9cbc90e6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 6 | East Elevation | Balcony Area
1f20873e-f397-4ab5-af78-701f046d3494 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | East Elevation | Balcony Area | Structural Opening Handover Checklist
b154ffe0-b843-47dd-a744-e812514a7071 |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | East Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
f1fe93a1-0f05-4530-88b7-0710fa04b969 |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | East Elevation | Balcony Area | FIXING OF PANEL
ff99b058-7121-49cc-bc32-2851a29b2fd3 |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 6 | East Elevation | Balcony Area | Aluminum Cladding
65e896f2-b8ff-479d-904a-1acd1da09758 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 7
f8a814a7-4acf-439f-b151-3501bbe3fae3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 7 | North Elevation
d9548ccc-51ea-4645-b439-733f863b3e59 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 7 | North Elevation | Curtain Wall
b3c4bf94-96ea-4574-8202-5088c2808330 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | North Elevation | Curtain Wall | Structural Opening Handover Checklist
3be01efb-a6e9-4f4e-a349-7ae2728cd709 |  | checklist-flat | not-started | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | North Elevation | Curtain Wall | Brackets, Bolts & Nuts
cb2b43d4-9c0e-4a54-a86b-3a2c7728d29a |  | checklist-flat | not-started | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | North Elevation | Curtain Wall | Fixing of CW Panel
71823b22-6c26-4c2d-988b-9ae681ceb002 |  | checklist-flat | not-started | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | North Elevation | Curtain Wall | Gutter Splices & Drainage
117c24db-8da9-4ca4-97c4-009ac20f5ab5 |  | checklist-flat | not-started | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | North Elevation | Curtain Wall | Rockwool & Fireseal
2281abeb-830b-41d3-b8ae-1c9939fc9983 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 7 | North Elevation | Balcony Area
5f040606-438e-4ecc-9e91-caba1dd180af |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | North Elevation | Balcony Area | Structural Opening Handover Checklist
c147f3a4-b9e3-4549-8cc8-981b3bad0cef |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | North Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
d1d0e880-2194-4eea-8fcc-e92b42dd9cbf |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | North Elevation | Balcony Area | FIXING OF PANEL
4800beec-aad3-45e0-a7c7-bae9da54acec |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | North Elevation | Balcony Area | Aluminum Cladding
af0c5380-d3ec-46e9-befc-9ed018c9c530 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 7 | West Elevation
c18c9416-31c1-408b-a3ed-37750d79e63c |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 7 | West Elevation | Curtain Wall
12a9687e-7c66-4fd4-9258-2efe82e64afe |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | West Elevation | Curtain Wall | Structural Opening Handover Checklist
3bc42530-639d-45b3-bf1d-1c01ae816836 |  | checklist-flat | not-started | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | West Elevation | Curtain Wall | Brackets, Bolts & Nuts
583c3657-062f-4e8d-85ee-76b20895b389 |  | checklist-flat | not-started | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | West Elevation | Curtain Wall | Fixing of CW Panel
495a436a-0eea-4764-a669-da201f4641e4 |  | checklist-flat | not-started | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | West Elevation | Curtain Wall | Gutter Splices & Drainage
669526dc-bde9-44de-a800-f3adb4680306 |  | checklist-flat | not-started | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | West Elevation | Curtain Wall | Rockwool & Fireseal
12dcfd28-f8f8-4b18-a77b-c6aa9a72b68e |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 7 | West Elevation | Balcony Area
49c9d097-b1d9-4e95-92bd-b3b1bef3ddeb |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | West Elevation | Balcony Area | Structural Opening Handover Checklist
0f6c480a-63c8-4e46-984c-3010e4e9a534 |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | West Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
c6fe781a-ddaa-4048-9d99-82bfa94a066a |  | checklist-flat | not-started | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | West Elevation | Balcony Area | Fixing of CW Panel
87e899eb-f3f0-4f82-8502-47b4dbe09798 |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | West Elevation | Balcony Area | Aluminum Cladding
4e095588-dfe5-4b05-89df-1f0588865931 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 7 | South Elevation
6ebf0645-c100-47cf-a6b1-4ccdb09de98d |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 7 | South Elevation | Curtain Wall
0822bbc4-6b21-45f2-adfe-db6634caf571 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | South Elevation | Curtain Wall | Structural Opening Handover Checklist
3af3c570-a692-4593-97b2-eb0fde4323a1 |  | checklist-flat | not-started | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | South Elevation | Curtain Wall | Brackets, Bolts & Nuts
27ccc318-b58e-424a-b727-5cc104d323b8 |  | checklist-flat | not-started | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | South Elevation | Curtain Wall | Fixing of CW Panel
2ca6d74b-a1fc-4505-9253-a030e34d3825 |  | checklist-flat | not-started | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | South Elevation | Curtain Wall | Gutter Splices & Drainage
c7d1b2d3-f566-4362-a012-b5c954616a5f |  | checklist-flat | not-started | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | South Elevation | Curtain Wall | Rockwool & Fireseal
4dcbe37b-1eff-4299-9a73-b4407eeb420b |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 7 | South Elevation | Balcony Area
97d8f824-fe39-41f5-971b-06b5f0eb5174 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | South Elevation | Balcony Area | Structural Opening Handover Checklist
90ee351b-c8c6-468b-9822-8c10ea41e010 |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | South Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
399bc37b-4a8c-4877-950f-07321ebb566a |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | South Elevation | Balcony Area | FIXING OF PANEL
feea8beb-51d1-4015-9447-c80902c0d412 |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | South Elevation | Balcony Area | Aluminum Cladding
b31db712-e704-4390-a7f8-6123e2056b9f |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 7 | East Elevation
c0bd1aca-4a67-46d4-8cd8-d56bc2d77eca |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 7 | East Elevation | Curtain Wall
b7584316-aee2-4307-a177-4964e02b84fd |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | East Elevation | Curtain Wall | Structural Opening Handover Checklist
9fede8f6-6d0a-4135-9d3e-182730ba2f71 |  | checklist-flat | not-started | SYS - Brackets, Bolts & Nuts (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | East Elevation | Curtain Wall | Brackets, Bolts & Nuts
2bdb97c0-79dd-425d-a704-d66957ed8603 |  | checklist-flat | not-started | SYS - Fixing of CW Panel (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | East Elevation | Curtain Wall | Fixing of CW Panel
9c28566b-08c4-40f1-a8b1-ebd7c06a84f7 |  | checklist-flat | not-started | SYS - Gutter Splices & Drainage (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | East Elevation | Curtain Wall | Gutter Splices & Drainage
3e93781c-f752-491a-b81e-5fe1e5e61556 |  | checklist-flat | not-started | SYS - Rockwool & Fireseal (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | East Elevation | Curtain Wall | Rockwool & Fireseal
2a18ab72-f998-4722-a248-8dff4add5b8e |  | folder-normal | not-started |  | step | TRUE | FALSE | Site QA | Level 7 | East Elevation | Balcony Area
577540c4-2e75-4e71-8c6f-ffdfd4400986 |  | checklist-flat | not-started | SYS - Structural Opening Handover Checklist (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | East Elevation | Balcony Area | Structural Opening Handover Checklist
5ac79de6-fbf9-44a1-a6e5-6701ce6e8533 |  | checklist-flat | not-started | SYS - SILL FLASHING, SILL TRAY, & SEISMIC HEAD (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | East Elevation | Balcony Area | SILL FLASHING, SILL TRAY, & SEISMIC HEAD
175aeb72-4a26-49e3-9a14-50a935b5ab3e |  | checklist-flat | not-started | SYS - FIXING OF PANEL (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | East Elevation | Balcony Area | FIXING OF PANEL
bbe37f45-1b59-4949-a174-08914ef93a4b |  | checklist-flat | not-started | SYS - Aluminum Cladding (old version) | checklist-flat | FALSE | FALSE | Site QA | Level 7 | East Elevation | Balcony Area | Aluminum Cladding
eb0c80cd-9c19-4bb4-aa29-56d7a891700b |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Site QA | Level 8
431f5931-3f5f-48c7-8a42-4dd2a871bff1 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Site QA | Level 8 | North Elevation
f9cf7c66-e167-4bb5-bada-6f17eccd6aca |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Site QA | Level 8 | West Elevation
e8003f9a-77c6-49a4-befb-f2c97e711419 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Site QA | Level 8 | South Elevation
6314dc02-0ba7-4b7d-b3a8-2cd8a14451e2 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Site QA | Level 8 | East Elevation