## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-005 -Track Drains | itp |  |  |  |  | ITP-005 -Track Drains
section | 1 - Preliminary Works
checkpoint | 1.1 Check for correct documentation
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Drainage design satisfies requirements of all relevant catchment and drainage authorities, a copy of all drainage work approvals are to be forwaded to the superintendent
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.3 Materials Check
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Ensure drainage pipes are of correct classification and are without damage
note | • Check triangle drains are of adequate quality, and are design according Ri57A rail profile
note | • Ensure lid and j-bolts being used are in accordance with STD T9022
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.1 STD T9021A STD T9020 STD T9022
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection, Inspection Checklist
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off, Recievable Inspection Checklist
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.4 Bedding Sand
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • The bedding of all pipes shall be in accordance with AS.3500.3-2003 using sand complying to the following:
note | • Max. particle size of 5 mm, Not more than 5% by weight passing a 75 micron AS 1152 sieve, Free from organic impurities,Consisting of hard durable particles, and well graded.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
section | 2 - Construction Works
checkpoint | 2.1 Set out drainage
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • The position of all drainage lines are to be confirmed with the superintendent
note | • Track drain locations are to be identified and based off IFC drawings and sections.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Design Drawings and Register
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.2 Excavation (pipes)
note | FREQUENCY: Each Trench
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Trenching to allow for minimum clearance depth of 100mm below UPVC pipe, and 15mm from bottom of rail to surface of pipe
note | • Track drains usually have invert for pipes at 400mm depth, with floor of pit 10mm deeper.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: STD T9021 CE-021-ST-0044 cl 4.3
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.3 Bedding
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Class 2 crush rock shall be compacted to refusal of 100mm minimum thickness
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: STD T9021A
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.4 Joining
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: All UPVC pipes shall be joined utilising 'male' to 'female' ends.UPVC pipes shall be joined using appropriate plumbing adhesive immediately prior to connection.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.5 Track Drain Installation
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Track drains shall be welded to designated positions, and cleaned of all weld splatter.
note | • Weld shall be sealed after installation
note | • Rectangular 300 x 450mm junction pit & lid shall be used with 4 x j-bolts secured as per STD T9022
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: STD T9021A STD T9022
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.6 Points Drainage
note | FREQUENCY: Where required
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • The road motor box pit for automatic points shall be drained separately to the normal switch drain and care shall be taken to ensure that water cannot flow into the road motor box pit.
note | • Points drainage shall be constructed as shown on Standard Drawing STD_T0304, with 100mm dia UPVC pipe.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3 STD T0304 STD T0305
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.7 Concrete Pour
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ensure correct heights of sub grade, as to allow for minimum thickness 150mm concrete, to be poured in same period as track slab
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: STD T9021A
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.8 Connection to local drainage
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Drainage shall be connected to existing Principal’s, VicRoads or the Local Authority's storm water drainage system using either UPVC pipe or reinforced concrete pipes, or an alternative approved by the relevant authority.
note | • The minimum pipe size shall be 150 mm.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: