## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-006 - Track Placement | itp |  |  |  |  | ITP-006 - Track Placement Rev3
section | 1 - Preliminary Works
checkpoint | 1.1 Check for Correct Documentation
note | FREQUENCY: Prior to Commencing Works
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Design Drawings and Register
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.2 Check Materials
note | FREQUENCY: Prior to Commencing Works
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used
note | • Check condition of rail sleepers
note | • Ensure rail jewellery is of sound condition
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: AS 1085
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Client, Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.3 Check Special Works Components
note | FREQUENCY: Prior to Commencing Works
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Special Works is any trackwork which must be pre-fabricated (ie bent or assembled) before it can be installed on site. This includes all switches, crossings and any trackwork which needs pre-bending.
note | • Ensure that all rails for crossing work is head hardened, and the appropriate weld kits and welding methods are adopted for welding modules and seperate rails.
note | • Superintendent to visit yard from intial inspection of the rail and fabrication plans.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.2
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.4 Check Curved rail
note | FREQUENCY: Prior to Commencing Works
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Rails for curved trackwork, i.e. radius less than 150 m, shall be head hardened and pre-bent.
note | • Additional 25 mm diameter tie bar holes may need to be drilled or cut into the web of the rails.This is to allow installation of additional tie bars between the rails to ensure correct gauge can be maintained during concreting.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.3
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.5 Welders Qualifications
note | FREQUENCY: Prior to Commencing Works
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Welders shall be trained and compliant in Aluminothermic Welding Requirements;
note | ○ TLIW2012 Grind Rails
note | ○ TLIW3015 Weld Rails using Aluminothermic welding process
note | ○ TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.6 Ultrasonic Testers Qualifications
note | FREQUENCY: Prior to Commencing Works
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing.
note | • Certification shall be provided to and approved by the Superintendent prior to commencement of testing.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
section | 2 - Construction Works
checkpoint | 2.1 Installation of Sleeper
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Dual block sleepers shall be installed at 700mm intervals, toelrance of +/- 50mm in placement
note | • Dual block sleepers shall also comply with the design offsets at each chainage
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.7.1
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.2 Placement of Rail
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | Ensure rail strings conform to rail plan
note | • All track work, including points and crossings shall confrom to alignment, offset, level and cant as per design drawings and track charts
note | • Bottom of rail and bearing surface shall be clean of foreign materials before laying
note | • Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device
note | • Geometry tolerances as follows:
note | – Centreline location: +/- 3mm
note | – Level: +/- 3mm - Line measured (>10m chord): +/- 3mm
note | – Twist (3.5m chord): +/- 2mm
note | – Cant: +/- 3mm
note | – Gauge (open track): +3mm, -0mm
note | – Gauge,Turnouts (opposite crossings): +2, -0mm
note | – Gauge, Diamonds and ‘H’ Crossings: +2, -0mm
note | • Note: Cant shall be applied uniformly over transitions
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.10
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Completion of track charts
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.3 Placement of Jewellery
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Each sleeper shall be fastened to track with approved jewellery and rail clips
note | • Clips shall be installed with panpuller or equivalent
note | • All fasteners shall be sealed as per agreed method with Yarra Trams
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.4 Rail End Preparation
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Rails shall be saw cut or flame cut
note | • Minimum closure length from proximity of welds shall be 2m
note | • Rail end conditions shall match (i.e flame cut - flame cut)
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9 & Appendix C Code of Practise SkV Elite Welding Proc.
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.5 Welding of Rail
note | FREQUENCY: Each Weld
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Joints shall be square across the track
note | • Maximum skew at square joints shall be 65mm
note | • Portions shall match rail type (i.e HHR, Ordinary)
note | • Welds shall not be within:
note | – 3m of another weld
note | – 3m of a rail end
note | – 1.5m of a glued insulation joint assembly
note | • Field welds shall be +/- 50mm from centre of bay between sleepers
note | • Weld Return forms shall be completed by qualified welder
note | • Welds shall be grinded after 1 hour
note | • Welds shall be free of water
note | • Post grinding, welds shall be cleaned for visual inspection
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9. & Appendix C AS1085 Code of Practise SkV Elite Welding Proc.
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | TP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.6 Grinding & Cleaning Welds
note | FREQUENCY: Each Weld
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring).
note | • The grinding stroke should not exceed 500 mm to each side of the weld.Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection.
note | • The vertical tolerance of the weld (of a 1m straight edge) shall be 0mm for dip and between 0mm and 0.5mm for peak.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.7 Track Adjustment
note | FREQUENCY: When required
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | Allowance must be made for expansion and contraction of rail to control stress.
note | The required adjustment depends on rail temperature at time of laying and/or adjusting the rail lengths,which shall be measured with anapproved type of thermometer.
note | In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep.
note | Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C STD T9008
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.8 Track Bonds
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Positions and configurations shall conform to design drawings and Yarra Trams Standards and Specifications
note | • Ensure bonds are sealed as per agreed method with Yarra Trams
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.5.4 Appendix C Design Drawings
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Inspection / Test Method
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
section | 3 - Testing
checkpoint | 3.1 Track Testing
note | FREQUENCY: Each Weld
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • All welds shall be tested by qualified NDT operator
note | • Failed welds shall be cut out and replaced
note | • Testing documentation shall be recorded and supplied to the superintendent
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Inspection / Test Method
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | TP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer/NDT
note | – – – – – – – – –
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: