## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-015-CIV-Kerb and Channel | itp |  |  |  |  | ITP-015-CIV-Kerb and Channel Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
note | Document Title: ITP-015-CIV-Kerb and Channel
note | ITP Description: Kerb and Channel
note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
note | Discipline (e.g. CIV/STR/RAIL): CIV
note | Revision Number: 0
note | Revision Date: 16/12/22
note | ITP created by: Isaac El Zayat
note | ITP approved for use by: Victor Mira
note | 1.1 Non Dependent
note | Reference: VicRoads Section 703, VR SD2001, VR SD2102, AS 2876, AS1379
section | Preliminary Works - Materials
checkpoint | 2.2 Mix design
note | REFERENCE: SD2001, AS1379, Section 703.05, 703.06, 703.07
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Approved VR mix design to be used.
note | • Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3
note | • Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cement–based concrete
textbox | TeamBinder Material approval number for the Concrete Mix:
note | – – – – – – – – – – – – – – – – –
note | METHOD: Verify
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: TeamBinder Material approval, ITP signed
textbox | Date Completed:
checkpoint | 2.3 Bedding Material
note | REFERENCE: Section 703.21, IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete. Or as per IFC drawings.
textbox | TeamBinder Material approval number for Bedding:
note | – – – – – – – – – – – – – – – – –
note | METHOD: Verify
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: TeamBinder Material approval, ITP signed
textbox | Date Completed:
checkpoint | 2.4 Curing Compound
note | REFERENCE: Section 703.10
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Curing compound shall comply with AS3799
textbox | TeamBinder Material approval number for Curing Compound:
note | – – – – – – – – – – – – – – – – –
note | METHOD: Verify
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: TeamBinder Material approval, ITP signed
textbox | Date Completed:
section | Preliminary Works - Documents
checkpoint | 2.1 Check for correct documentation
note | REFERENCE: Drawing and Drawing Register
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ensure that all employee and sub contractors are:
note | — Using the correct and complete set of drawings
note | — All drawings are the latest version
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual inspection
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ITP Signed
textbox | Date Completed:
checkpoint | Lot Map
note | REFERENCE: MRPA Lot Management Procedure
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Upload a Marked up drawing which indicates the Location of this Lot:
note | • Attach: Lot Map
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: For Each Lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Lot Map
textbox | Date Completed:
section | Pre-construction / Pre-installation Activities
checkpoint | 3.1 Setting out
note | REFERENCE: Section 703.17
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Set out work in accordance with drawing.
note | • The superintendent will review and confirm set out.
note | • The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
note | • Attach: Survey Report
note | – – – – – – – – – – – – – – – – –
note | METHOD: verify
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Prior to start
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Surveyor
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ITP signed, Survey Report
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.2 Temporary drainage provisions
note | REFERENCE: Section 703.18
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place.
note | • Need to obtain prior written approval from the relevant waterway authority prior to diversion.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual inspection
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: If required
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: WP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ITP signed
textbox | Date Completed:
section | Construction / Installation Activities
checkpoint | 4.1 Bedding
note | REFERENCE: Section 703.21
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Bedding to be compacted to a thickness of not less than 100mm.
note | • Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted .
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: WP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ITP signed
textbox | Date Completed:
checkpoint | 4.2 Formwork
note | REFERENCE: Section 703.12 AS3610
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Joints in formwork shall be constructed such that loss of mortar is prevented.
note | • Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual Inspection
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: WP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ITP signed
textbox | Date Completed:
checkpoint | 4.3 Pre Pour Check
note | REFERENCE: Section 703.09
note | • Section 703.21 Section 610.17a), b) & c)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
note | • Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
note | – – – – – – – – – – – – – – – – –
note | METHOD: Verify
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ITP signed
textbox | • Ambient temperature |  |  | °C
textbox | Date Completed:
checkpoint | 4.4 Concrete placement
note | REFERENCE: Section 703.08
note | • Section 703.23
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
note | • Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
note | • Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
note | • Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ITP signed
textbox | • Ambient temperature |  |  | °C
textbox | Date Completed:
checkpoint | 4.5 Transitions
note | REFERENCE: Section 703.24
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Site inspection
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ITP Signed
textbox | Date Completed:
checkpoint | 4.6 Surface Finish
note | REFERENCE: Section 703.25
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
note | • Renderings shall be applied within 30 minutes of extrusion.
note | • Concrete to have a neat appearance and uniform colour.
note | • Class 3 finish required for external surfaces.
note | • Class 4 finish required for permanently hidden surfaces.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual inspection
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ITP signed
textbox | Date Completed:
checkpoint | 4.7 Formwork Stripping
note | REFERENCE: Section 703.12 AS3610
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Formwork shall not be stripped before the minimum time of:
note | — External faces 2 days
note | — Permanently hidden faces 1 day
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual inspection
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ITP signed
textbox | Date Completed:
checkpoint | 4.8 Tolerance
note | REFERENCE: Section 703.15
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width , for dimension less than 25mm tolerance to be ±3mm.
note | • Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm.
note | • Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
note | – – – – – – – – – – – – – – – – –
note | METHOD: verify
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/surveyor
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ITP signed
textbox | Date Completed:
checkpoint | 4.9 Curing
note | REFERENCE: Section 703.10
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
note | • Concrete edgings shall be cured for a period of not less than three days after placing the concrete
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual inspection
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ITP signed
textbox | Date Completed:
checkpoint | 4.10 Joints
note | REFERENCE: Section 703.26
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
note | • Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
note | • Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Verify
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each joint
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ITP signed
textbox | Date Completed:
checkpoint | 4.12 Protection of Concrete
note | REFERENCE: Section 703.27
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual inspection
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ITP signed
textbox | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 4.11 Backfilling
note | REFERENCE: Vic Road spec 703.29
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Verify
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ITP signed
textbox | Date Completed:
checkpoint | 4.13 Cracking of Concrete
note | REFERENCE: Section 703.30
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
note | • Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual inspection
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ITP signed
textbox | Date Completed:
checkpoint | 5.1 Survey Conformance
note | REFERENCE: Section 703.15
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Survey to as built the works and to confirm the works are within the specified tolerances.
note | • The departure of the finished work from line or level shall not exceed 10 mm at any point, and the rate of change of deviation from line or level shall not exceed 10 mm in 10 m.
note | • Attach: Survey Report
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Completion of each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: WP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: PE/Surveyor
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: As-built survey records
textbox | Date Completed:
checkpoint | 5.2 Non-conformance Report (NCR) Closure
note | REFERENCE: MRPA Quality Management Plan
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, prior to closure of this lot / element / Work area
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP