## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP013 - PCC Pavements | itp |  |  |  |  | FH-ZU2-QU-ITP013 - PCC Pavements - Rev 1
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Current revision of drawings, technical specifications and any other construction documentation is being utilised by Fulton Hogan and subcontractors.
label | ○ Current revisions of these documents to be obtained via Aconex or ACC.
label | Reference Documents - Current Revisions in Aconex or ACC
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing works
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WMS
label | Reference Documents - PSP, EMP, TMP, SWMS, WMS
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.3 - Mix Design Report Submission and Approval
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Theoretical mix design and preliminary trial mix results submitted in a report to the Contract Administrator for review and acceptance prior to full trial mixing.
label | Reference Documents - Beca Spec 002 - 11.5.3
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Reference
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
label | Principal's Representative - BecaCPL-GCOR-000846
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Job Mix Formula
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The Job Mix Formula must state the mass proportion of all ingredients per cubic metre of concrete. The allowable limits in the Job Mix Formula (when compared to the agreed theoretical concrete mix design) must be in accordance with Table 11-2 of BECA 11.5.4 (see notes section).
label | Reference Documents - Beca Spec 002 - 11.5.4
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Reference
label | WP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
label | Principal's Representative - BecaCPL-GCOR-000839
checkpoint | 1.5 - Production and Construction Trials
label | Frequency - Prior to commencing works
label | Acceptance Criteria - A production and construction trial must be completed as per the requirements in the specification.
label | ○ The results, control procedures, construction methods and completed trial pavement will be presented for review and approval by the Contract Administrator.
label | Reference Documents - Beca Spec 002 - 11.6.1 to 11.6.4
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Reference
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Curing Compound Material Submission
label | Frequency - Prior to use of curing compound
label | Acceptance Criteria - Membrane curing compounds shall be a white pigmented type confirming to AS 3799, Type 2. Wax based compounds shall not be used.
label | ○ No compound shall be used without written approval by the Contract Administrator.
label | Reference Documents - Beca Spec 002 - 11.4.11.1
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Reference
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
label | Principal's Representative - BecaCPL-GCOR-000791
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Impermeable Blanket Material Submission
label | Frequency - Prior to use of impermeabl e blanket
label | Acceptance Criteria - If required to be used, impermeable blankets shall comply with the requirements of ASTM C.171.
label | ○ The blankets shall have sufficient strength and weight to meet the required conditions of service and shall be approved by the Contract Administrator before use.
label | Reference Documents - Beca Spec 002 - 11.4.11.2
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Reference
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 - Pre-Placement Activities
checkpoint | 2.1 - Formwork Installation
label | Frequency - Prior to placing concrete
label | Acceptance Criteria - Formwork must rest firmly on the base to eliminate gaps and ensure no leakage of concrete will occur during placement.
label | ○ Formwork must be secured into position and locked together during placing, spreading and finishing of the concrete.
label | ○ The top of the form must not deviate by more than 3mm from the required level.
label | ○ The form face shall be vertical and not vary more than 6mm from the required alignment.
label | Reference Documents - Beca Spec 002 - 11.8.1.1
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 2.2 - Pre-pour checklist
label | Frequency - Prior to placing concrete
label | Acceptance Criteria - Completion of the pre-pour checklist: CL013A – Pre-Pour Checklist which details various checks required for formwork, reinforcement, joints and the pour area.
label | Reference Documents - Beca Spec 002 - 11.8, 11.10, 11.13
label | Inspection/Test Method - Visual inspection
label | Record of conformity - CL013A, This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 2.3 - Pre-pour inspection
label | Frequency - Prior to placing concrete
label | Acceptance Criteria - The area in which concrete is proposed to be placed shall be inspected and checked immediately prior to commencement of placing.
label | Reference Documents - Beca Spec 002 - 11.9.1
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 2.4 - Weather Forecast Checks
label | Frequency - Prior to placing concrete
label | Acceptance Criteria - Check the weather forecast for unfavourable conditions (rain, wind, hot weather or cold weather) on the day prior and immediately before confirming
label | Reference Documents - Beca Spec 002 - 11.9.5.1
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
section | 3.0 - Placing Concrete
checkpoint | 3.1 - Place, Spread and Compact Concrete
label | Frequency - Each concrete pour
label | Acceptance Criteria - Concrete placement must be at a rate appropriate to achieve a consistent high quality resulting pavement.
label | ○ During placing, the concrete must not drop freely by more than one metre onto the base of the paving lane.
label | ○ Concrete shall be placed uniformly over the width of the slab and in a way to minimise segregation.
label | ○ Concrete to be adequately compacted by internal mechanical vibration.
label | Reference Documents - Beca Spec 002 - 11.9.1, 11.9.4, 11.11.2.1
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 3.2 - Concrete Deliveries
label | Frequency - Each concrete pour
label | Acceptance Criteria - Each concrete delivery to site is to be recorded on CL013B – Concrete Pour Record Sheet.
label | ○ Concrete shall be placed within 90 minutes from the time of batching and before the concrete has attained its initial set.
label | ○ The pour location, direction and order to be recorded on CL013C – Load-Batch Traceability.
label | Reference Documents - Beca Spec 002 - 11.9.1
label | Inspection/Test Method - Verify
label | Record of conformity - CL013B CL013C, This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 3.3 - Evaporation Rate
label | Frequency - Each concrete pour
label | Acceptance Criteria - Concrete must not be when the evaporation rate from the surface of unprotected concrete is in excess of one (1) kg/m²/hr.
label | ○ When the evaporation rate exceeds 0.6 kg/m²/hr, precautionary measures to prevent plastic shrinkage shall be taken.
label | ○ Evaporation rate to be recorded on CL013D – Rate of Evaporation.
label | Reference Documents - Beca Spec 002 - 11.9.5.2
label | Inspection/Test Method - Verify
label | Record of conformity - CL013D, This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 3.4 - Hot Weather Concreting
label | Frequency - Each concrete pour
label | Acceptance Criteria - Undertake additional precautions when placing concrete in hot weather.
label | ○ Ensure the concrete is placed at the coolest temperature practicable – the concrete temperature should not exceed 32°C.
label | Reference Documents - Beca Spec 002 - 11.9.5.3
label | Inspection/Test Method - Verify
label | Record of conformity - CL013B, This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 3.5 - Cold Weather Concreting
label | Frequency - Each concrete pour during ‘cold weather concreting’ conditions
label | Acceptance Criteria - Cold weather concreting applies when placing concrete when the temperature of the air, aggregates or water is below 10°C.
label | ○ Placement of concrete can only proceed if the ground temperature at the concreting site is greater than 5°C and the temperature of the concrete is not below 10°C.
label | ○ Refer to checklist CL013E – Cold Weather Concreting for ground temperature records.
label | Reference Documents - Beca Spec 002 - 11.9.5.4
label | Inspection/Test Method - Verify
label | Record of conformity - CL013B CL013E, This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 3.6 - Concrete Surface Finishing
label | Frequency - Each concrete pour
label | Acceptance Criteria - Finishing operations shall compose transverse finishing, longitudinal straight-edge finishing, floating and broom finishing, in that order.
label | ○ Finishing operations must be started immediately after compaction of the concrete and completed as soon as possible but not later than 90 minutes from the time of batching and prior to the concrete attaining its initial set.
label | Reference Documents - Beca Spec 002 - 11.11.2.2
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
section | 4.0 - Sampling and Testing Concrete
checkpoint | 4.1 - Slump
label | Frequency - 1 test every 2 trucks
label | Acceptance Criteria - 60mm +/- 10mm
label | Reference Documents - Beca Spec 002 - 11.24.18, BecaCPL- GCOR- 000846
label | Inspection/Test Method - AS 1012.3.1
label | Record of conformity - NATA Test Certificate
label | TP
label | Responsibility - Project / Site Engineer, Laboratory Technician
date | Date Completed:
checkpoint | 4.2 - Temperature
label | Frequency - 1 test every 2 trucks
label | Acceptance Criteria - Minimum 15°C (except in cold weather concreting where minimum is 10°C)
label | ○ Maximum 32°C
label | Reference Documents - Beca Spec 002 - 11.24.17
label | Inspection/Test Method - AS 1012.3.1
label | Record of conformity - NATA Test Certificate
label | TP
label | Responsibility - Project / Site Engineer, Laboratory Technician
date | Date Completed:
checkpoint | 4.3 - Flexural Strength (7 day)
label | Frequency - First 5 lots: 2 Beams per 75m3 or part thereof.
label | ○ After 5 lots: 1 Beam per 75m3 or part thereof.
label | Acceptance Criteria - Results for information only
label | Reference Documents - Beca Spec 002 - 11.24.10
label | Inspection/Test Method - AS 1012.11
label | Record of conformity - NATA Test Certificate
label | TP
label | Responsibility - Project / Site Engineer, Laboratory Technician
date | Date Completed:
checkpoint | 4.3 - Flexural Strength (28 day)
label | Frequency - First 5 lots: 2 Beams per 75m3 or part thereof.
label | ○ After 5 lots: 2 Beams per 75m3 or part thereof.
label | Acceptance Criteria - Mean of the pair of beams > 5.0 MPa Individual beams > 4.8 MPa
label | Reference Documents - Beca Spec 002 - 11.24.10, 11.24.11.5
label | Inspection/Test Method - AS 1012.11
label | Record of conformity - NATA Test Certificate
label | TP
label | Responsibility - Project / Site Engineer, Laboratory Technician
date | Date Completed:
checkpoint | 4.4 - Air Content
label | Frequency - 1 test per Lot
label | Acceptance Criteria - 3% - 5% ±1%
label | Reference Documents - Beca Spec 002 - 11.24.8, 11.24.9
label | Inspection/Test Method - AS 1012.4.1 or 1012.4.2
label | Record of conformity - NATA Test Certificate
label | TP
label | Responsibility - Project / Site Engineer, Laboratory Technician
date | Date Completed:
checkpoint | 4.5 - Mass Per Unit Volume
label | Frequency - 1 test per Lot
label | Acceptance Criteria - Results for information only
label | Reference Documents - Beca Spec 002 - 11.24.9
label | Inspection/Test Method - AS 1012.5
label | Record of conformity - NATA Test Certificate
label | TP
label | Responsibility - Project / Site Engineer, Laboratory Technician
date | Date Completed:
checkpoint | 4.6 - Wet Analysis
label | Frequency - 1 test per Lot
label | Acceptance Criteria - Results for information only
label | Reference Documents - Beca Spec 002 - 11.24.9
label | Inspection/Test Method - AS 1289.3.6.1
label | Record of conformity - NATA Test Certificate
label | TP
label | Responsibility - Project / Site Engineer, Laboratory Technician
date | Date Completed:
checkpoint | 4.7 - Concrete Core Analysis (Density & Compressive Strength)
label | Frequency - First 10 lots: 6 cores per Lot
label | ○ After 10 lots: 1 core per 75m3 or part thereof
label | Acceptance Criteria - Cores must be not less than 120mm diameter.
label | ○ Calculate the degree of compaction by comparing the density of individual cores with the average density of flexural test beams (exclude beams whose density is less than 97.5% of maximum theoretical density). Refer to notes section for acceptance requirements.
label | ○ On third of the cores taken shall not be tested for density but shall be tested for compressive strength and results submitted for information purposes only.
label | Reference Documents - Beca Spec 002 - 11.24.13
label | Inspection/Test Method - AS 1012.12, AS 1012.9
label | Record of conformity - NATA Test Certificate
label | TP
label | Responsibility - Project / Site Engineer, Laboratory Technician
date | Date Completed:
section | 5.0 - Post-Placement
checkpoint | 5.1 - Curing
label | Frequency - Each concrete pour
label | Acceptance Criteria - Concrete shall be cured by protection against loss of moisture and rapid temperature changes for a period of not less than seven (7) days from completion of the finishing operations.
label | ○ Curing of the concrete shall comprise an initial mist curing followed as soon as possible with continuous wet curing with hessian matting for the duration of curing period.
label | Reference Documents - Beca Spec 002 - 11.12.4
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 5.2 - Cold Weather Concreting Concrete Protection
label | Frequency - Each concrete pour during ‘cold weather concreting’ conditions
label | Acceptance Criteria - The surface of the concrete must be maintained at a temperature of at least 10°C, for not less than 72 hours after placing and at a surface temperature above freezing (0°C) for the remainder of the curing period.
label | ○ Concrete surface temperatures post-pour to be recorded on checklist CL013E – Cold Weather Concreting.
label | Reference Documents - Beca Spec 002 - 11.9.5.4
label | Inspection/Test Method - Verify
label | Record of conformity - CL013E
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 5.3 - Inducement Saw Cutting
label | Frequency - Each concrete pour
label | Acceptance Criteria - An initial 3-5mm wide saw cut to a depth of T/4 to T/3 where ‘T’ is the concrete thickness (generally 150mm) is performed along transverse contraction joints as early as possible post pour.
label | ○ The concrete must harden sufficiently to permit cutting the concrete without excessive chipping, spalling, or tearing.
label | Reference Documents - Beca Spec 002 - 11.13.5.2
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 5.4 - Formwork Removal
label | Frequency - Each concrete pour
label | Acceptance Criteria - Forms must remain in place at least 12 hours after the concrete has been placed (but no longer than 48 hours).
label | Reference Documents - Beca Spec 002 - 11.8.1.3
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
section | 6.0 - Completion
checkpoint | 6.1 - Surface Smoothness Testing
label | Frequency - Per Lot
label | Acceptance Criteria - The finished surfaces of the concrete pavements shall not deviate from the testing edge of an approved 3.5m straight-edge more than 5mm longitudinally and 5mm transversely. No ponding of water is permitted.
label | ○ Points exceeding tolerances and any observed areas of ponding water will be recorded on ArcGIS.
label | Reference Documents - Beca Spec 002 - 11.14.3
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - ArcGIS, This ITP Signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 6.2 - Pavement Surface Levels
label | Frequency - Per Lot
label | Acceptance Criteria - The Contractor shall take levels on the finished pavement surface at the corner of each slab.
label | ○ The finished surface levels taken shall be within ±5mm of the design levels shown on the Drawings.
label | ○ The levels shall be measured to an accuracy of 2mm.
label | Reference Documents - Beca Spec 002 - 11.14.2
label | Inspection/Test Method - Verify
label | Record of conformity - Conformance Report
label | SCP
label | Responsibility - Project / Site Engineer, Surveyor
date | Date Completed:
checkpoint | 6.3 - Protection of Slabs
label | Frequency - Per Lot
label | Acceptance Criteria - Concrete pavement must not be trafficked until 7 days old or early strength results are obtained. Steel tracked or steel wheeled equipment is not to be used.
label | Reference Documents - Beca Spec 002 - 11.17
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 6.4 - Defects to Slabs
label | Frequency - Per Lot
label | Acceptance Criteria - Check for any nonconforming defects (cracks) in the concrete slabs.
label | Reference Documents - Beca Spec 002 - 11.19
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality/System Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: