## res_1630-P200-SYM-QAC-ITP-0021.
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CC0399 - ITP-002 - Site Clearing | itp |  |  |  |  | CC0399 - ITP-002 - Site Clearing
section | 1.0 Pre-start activities
checkpoint | 1.1 - Determine Lot Size
label | Ref docs - NA
label | Acceptance criteria - What is the lot size?
textbox | Acceptance |  |  | m2
label | Maximum lot size = 4,000m2
label | Freq - Once
label | Key - S
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Work Lot Map
checkpoint | 1.2 - Safety
label | Ensure that the following items have been actioned:
label | – SWMS if applicable
label | – Plant Pre-start Inspection
label | – Service locations identified
label | – Traffic Management Plans (if req’d)
label | – All staff inducted
label | Ref docs - SWMS TMPS, Plant prestart inspection form
label | Acceptance criteria - SWMS submitted reviewed and accepted if required. Personnel inducted to SGJV requirements.
label | ○ Plant inspections completed and entered.
label | ○ Pre-work briefings completed. Service diagrams available and services located.
button | Acceptance | Yes,No,N/A
label | Freq - Once (Pre-Start)
label | Key - W
label | Resp - SS
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Hard copy of the SWMS, Plant prestart inspections, TMs present onsite at all times
checkpoint | 1.3 - Excavation Permit
label | Ref docs - Excavation permit template
label | Acceptance criteria - All identified underground services marked and potholed to confirm location and depth. No machine excavation within 1m of underground services. Permit available and signed.
button | Acceptance | Yes,No,N/A
label | Freq - Prior to start of works
label | Key - H
label | Resp - SS
label | SGJV Key - W
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Signed Excavation Permit
checkpoint | 1.4 - Check Survey Set-out
label | Ref docs - IFC dwgs
label | Acceptance criteria - Survey setout extend of works
button | Acceptance | Yes,No,N/A
label | Freq - Prior to start of Works
label | Key - H
label | Resp - SV, SS
label | SGJV Key - W
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Not Applicable
section | 2.0 CLEARING AND GRUBBING
checkpoint | 2.1 - Clearing and Grubbing
label | Ref docs - MRH/00/P/0 0- PM/SPC/000 3 rev 3 page 53
label | Acceptance criteria - Have the identified areas been cleared of all vegetation, refuse, unsuitable material and obstructions down to natural surface?
label | ○ In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed.
label | ○ Unsuitable material and topsoil is to be stockpiled in the designated location and is not to be used as fill material.
button | Acceptance | Yes,No,N/A
label | Freq - Once
label | Key - W
label | Resp - SS
label | SGJV Key - W
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos/visual check
section | 3.0 Topsoil Stripping
checkpoint | 3.1 - Stripping
label | Ref docs - IFC Construction MRH/A0/B/0 0- CV/DWG/00 08
label | Acceptance criteria - Has the area been stripped and stockpiled to an appropriate depth (minimum top 50mm) removing surface topsoil and unsuitable material in a way to leave the surface evenly graded and free-draining?
button | Acceptance | Yes,No,N/A
label | Freq - Once
label | Key - W
label | Resp - SS
label | SGJV Key - W
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Visual/Daily reports
checkpoint | 3.2 - Topsoil export / stockpiling
label | Ref docs - IFC construction drawing MRH/A0/B/0 0- CV/DWG/00 21
label | Acceptance criteria - Has the topsoil being stockpiled been approved by SGJV (where applicable) and silt fence around the stockpile present?
label | ○ Have the environmental controls as per CHMP &CEMP and Enviro/Biodiversity Assessment been adhered to.
label | ○ Dispose material as per CHMP and Enviro/Biodiversity requirements
button | Acceptance | Yes,No,N/A
label | Freq - Once
label | Key - W
label | Resp - SS
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Stockpile plan/Photos