## res_1630-P200-SYM-QAC-ITP-0021.
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CC0399 - ITP-003 - Bulk Earthworks | itp |  |  |  |  | CC0399 - ITP-003 - Bulk Earthworks
section | 1.0 Preliminaries
checkpoint | 1.1 - Determine lot size
label | Ref docs - N/A
label | Acceptance criteria - What is the lot size?
textbox | Acceptance |  |  | m2
label | Freq - Prior to start of Works
label | Key - S
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Lot Map
checkpoint | 1.2 - Survey set-out
label | Ref docs - IFC Dwgs
label | Acceptance criteria - Is the most current survey file what the team is working to and has the work area been set out for line and level?
button | Acceptance | Yes,No,N/A
label | Freq - Each lot & Each possession
label | Key - W
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos
checkpoint | 1.3 - Water management
label | Ref docs - EMP
label | Acceptance criteria - Where necessary, have batters been rounded and catch drains constructed to allow for potential surface runoff during the course of excavation?
button | Acceptance | Yes,No,N/A
label | Freq - Each lot & Each possession
label | Key - S
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos
checkpoint | 1.4 - Clearing
label | Ref docs - CC0399- ITP-002
label | Acceptance criteria - Has the area been cleared and grubbed in accordance with ITP-002?
button | Acceptance | Yes,No,N/A
label | Freq - Prior to start of Works
label | Key - W
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos
checkpoint-no-status | Is the area in cut / fill / both?
label | If in cut proceed to step 2.0 and strike out section 3.0.
label | If in fill please strike out section 2.0 and proceed to section 3.0
label | If in both proceed to step 2.0 as well as section 3.0
section | 2.0 Bulk earthworks – Cut
checkpoint | 2.1 - Excavation material classification
label | Ref docs - MRH/00/P/0 0- PM/SPC/00 03 rev 3 page 53
label | Acceptance criteria - Has the material being excavated been inspected with category agreed upon by Superintendent? Tick category below:
bool | Topsoil
bool | Unsuitable material
bool | Fill material
bool | Other
textbox | Other:
button | Acceptance | Yes,No,N/A
label | Freq - Prior to start of Works
label | Key - W
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Test reports
checkpoint | 2.2 - Stockpile
label | Ref docs - N/A
label | Acceptance criteria - Has the stockpile location been approved by SGJV.
button | Acceptance | Yes,No,N/A
label | Freq - Prior to start of Works
label | Key - H
label | Resp - SE
label | SGJV Key - H
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - SGJV approved stockpile plan
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Subgrade preparation
label | Ref docs - MRH/A0/B/ 00- CV/DWG/00 40
label | Acceptance criteria - Has the cut surface been trimmed to an even surface free from lose material?
label | ○ Have surface levels been checked to avoid over excavation?
button | Acceptance | Yes,No,N/A
label | Freq - Each lot & Each possession
label | Key - S
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Test reports/as- built survey
checkpoint | 2.4 - Lime mix
label | Ref docs - MRH/A0/B/ 00- CV/DWG/00 40
label | Acceptance criteria - Has lime demand testing been completed and submitted?
button | Acceptance | Yes,No,N/A
label | Freq - Prior to starting
label | Key - H
label | Resp - SE
label | SGJV Key - H
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Test reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Lime stabilisation
label | Ref docs - MRH/A0/B/ 00- CV/DWG/00 40
label | Acceptance criteria - Has the prepared subgrade been lime stabilised as per the IFC design?
button | Acceptance | Yes,No,N/A
label | Freq - Each lot & Each possession
label | Key - S
label | Resp - SE
label | SGJV Key - W
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos/As-built report
checkpoint | 2.6 - Compaction
label | Ref docs - IFC drawing MRH/A0/B0 0- CV/DWG/00 08
label | Acceptance criteria - Compaction Scale: minimum 3 tests per lot, or 1 test per 1000m2
label | ○ Has the stabilised subgrade been adequately compacted achieving 100 SDD for subgrade.
label | ○ Is the subgrade material within +/- 2% of the optimum moisture content.
label | ○ Has a minimum 3% CBR been achieved?
button | Acceptance | Yes,No,N/A
label | Freq - Each lot & Each possession
label | Key - W
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Test reports
checkpoint | 2.7 - Test Rolling
label | Ref docs - MRH/A0/B/ 00- CV/DWG/00 40
label | Acceptance criteria - Does the layer withstand test rolling without visible deformation or springing?
textbox | List Attendees:
button | Acceptance | Yes,No,N/A
label | If ‘no’ please see below. If ‘yes’ please proceed.
label | Freq - Each lot & Each possession
label | Key - H
label | Resp - SE
label | SGJV Key - H
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Proof Roll Inspection Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Identification of soft wet or unstable material
label | Ref docs - IFC Dwg
label | Acceptance criteria - What quantity of soft, wet, or unstable material is present?
label | Acceptance
textbox | m2
textbox | m3
label | Freq - As required
label | Key - W
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos
checkpoint | Treatment of unsuitable material
label | Ref docs - N/A
label | Acceptance criteria - Has rectification process been submitted to SGJV for review. What was the rectification process used.
button | Acceptance | Yes,No,N/A
label | Freq - As required
label | Key - W
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Aconex Correspondence
section | 3.0 Bulk earthworks - Fill
checkpoint | 3.1 - Fill material classification
label | Ref docs - MRH/00/P/0 0- PM/SPC/00 03 page 53
label | Acceptance criteria - Has the material to be used as fill been approved for use?
button | Acceptance | Yes,No,N/A
label | Freq - Prior to start of Works
label | Key - S
label | Resp - SE
label | SGJV Key - H
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Material Acceptance correspondence/Certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Stripped surface - test rolling (If applicable)
label | Ref docs - MRH/A0/B/ 00- CV/DWG/00 40
label | Acceptance criteria - Does the stripped surface to be filled withstand test rolling without visible deformation or springing?
textbox | List Attendees:
button | Acceptance | Yes,No,N/A
label | If ‘no’ please see below. If ‘yes’ please proceed to item 3.2
label | Freq - Each lot & Each possession
label | Key - H
label | Resp - SE
label | SGJV Key - H
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Proof roll checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Identification of soft wet or unstable material (1)
label | Ref docs - N/A
label | Acceptance criteria - What quantity of soft, wet or unstable material is present?
label | Acceptance
textbox | m2
textbox | m3
label | Freq - As required
label | Key - H
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos /Visual check
checkpoint | Treatment of unsuitable material (1)
label | Ref docs - N/A
label | Acceptance criteria - What rectification process is to be undertaken
button | Acceptance | Yes,No,N/A
label | Freq - As required
label | Key - S
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Aconex Correspondence/Approval from SGJV
checkpoint | 3.3 - Preparation of surface
label | Ref docs - MRH/A0/B/ 00- CV/DWG/00 40
label | Acceptance criteria - Has adequate water been added to the stripped surface to ensure adhesion to the next layer?
button | Acceptance | Yes,No,N/A
label | Freq - Each lot & Each possession
label | Key - S
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos
checkpoint | 3.4 - Fill Placement
label | Ref docs - IFC drawing MRH/A0/B0 0- CV/DWG/00 08
label | Acceptance criteria - Has fill been placed in maximum 300mm and minimum 100mm compacted layer thickness?
label | ○ Rock in the fill should be less than 75 mm.
label | – Fill should be free of clay and free from organic.
button | Acceptance | Yes,No,N/A
label | Freq - Each lot & Each possession
label | Key - S
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos
checkpoint | 3.5 - Moisture
label | Ref docs - MRH/A0/B/ 00- CV/DWG/00 40
label | Acceptance criteria - Has the material maintained at optimum moisture content (within +/- 2% of optimum moisture), with additional water being added if required during compaction?
button | Acceptance | Yes,No,N/A
label | Freq - As required
label | Key - S
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Test Reports
checkpoint | 3.6 - Lime mix
label | Ref docs - IFC Dwgs MRH/A0/B/ 00- CV/DWG/00 40
label | Acceptance criteria - Has mix demand testing been completed and submitted?
button | Acceptance | Yes,No,N/A
label | Freq - Once
label | Key - H
label | Resp - SE
label | SGJV Key - H
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Test reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Lime stabilisation
label | Ref docs - MRH/A0/B/ 00- CV/DWG/00 40
label | Acceptance criteria - Has the prepared subgrade been lime stabilised as per the IFC design?
button | Acceptance | Yes,No,N/A
label | Freq - Each lot & Each possession
label | Key - S
label | Resp - SE
label | SGJV Key - W
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos/As-built report
checkpoint | 3.8 - Compaction
label | Ref docs - IFC drawing MRH/A0/B0 0- CV/DWG/00 08
label | Acceptance criteria - Compaction Scale: minimum 3 tests per lot, or 1 test per 1000m2
label | ○ Has the stabilised subgrade been adequately compacted achieving 100% SDD for subgrade.
label | ○ Is the subgrade material within +/- 2% of the optimum moisture content.
label | ○ Has a minimum 3% CBR been achieved?
button | Acceptance | Yes,No,N/A
label | Freq - Each lot & Each possession
label | Key - W
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Test reports
checkpoint | 3.9 - Test Rolling
label | Ref docs - MRH/A0/B/ 00- CV/DWG/00 40
label | Acceptance criteria - Does the layer withstand test rolling without visible deformation or springing?
textbox | List Attendees:
button | Acceptance | Yes,No,N/A
label | If ‘no’ please see below. If ‘yes’ please proceed
label | Freq - Each lot & Each possession
label | Key - H
label | Resp - SE
label | SGJV Key - H
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Proof Roll Inspection Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Identification of soft wet or unstable material (2)
label | Ref docs - IFC Dwgs
label | Acceptance criteria - What quantity of soft, wet or unstable material is present?
label | Acceptance
textbox | m2
textbox | m3
label | Freq - As required
label | Key - S
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos
checkpoint | Treatment of unsuitable material (2)
label | Ref docs - IFC Dwgs
label | Acceptance criteria - Has rectification process been submitted to SGJV for Review? What was the rectification process used?
button | Acceptance | Yes,No,N/A
label | Freq - As required
label | Key - H
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos
section | 4.0 Conformance check
checkpoint | 4.1 - Width and alignment
label | Ref docs - IFC Dwgs
label | Acceptance criteria - Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings?
button | Acceptance | Yes,No,N/A
label | Freq - Once
label | Key - W
label | Resp - SE
label | SGJV Key - H
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | As built report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Subgrade level and shape
label | Ref docs - IFC Dwgs
label | Acceptance criteria - Has the prepared subgrade been surveyed in accordance with and verifying specified requirements?
label | ○ Is the subgrade within +/- 20mm of design surface.
button | Acceptance | Yes,No,N/A
label | Freq - As required
label | Key - W
label | Resp - SE
label | SGJV Key - H
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | As built report
holdpoint | AUTHORITY HOLDPOINT