## res_1630-P200-SYM-QAC-ITP-0021.
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CC0399 - ITP-005 - Crushed Rock Pavement Construction | itp |  |  |  |  | CC0399 - ITP-005 - Crushed Rock Pavement Construction
section | 1.0 Pre-start activities
checkpoint | 1.1 - Determine Lot Size
label | Ref docs - N/A
label | Acceptance criteria - What is the lot size?
textbox | Acceptance |  |  | m2
label | Maximum lot size = See pre-approved lot maps
label | Freq - N/A
label | Key - S
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Work Lot Map
checkpoint | 1.2 - Survey Setout
label | Ref docs - IFC Drawings
label | Acceptance criteria - Has the work area been set out for line and level?
button | Acceptance | Yes,No,N/A
label | Freq - Prior to start of Works
label | Key - W
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Photo
checkpoint | 1.3 - Material Classification & Source
label | Ref docs - MRH/00/P/0 0- PM/SPC/00 03 rev 3 page 55
label | Acceptance criteria - Is the correct material being used?
button | Acceptance | Yes,No,N/A
radio | Please select appropriate option: | Site Won,20mm Class 2,20mm Class 3,20mm Class 4
label | Freq - Prior to start of Works
label | Key - W
label | Resp - SE
label | SGJV Key - H
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Test Report/Material certificate
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Previous pavement conformance
checkpoint | 2.1 - Conformance of Previous Layer
label | Ref docs - MRH/A0/B/0 0- CV/DWG00 40
label | Acceptance criteria - Has the previous layer passed acceptance criteria?
button | Acceptance | Yes,No,N/A
label | Freq - Each Lot
label | Key - W
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Refer to ITP for previous layer
section | 3.0 Placement of pavement
checkpoint | 3.1 - Placement
label | Ref docs - IFC Drawings MRH/A0/B/0 0- CV/DWG00 40
label | Acceptance criteria - Has the fill been placed in a maximum compacted layer as outlined below?
label | ○ Maximum Layer Depth: 200mm
button | Acceptance | Yes,No,N/A
label | Freq - Each Lot
label | Key - S
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Photo
checkpoint | 3.2 - Moisture
label | Ref docs - MRH/A0/B/0 0- CV/DWG00 40
label | Acceptance criteria - Has the material maintained at optimum moisture content (>85%), with additional water being added if required during compaction?
button | Acceptance | Yes,No,N/A
label | Freq - Each Lot
label | Key - S
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Photo
checkpoint | 3.3 - Compaction
label | Ref docs - IFC Drawings MRH/A0/B/0 0- CV/DWG00 40
label | Acceptance criteria - Has the layer been adequately compacted achieving a mean value density ratio of:
label | – Lower Subbase: 98% Std
label | – Upper Subbase: 95% Mod
label | ○ 3 x tests to be conducted per compacted layer per approved lot map.
button | Acceptance | Yes,No,N/A
label | Freq - Each Lot
label | Key - W
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Compaction test results
checkpoint | 3.4 - Test Rolling
label | Ref docs - MRH/A0/B/0 0- CV/DWG00 40
label | Acceptance criteria - Does the layer withstand test rolling without visible deformation of springing?
textbox | List attendees:
button | Acceptance | Yes,No,N/A
label | If ‘no’, please see sections 3.5 and 3.6. If ‘yes’, proceed to section 4.0.
label | Freq - Each Lot
label | Key - W
label | Resp - SE
label | SGJV Key - H
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Photo
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Identification of soft, wet or unstable material
label | Ref docs - N/A
label | Acceptance criteria - What quantity of soft, wet or unstable material is present?
textbox | Acceptance |  |  | m
label | Freq - As required
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Photo
checkpoint | 3.6 - Treatment of unsuitable material
label | Ref docs - IFC Drawings
label | Acceptance criteria - Has rectification process been submitted for review?
label | ○ What was the rectification process used?
button | Acceptance | Yes,No,N/A
textbox | Process Used:
label | Freq - As required
label | Key - S
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Photo
section | 4.0 Pavement conformance
checkpoint | 4.1 - Pavement Finish
label | Ref docs - IFC Drawings
label | Acceptance criteria - Has the pavement course been finished to a smooth and uniform surface?
button | Acceptance | Yes,No,N/A
label | Freq - Once
label | Key - W
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Photo
checkpoint | 4.2 - Width & Alignment
label | Ref docs - IFC Drawings
label | Acceptance criteria - Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings?
button | Acceptance | Yes,No,N/A
label | Freq - Each Lot
label | Key - W
label | Resp - SE
label | SGJV Key - S
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Photo
checkpoint | 4.3 - Surface Level of Pavement Courses
label | Ref docs - IFC Drawings
label | Acceptance criteria - Has the prepared layer been surveyed in accordance with and verifying specified requirements?
label | ○ All crushed rock layers: Mean Range: +10mm to - 10mm
button | Acceptance | Yes,No,N/A
label | Freq - Each Lot
label | Key - H
label | Resp - SE
label | SGJV Key - H
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | As-Built Reports
holdpoint | AUTHORITY HOLDPOINT