## Bituminous Seal Coat
|  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | Lot Reference number:
|  |  |  | Project Name: 5126 Takitimu Street, Whenuapai, Auckland |  |  |  |  | Date submitted: dd-mm-yyyy
|  |  |  | Construction Process: Chipseal Membrane - G5 on 1 l/m2 residual (CAT60) |  |  |  |  | Prepared By:
Client's Rep.Engineer |  | Contractor: Vuksich & Borich (NZ) Limited |  | Specification: as referenced |  |  |  |  | Approved By:
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Conducted or Accepted/Approved by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) | Inspection / Test method |  |  |  |  | Colas | Designer | Clients Rep | Date | Comment on compliance with ITP correpsondence etc
Sealing
7 | Seal Design(s) | Seal designs for Chipseal Membrane | H | 1 seal design per seal application type for the project | Review and acceptance by Client Rep | Membrane requirements as per project specifications and NZTA specifications | Seal Design Report/ Statement justifying stone size and residual binder rate | Designer/Colas | As per drawings and specifications usually but if not specified Colas to justify design chip size and application rate, as per NZTA M10 minimum 1 l/m2 residual but used G5 not G4 |  |  |  |  | Justify via communication as per Cl 9.3.2 Chip Seal used minimum 1 l/m2 residual but changed from G4 to G5 a smaller chip as asphalt surface very thin being a 30mm DG7
7.1.1 | Check raw materials | Sealing Aggregates | M | 1 per source stockpile | Source Properties | NZTA M06 / RNZ 9805:2009 as per G5 | Certificate in contractor's site folder | Colas/ Quarry | Test certificates issued to the Designer at least 10 days prior to sealing
7.1.2 |  | Sealing Aggregates | M | 1 per source stockpile | Production Properties | NZTA M06 / RNZ 9805:2009 as per G5 | Certificate in contractor's site folder | Colas/ Quarry
7.1.3 |  | Adhesion Agents | M | Prior to use |  | NZTA M06 / NZTA M13 | Certificate in contractor's site folder | Colas/ Bitumen Supplier | Only required if adhesion agent used.
7.1.4 |  | Audit samples taken from truck on site | M | 20 kg for each sealing day for each chip size used | N/A | Stored in a sealed plastic bag in a covered environment | Labelled bags date/time sampled and location and chip type | Colas | Retain for testing if required
7.2.1 | Pre-Seal requirements | Weather suitable for sealing | H | The day before sealing and 2 hours prior to sealing | Contractor visual on site and weather forecasts | Confirm weather conditions are free of rain during sealing and for next 24 hours and surface to be sealed is visually dry and free of surface water' | Contractor's site diary and email or verbal confirmation weather ok for sealing | Contractor
7.2.2 |  | Sweep and clean finished basecourse surface prior to sealing | W | 100% of area swept and cleaned | Observation area was swept | Surface is broomed and clean of all dirt, dust, aggregate fines, surface should present a tight mosaic pattern of large aggregate tightly bonded | Site diary and photos | Colas
7.2.3 |  | Visual inspection of surface to be sealed | H | per sealing schedule. 1 Lot = 1 day's production and < 1500m2 | Visual Inspection | NZTA B02 - a tight mosaic pattern of large aggregate tightly bonded | Contractor's site diary, Photos of site every 20meters | Contractor/Clients Rep | The surface finish, line and level is checked by Contractor/Designer and approved by Client Rep immediately prior to sealing, for surface levels important there is room for asphalt surface taking into account a 5mm thick chipseal and top of kerb
7.2.4 |  | Surface Shape | H | every 20m | Measurement | < 5mm using 5m straight edge and no areas that can pond water | Worksheet | Colas | Agree with Contractor and Client Rep on expected finished asphalt surface smoothness based on surface smoothness prior to sealing on granular base
7.2.5 |  | Surface Levels | H | every 20m | Measurement | +5mm, - 10mm | Survey | Colas | Agree with Contractor and Client Rep on expected finished asphalt surface smoothness based on surface smoothness prior to sealing on granular base
7.2.6 |  | Dry back Moisture Content | H | 9 per Lot | NZS 4407.4.2.1 | DOS ≤ 80% preferably ≤ 70% as per NTZA B:02 spec using NDM | IANZ Report | Contractor/Clients Rep | Check moisture content of granular base - Will be completed by Main Contractor whom will have Enginners approval sealing can proceed
7.2.7 |  | E/2 Certificate Bitumen Sprayer | H | Once per project | RNZ E/2 | Current compliant E/2 certificate from CCNZ less than 12 months old | E/2 Cert | Colas
7.3.1 | Sealing | Bitumen / Bitumen Emulsion for Chip Sealing | M | Tested per batch at manufacturing location prior to delivery (test cert for tanker load of bitumen) | Penetration grade testing | NZTA M01 - Tables 1, 2, 3 and 5 | Certificate in contractor's site folder | Colas/ Bitumen Supplier | Bitumen supplier to supply batch number and test certificate for compliance, for this project note batch number used.
7.3.2 |  |  | M |  | Durability | NZTA M01 - Table 5 | Certificate in contractor's site folder | Colas/ Bitumen Supplier | Bitumen supplier to supply batch number and test certificate for compliance, for this project note batch number used.
7.3.3 |  | Spraying Temperature (Bitumen only) | W | Ongoing with non-going heat sensing gauge | Non-contact heat sensing gun | NZTA P03 - Table 2 | ITP | Colas | Infrared guage record in notebook on site
7.3.4 |  | Residual Bitumen Application Rate | M | Reconcile day's production | Dockets vs Area | ± 0.1 L/m2 | Site diary | Colas | Need record for each run and include design target
7.3.5 |  | Chip Application Rate | M | Each Days Sealing visual 100% of Area | Visual Inspection | For single coat seals the spread rate of the chips shall be such that when fully rolled it will be one stone thick, closely packed shoulder to shoulder, with the individual stones lying flat | Site diary/ Photos | Colas / Client's Rep | Visually ok no excess chip, better to be slightly less than too much
7.3.6 |  | Rolling - Pneumatic | W | Activity over 100% of area | Observe | Confirm minimum two passes of pneumatic roller of chipseal completed and chips lying flat firmly in place | Site diary | Colas
7.3.7 |  | Sweeping | W | Activity over 100% of area | Observe | Confirm area swept and cleaned of no loose chip and remove chip outside areas | Site diary | Colas
7.4 | Approval of the days sealing and amendments to sealing method/design if required | Client Rep approves the days sealing and agrees a revised dealing design/methodology or Holds /Stops sealing until any concerns, issues and non-comformances are corrected | H | Each days sealing | Review of the days results and sealing activity plus visual inspection | Acceptance by Designer and Client Rep | Daily work Log | Contractor/ Client Rep | This item is to sign and agree the days sealing is acceptable and if necessary stop sealing until issues and non-conformances are resolved with the Client Rep before proceeding to the next days sealing.
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Client. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Client. Rep.
[7 empty] | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Client. Rep.
Designer's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________
Client's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________

## AC Mix Design
|  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | Lot Reference number:
|  |  |  | Project Name: 5126 Takitimu Street, Whenuapai, Auckland |  |  |  |  | Date submitted: dd-mm-yyyy
|  |  |  | Construction Process: Asphalt Mix Design JMF approval prior to Paving |  |  |  |  | Prepared By:
Client's Rep. |  | Contractor: Vuksich & Borich (NZ) Limited |  | Specification: as referenced |  |  |  |  | Approved By:
Spec. section | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Conducted or Accepted/Approved by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) | Inspection / Test method |  |  |  |  | Colas | Designer | Clients Rep | Date
8 | Asphalt Constituents
8.0.1 | Course Aggregates | Crushing resistance | M | Last three results with one test < 3 months old | NZS 4407 Test 3.10 | ≥ 200kN [NZTA M/10] | IANZ accredited test cert | Colas/ Quarry Owner
8.0.2 |  | Weathering Quality Index | M | Last three results with one test < 3 months old | NZS 4407 Test 3.11 | AA or BA [NZTA M/10] | IANZ accredited test cert | Colas/ Quarry Owner
8.0.3 |  | Single Broken Faces | M | Last three results with one test < 3 months old | NZS 4407 Test 3.14 | ≥ 98% [NZTA M/10] | IANZ accredited test cert | Colas/ Quarry Owner | Not needed from crushed rock quarries
8.0.4 |  | Two Broken Faces | M | Last three results with one test < 3 months old | NZS 4407 Test 3.14 | ≥ 60% [NZTA M/10] | IANZ accredited test cert | Colas/ Quarry Owner | Not needed from crushed rock quarries
8.0.5 |  | Polished Stone Value (AC14 surfacing only) | M | One test < 18 months old | BS EN 1097 Part 8 | As per specific project requirements PSV >=54 | IANZ accredited test cert | Colas/ Quarry Owner | Last result from Stevenson Drury was 56 PSV
8.0.6 |  | Los Angeles Abrasion Loss | M | Last result < 18 months old | NZS 4407 Test 3.12 | Report Value | IANZ accredited test cert | Colas/ Quarry Owner
8.0.7 |  | Wet/Dry Strength variation | M | Last result < 18 months old | AS 2558 Part 5 | Report Value | IANZ accredited test cert | Colas/ Quarry Owner
8.0.8 |  | Water Absorbtion | M | Last result < 18 months old | AS 1141 or ASTM C127 | Report Value | IANZ accredited test cert | Colas/ Quarry Owner
8.0.9 | Fine Aggregates | Crushing resistance | M | Last three results with one test < 3 months old | NZS 4407 Test 3.10 | ≥ 200kN [NZTA M/10] | IANZ accredited test cert | Colas/ Quarry Owner
8.0.10 |  | Sand Equivalent | M | Last three results with one test < 3 months old | NZS 4407 Test 3.6 | ≥ 35 [NZTA M/10] | IANZ accredited test cert | Colas/ Quarry Owner
8.0.11 |  | Clay Index | M | Last three results with one test < 3 months old | NZS 4407 Test 3.5 | ≤ 3 [NZTA M/10] | IANZ accredited test cert | Colas/ Quarry Owner
8.0.12 |  | Water Absorbtion | M | Last three results with one test < 3 months old | AS 1141 or ASTM C127 | Report Value | IANZ accredited test cert | Colas/ Quarry Owner
8.0.13 |  | Degradation factor | M | Last three results with one test < 3 months old | AS 1141.25.3 | Report Value | IANZ accredited test cert | Colas/ Quarry Owner
8.0.14 | Mineral Filler | Particle Size Distribution | M | Last three results with one test < 3 months old | NZS 4407 | Table 2.4 NZTA M/10 | IANZ accredited test cert | Colas/ Quarry Owner | Only needed if mineral filler used in Asphalt Mix
8.0.15 | Binder | Flash point | M | 1 per imported batch of bitumen | AASHTO T48 or ASTM D92 | ≥ 230 ⁰C [NZTA M1-A] | IANZ accredited test cert | Colas/ Bitumen Supplier | Test certficate supplied by bitumen supplier
8.0.16 |  | Viscosity at 135 ⁰C | M | 1 per imported batch of bitumen | AASHTO T316 or ASTM D4402 | ≤ 3 Pa.s [NZTA M1-A] | IANZ accredited test cert | Colas/ Bitumen Supplier
8.0.17 |  | G*/sinδ at 64⁰C @ 10 rad/s | M | 1 per imported batch of bitumen | AASHTO T315 or ASTM D7175 | ≥ 1.00 kPa [NZTA M1-A] | IANZ accredited test cert | Colas/ Bitumen Supplier
8.0.18 |  | RTFOF residue: Mass change (+ve and -ve) | M | 1 per imported batch of bitumen | AASHTO T240 or ASTM D2872 | ≤ 1.00% [NZTA M1-A] | IANZ accredited test cert | Colas/ Bitumen Supplier
8.0.19 |  | Jnr3.2 at 64⁰C | M | 1 per imported batch of bitumen | AASHTO T350 | ≤ 4.5 kPa (S); ≤ 2.0 kPa (H); ≤ 1.0 kPa (V) ≤ 0.5 kPa (E) [NZTA M1-A] | IANZ accredited test cert | Colas/ Bitumen Supplier
8.0.20 |  | Jnr3.2 at 64⁰C | M | 1 per imported batch of bitumen | AASHTO T350 | Report Value | IANZ accredited test cert | Colas/ Bitumen Supplier
8.0.21 |  | PAV residue (aging temp of 100⁰C) G*/sinδ at 28⁰C @ 10 rad/s | M | 1 per imported batch of bitumen | AASHTO T315 or ASTM D7175 | ≤ 5000 kPa (S); ≤ 6000 kPa (H, V, E) [NZTA m1-A] | IANZ accredited test cert | Colas/ Bitumen Supplier
8.0.22 |  | S at -6⁰C @ 60s | M | 1 per imported batch of bitumen | AASHTO T313 or ASTM D6648 | ≤ 6000 kPa [NZTA M1-A] | IANZ accredited test cert | Colas/ Bitumen Supplier
8.0.23 |  | m-value at -6⁰C @ 60s | M | 1 per imported batch of bitumen | AASHTO T313 or ASTM D6648 | ≥ 0.300 [NZTA 1-A] | IANZ accredited test cert | Colas/ Bitumen Supplier
8.0.24 |  | Failure strain at -6⁰C @ 1.0 mm/min | M | 1 per imported batch of bitumen | AASHTO T314 or ASTM D6723 | ≥ 1.0% [NZTA m1-A] | IANZ accredited test cert | Colas/ Bitumen Supplier
8.1 | Asphalt Mix Design -Laboratory Made
8.1.1 | Asphalt mix - Lab Made Mix Design | Mix design report and JMF | H | 1 per site location | Meets Requirements of NZTA M/10 and if appropriate approved by Auckland Transport | NZTA M/10, VMA, BFI, AirVoids, etc | Mix Design report | Colas | Mix Design report including all testing outlined in this ITP to be issued to the Engineers Rep at least 10 days prior to paving
8.1.2 |  | TSR - Tensile Strength Ratio | H | 1 Result in last 24 months (can be production sample) | ASTM D4867 | ≥ 75% [NZTA M/10] | IANZ accredited test cert | Colas
8.1.3 |  | Modulus (Indirect Matta Resilient Modulus) | W | 1 Result in last 24 months (can be production sample) | AS 2891.13.1 | None to report for use by Pavement Designer | IANZ accredited test cert | Colas | Not required for compliance report of interest only
8.1.3 |  | Wheel Tracking (only for H and V.H DGA mixes) | H | 1 Result in last 24 months (can be production sample) | AGPT/T231 | ≤ 6.0mm [NZTA M/10] | IANZ accredited test cert | Colas | Not needed for DG7 and DG10 mixes
8.2 | Asphalt Mix Design - 6 Monthly Validation and Refinement from Production Mix and Lab and Field Airvoids
8.2.1 | Asphalt Production Mix to Validate and Refine/Adjust Lab JMF | Aggregate Particle Size Distribution & Binder Content | H | Last three results with one test < 3 months old | NZS 4407 Test 3.8.1 | As per Lab JMF (BFI, Bitumen Content and Gradings) compliant with NZTA M/10 | IANZ accredited test cert | Colas
8.2.2 |  | Lab Compacted Mix Air Voids | H | Last three results with one test < 3 months old | Gyratory Servopac or | Table 3.4 [NZTA M/10) Light = 4% Voids 40 cycles Medium, Heavy = 4% Voids 80/120 cycles V.Heavy = 5% Voids 120 cycles | IANZ accredited test cert | Colas
8.2.3 |  | Extracted Core Field and/or NDM Air Voids | H | One site less than 12 months old | NZTA M10 | 9.9 [NZTA M/10) | IANZ accredited test cert | Colas | Not needed for DG7 and DG10 mixes
8.2.4 |  | VMA, BFI calculated | H | One site less than 12 months old | NZTA M10 | VMA and BFI as per NZTA M10 for mix type | Calculated correctly from IANZ test results | Colas
8.2.5 |  | JMF adjustment from production and field air voids results | H | Once per year | NZTA M10 | Detailing justification from production and field results (namely lab and field air voids) a proposed new refined JMF varying within allowable limits of lab jmf as per M10. Generally only target binder content is adjusted up and down from lab JMF based on field air voids compliance | Mix Design Re-validation report | Colas
8.2.6 |  | Agreement of new refined JMF from Production Mix | H | Once per year | NZTA M10 | New refined JMF submitted to Designer and Client Rep for acceptance | Approval or new JMF | Colas / Client Rep | If adjustments to JMF needed this will be submitted to Engineer for apoproval and to support this AT approval will also be submitted
8.2.7
8.3 | Asphalt Mix Design Acceptance
8.3.1 | Aspahlt Mix Acceptance | Assessment of all test results for conformity and revised JMF based on Production and Field Results | H | For each mix used on the project | Review | Reporting of any non-conforming results to Designer via NCR | NCR - Email Approval | Colas/Clients Rep | Results and reports for revalidation of mix design and associated AT approval will be submitted
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Client. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Client. Rep.
[7 empty] | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Client. Rep.
Designer's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________
Client's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________

## AC Placement
|  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | Lot Reference number:
|  |  |  | Project Name: 5126 Takitimu Street, Whenuapai, Auckland |  |  |  |  | Date submitted: dd-mm-yyyy
|  |  |  | Construction Process: Asphalt Mix Placement |  |  |  |  | Prepared By:
Client's Rep. |  | Contractor: Vuksich & Borich (NZ) Limited |  | Specification: as referenced |  |  |  |  | Approved By:
Spec. section | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) | Inspection / Test method |  |  |  |  | Colas | Contractor | Date
9 | Asphalt Paving
9.1 | Pre-paving inspection
9.1.1 | Pre-paving inspection | Weather suitable for paving | H | The day before paving and 2 hours prior to paving | Contractor visual on site and weather forecasts | Confirm weather conditions are free of rain and not foggy during sealing and for next 24 hours and surface to be paved is visually dry and free of surface water' | Contractor's site diary and email or verbal confirmation weather ok for sealing | Colas / Client Rep
9.1.2 |  | Temperature of underlying base prior to paving asphalt is >=7 degrees | H | 4 randomly located measurements in the shade | Infra Red Temperature Gun | Temperature on3 out of 4 measurements > 7 degrees on underlying base prior to asphalt | Contractors site diary (Photo of temperature gun reading) | Colas / Client Rep
9.1.3 |  | Surface Shape | H | every 20m | Measurement | < 5mm using 5m straight edge and no areas that can pond water | Worksheet | Colas
9.1.4 |  | Surface Levels | H | every 20m | Measurement | +5mm, - 10mm | Survey | Colas
9.1.5 |  | Visual inspection of surface to be sealed | H | per paving schedule. 1 Lot = 1 day's production and < 1500m2 | Visual Inspection | If surface is sealed or asphalt then surface must be clean and free of any dust and ponding water. | Contractor's site diary | Colas / Client Rep | The surface finish, line and level, condition is checked by clients Rep. immediately prior to paving
9.1.6 |  | Acceptance of Asphalt Paver | H | Once per project | Specifications and level controls for Paver | Specifications and level controls for levels on asphalt paver submitted and accepted by Client Rep and Contractor to demonstrate the desired slope of the surface is within plus or minus 0.1% | Communications with Contractor and Client Rep on Paver Equipment and Levels controls used | Colas / Contractor/ Client Rep | See Cl2 determine what current method used on Paver to control smoothness and transverse slope and add in acceptance criteria
9.1.6 |  | Certified full length weigh bridge | H | Once per project | Certificate of Calibration of full length weigh bridge | Accurate and passes certification for weighbridge by independent weighbridge certifier | Weigh Bridge Certificate | Colas
9.2 | Production
9.2.1 | Production mix at Asphalt Plant | Particle Size Distribution | M | 1 per day and the 1 per 200 t at asphalt plant | Approved JMF and NZTA M10 |  | IANZ accredited test cert | Colas
9.2.2 |  | Binder Content | M | 1 per day and the 1 per 200 t at asphalt plant | Approved JMF and NZTA M10 |  | IANZ accredited test cert | Colas
9.2.3 |  | Max. Specific Gravity | M | 1 per day and the 1 per 600 t at asphalt plant | Approved JMF and NZTA M10 |  | IANZ accredited test cert | Colas
9.2.4 |  | Lab Air Voids Gyro | M | 1 per project or 1 per 600 tonnes | Approved JMF and NZTA M10 |  | IANZ accredited test cert | Colas
9.2.5 |  | Mix discharge temperature | M | 1 per day and the 1 per 200 t at asphalt plant | Approved JMF and NZTA M10 | >158 degrees as per M10 Notes for S grade binder PG64S | Diary Records at Plant | Colas
9.3 | Paving on site
9.3.1 | Planning location of paving runs and joints | Determine joint locations and paving runs as acceptable by Client Rep, also agree areas that need to be hand layed | M | Each paver run | Best Practice/ Drawings/ Visual | As agreed by Client Rep | Field diary | Colas
9.3.2 | Cold Joints Cut Back | Locate cold joints and cut back prior to adjacent paving | M | Each paver run | Best Practice/ Visual | Visually accepted finished joints (almost invisible joints) | Field diary/ Photos | Colas
9.3.3 | Paving and compacting mix on site | Record temperature of mix in paver, on mat start of rolling and on mat end of rolling | M | Each paver run | NZTA M10/ Best Practice | Temperatures >90 degrees (minimum compaction); First delivered in paver mix temp >130 deg - note departure from NZTA M10 Notes that require 146 deg compaction temperature | Field diary | Colas | Experience found for thin asphalt mix cools very quickly but can still be succesfully compacted on site
9.3.4 |  | Record rolling methodology, types of rollers, order, vibe and static and number of passes | M | Each paver run | Best Practice | No Nuke Plateau and/or NDM Density and approved by Area Manager as confirm best practice has be used to achieve compaction on site | Field diary | Colas
9.3.5 |  | NDM or No Nuke Density Measurements on site for Air Voids | M | Each paver run | NZTA M10 | At 10m increments using NDM if required as per NZTA M10 for asphalt mixes >35mm thick | IANZ accredited test cert | Colas | If NDM or No Nuke used then evidence of apropriate offset is needed found from correlations between air voids from NDM or No Nuke and extracted core air voids
9.3.6 |  | Extracted Core Air Voids if required | M | Each days production 8 on mat and 3 on joints | NZTA M10 | Air voids requirements as per NZTA M10. Cores not required as per NZTA M10 for asphalt thickness < 35mm | IANZ accredited test cert | Colas | Often for surfacing mixes cores are not allowed due to visually being unacceptable and thus use NDM and NoNule methods above
9.3.7 |  | Thickness | M | Dipstick and field report each truck load | Record | As per design requirements | Field report | Colas
9.3.8 |  | Layer Width/ Length and Area per truck | M | Field report each truck load | Record | As per design requirements | Field report | Colas
9.3.9 |  | Surface Shape | H | every 20m | Measurement | < 6mm using 3m straight edge and no areas that can pond water | Worksheet | Colas | Or as agreed prior to sealing in terms of what practically can be achieved based on smoothness of granular base and kerb alignment
9.3.10 |  | Surface Levels | H | every 20m | Measurement | +5mm, - 5mm | Survey | Contractor/ Colas
9.3.11
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Client. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Client. Rep.
[7 empty] | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Client. Rep.
Designer's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________
Client's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________