## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Bituminous Seal Coat | itp |  |  |  |  | ITP - Bituminous Seal Coat
section | Sealing
checkpoint | 7 - Seal Design(s)
label | Detail of Activity - Seal designs for Chipseal Membrane
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 seal design per seal application type for the project
label | Inspection / Test method - Review and acceptance by Client Rep
label | Acceptance Criteria - Membrane requirements as per project specifications and NZTA specifications
label | Record documents - Seal Design Report/ Statement justifying stone size and residual binder rate
label | Responsibility - Designer/Colas
label | Comments - As per drawings and specifications usually but if not specified Colas to justify design chip size and application rate, as per NZTA M10 minimum 1 l/m2 residual but used G5 not G4
holdpoint | HOLD POINT
checkpoint | 7.1.1 - Check raw materials
label | Detail of Activity - Sealing Aggregates
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per source stockpile
label | Inspection / Test method - Source Properties
label | Acceptance Criteria - NZTA M06 / RNZ 9805:2009 as per G5
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Colas/ Quarry
label | Comments - Test certificates issued to the Designer at least 10 days prior to sealing
checkpoint | 7.1.2 - Check raw materials
label | Detail of Activity - Sealing Aggregates
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per source stockpile
label | Inspection / Test method - Production Properties
label | Acceptance Criteria - NZTA M06 / RNZ 9805:2009 as per G5
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Colas/ Quarry
checkpoint | 7.1.3 - Check raw materials
label | Detail of Activity - Adhesion Agents
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to use
label | Acceptance Criteria - NZTA M06 / NZTA M13
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Colas/ Bitumen Supplier
label | Comments - Only required if adhesion agent used.
checkpoint | 7.1.4 - Check raw materials
label | Detail of Activity - Audit samples taken from truck on site
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 20 kg for each sealing day for each chip size used
label | Inspection / Test method - N/A
label | Acceptance Criteria - Stored in a sealed plastic bag in a covered environment
label | Record documents - Labelled bags date/time sampled and location and chip type
label | Responsibility - Colas
label | Comments - Retain for testing if required
checkpoint | 7.2.1 - Pre-Seal requirements
label | Detail of Activity - Weather suitable for sealing
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - The day before sealing and 2 hours prior to sealing
label | Inspection / Test method - Contractor visual on site and weather forecasts
label | Acceptance Criteria - Confirm weather conditions are free of rain during sealing and for next 24 hours and surface to be sealed is visually dry and free of surface water'
label | Record documents - Contractor's site diary and email or verbal confirmation weather ok for sealing
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 7.2.2 - Pre-Seal requirements
label | Detail of Activity - Sweep and clean finished basecourse surface prior to sealing
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 100% of area swept and cleaned
label | Inspection / Test method - Observation area was swept
label | Acceptance Criteria - Surface is broomed and clean of all dirt, dust, aggregate fines, surface should present a tight mosaic pattern of large aggregate tightly bonded
label | Record documents - Site diary and photos
label | Responsibility - Colas
checkpoint | 7.2.3 - Pre-Seal requirements
label | Detail of Activity - Visual inspection of surface to be sealed
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - per sealing schedule.
label | ○ 1 Lot = 1 day's production and < 1500m2
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - NZTA B02 - a tight mosaic pattern of large aggregate tightly bonded
label | Record documents - Contractor's site diary, Photos of site every 20meters
label | Responsibility - Contractor/Clients Rep
label | Comments - The surface finish, line and level is checked by Contractor/Designer and approved by Client Rep immediately prior to sealing, for surface levels important there is room for asphalt surface taking into account a 5mm thick chipseal and top of kerb
holdpoint | HOLD POINT
checkpoint | 7.2.4 - Pre-Seal requirements
label | Detail of Activity - Surface Shape
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - < 5mm using 5m straight edge and no areas that can pond water
label | Record documents - Worksheet
label | Responsibility - Colas
label | Comments - Agree with Contractor and Client Rep on expected finished asphalt surface smoothness based on surface smoothness prior to sealing on granular base
holdpoint | HOLD POINT
checkpoint | 7.2.5 - Pre-Seal requirements
label | Detail of Activity - Surface Levels
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - +5mm, - 10mm
label | Record documents - Survey
label | Responsibility - Colas
label | Comments - Agree with Contractor and Client Rep on expected finished asphalt surface smoothness based on surface smoothness prior to sealing on granular base
holdpoint | HOLD POINT
checkpoint | 7.2.6 - Pre-Seal requirements
label | Detail of Activity - Dry back Moisture Content
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 9 per Lot
label | Inspection / Test method - NZS 4407.4.2.1
label | Acceptance Criteria - DOS ≤ 80% preferably ≤ 70% as per NTZA B:02 spec using NDM
label | Record documents - IANZ Report
label | Responsibility - Contractor/Clients Rep
label | Comments - Check moisture content of granular base - Will be completed by Main Contractor whom will have Enginners approval sealing can proceed
holdpoint | HOLD POINT
checkpoint | 7.2.7 - Pre-Seal requirements
label | Detail of Activity - E/2 Certificate Bitumen Sprayer
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Once per project
label | Inspection / Test method - RNZ E/2
label | Acceptance Criteria - Current compliant E/2 certificate from CCNZ less than 12 months old
label | Record documents - E/2 Cert
label | Responsibility - Colas
holdpoint | HOLD POINT
checkpoint | 7.3.1 - Sealing
label | Detail of Activity - Bitumen / Bitumen Emulsion for Chip Sealing
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Tested per batch at manufacturing location prior to delivery (test cert for tanker load of bitumen)
label | Inspection / Test method - Penetration grade testing
label | Acceptance Criteria - NZTA M01 - Tables 1, 2, 3 and 5
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Colas/ Bitumen Supplier
label | Comments - Bitumen supplier to supply batch number and test certificate for compliance, for this project note batch number used.
checkpoint | 7.3.2 - Sealing
label | Detail of Activity - Bitumen / Bitumen Emulsion for Chip Sealing
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Tested per batch at manufacturing location prior to delivery (test cert for tanker load of bitumen)
label | Inspection / Test method - Durability
label | Acceptance Criteria - NZTA M01 - Table 5
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Colas/ Bitumen Supplier
label | Comments - Bitumen supplier to supply batch number and test certificate for compliance, for this project note batch number used.
checkpoint | 7.3.3 - Sealing
label | Detail of Activity - Spraying Temperature (Bitumen only)
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Ongoing with non-going heat sensing gauge
label | Inspection / Test method - Non-contact heat sensing gun
label | Acceptance Criteria - NZTA P03 - Table 2
label | Record documents - ITP
label | Responsibility - Colas
label | Comments - Infrared guage record in notebook on site
checkpoint | 7.3.4 - Sealing
label | Detail of Activity - Residual Bitumen Application Rate
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Reconcile day's production
label | Inspection / Test method - Dockets vs Area
label | Acceptance Criteria - ± 0.1 L/m2
label | Record documents - Site diary
label | Responsibility - Colas
label | Comments - Need record for each run and include design target
checkpoint | 7.3.5 - Sealing
label | Detail of Activity - Chip Application Rate
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each Days Sealing visual 100% of Area
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - For single coat seals the spread rate of the chips shall be such that when fully rolled it will be one stone thick, closely packed shoulder to shoulder, with the individual stones lying flat
label | Record documents - Site diary/ Photos
label | Responsibility - Colas / Client's Rep
label | Comments - Visually ok no excess chip, better to be slightly less than too much
checkpoint | 7.3.6 - Sealing
label | Detail of Activity - Rolling - Pneumatic
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Activity over 100% of area
label | Inspection / Test method - Observe
label | Acceptance Criteria - Confirm minimum two passes of pneumatic roller of chipseal completed and chips lying flat firmly in place
label | Record documents - Site diary
label | Responsibility - Colas
checkpoint | 7.3.7 - Sealing
label | Detail of Activity - Sweeping
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Activity over 100% of area
label | Inspection / Test method - Observe
label | Acceptance Criteria - Confirm area swept and cleaned of no loose chip and remove chip outside areas
label | Record documents - Site diary
label | Responsibility - Colas
checkpoint | 7.4 - Approval of the days sealing and amendments to sealing method/design if required
label | Detail of Activity - Client Rep approves the days sealing and agrees a revised dealing design/methodology or Holds /Stops sealing until any concerns, issues and non-comformances are corrected
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each days sealing
label | Inspection / Test method - Review of the days results and sealing activity plus visual inspection
label | Acceptance Criteria - Acceptance by Designer and Client Rep
label | Record documents - Daily work Log
label | Responsibility - Contractor/ Client Rep
label | Comments - This item is to sign and agree the days sealing is acceptable and if necessary stop sealing until issues and non-conformances are resolved with the Client Rep before proceeding to the next days sealing.
holdpoint | HOLD POINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Designer's Rep Name:
textbox | Client's Rep. Name:
date | Date:
signoff | Sign ITP
checklist | ITP - AC Mix Design | itp |  |  |  |  | ITP - AC Mix Design
section | 8.0 - Asphalt Constituents
checkpoint | 8.0.1 - Course Aggregates
label | Detail of Activity - Crushing resistance
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Last three results with one test < 3 months old
label | Inspection / Test method - NZS 4407 Test 3.10
label | Acceptance Criteria - ≥ 200kN [NZTA M/10]
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Quarry Owner
checkpoint | 8.0.2 - Course Aggregates
label | Detail of Activity - Weathering Quality Index
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Last three results with one test < 3 months old
label | Inspection / Test method - NZS 4407 Test 3.11
label | Acceptance Criteria - AA or BA [NZTA M/10]
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Quarry Owner
checkpoint | 8.0.3 - Course Aggregates
label | Detail of Activity - Single Broken Faces
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Last three results with one test < 3 months old
label | Inspection / Test method - NZS 4407 Test 3.14
label | Acceptance Criteria - ≥ 98% [NZTA M/10]
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Quarry Owner
label | Comments - Not needed from crushed rock quarries
checkpoint | 8.0.4 - Course Aggregates
label | Detail of Activity - Two Broken Faces
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Last three results with one test < 3 months old
label | Inspection / Test method - NZS 4407 Test 3.14
label | Acceptance Criteria - ≥ 60% [NZTA M/10]
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Quarry Owner
label | Comments - Not needed from crushed rock quarries
checkpoint | 8.0.5 - Course Aggregates
label | Detail of Activity - Polished Stone Value (AC14 surfacing only)
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - One test < 18 months old
label | Inspection / Test method - BS EN 1097 Part 8
label | Acceptance Criteria - As per specific project requirements PSV >=54
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Quarry Owner
label | Comments - Last result from Stevenson Drury was 56 PSV
checkpoint | 8.0.6 - Course Aggregates
label | Detail of Activity - Los Angeles Abrasion Loss
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Last result < 18 months old
label | Inspection / Test method - NZS 4407 Test 3.12
label | Acceptance Criteria - Report Value
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Quarry Owner
checkpoint | 8.0.7 - Course Aggregates
label | Detail of Activity - Wet/Dry Strength variation
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Last result < 18 months old
label | Inspection / Test method - AS 2558 Part 5
label | Acceptance Criteria - Report Value
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Quarry Owner
checkpoint | 8.0.8 - Course Aggregates
label | Detail of Activity - Water Absorbtion
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Last result < 18 months old
label | Inspection / Test method - AS 1141 or ASTM C127
label | Acceptance Criteria - Report Value
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Quarry Owner
checkpoint | 8.0.9 - Fine Aggregates
label | Detail of Activity - Crushing resistance
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Last three results with one test < 3 months old
label | Inspection / Test method - NZS 4407 Test 3.10
label | Acceptance Criteria - ≥ 200kN [NZTA M/10]
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Quarry Owner
checkpoint | 8.0.10 - Fine Aggregates
label | Detail of Activity - Sand Equivalent
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Last three results with one test < 3 months old
label | Inspection / Test method - NZS 4407 Test 3.6
label | Acceptance Criteria - ≥ 35 [NZTA M/10]
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Quarry Owner
checkpoint | 8.0.11 - Fine Aggregates
label | Detail of Activity - Clay Index
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Last three results with one test < 3 months old
label | Inspection / Test method - NZS 4407 Test 3.5
label | Acceptance Criteria - ≤ 3 [NZTA M/10]
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Quarry Owner
checkpoint | 8.0.12 - Fine Aggregates
label | Detail of Activity - Water Absorbtion
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Last three results with one test < 3 months old
label | Inspection / Test method - AS 1141 or ASTM C127
label | Acceptance Criteria - Report Value
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Quarry Owner
checkpoint | 8.0.13 - Fine Aggregates
label | Detail of Activity - Degradation factor
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Last three results with one test < 3 months old
label | Inspection / Test method - AS 1141.25.3
label | Acceptance Criteria - Report Value
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Quarry Owner
checkpoint | 8.0.14 - Mineral Filler
label | Detail of Activity - Particle Size Distribution
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Last three results with one test < 3 months old
label | Inspection / Test method - NZS 4407
label | Acceptance Criteria - Table 2.4 NZTA M/10
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Quarry Owner
label | Comments - Only needed if mineral filler used in Asphalt Mix
checkpoint | 8.0.15 - Binder
label | Detail of Activity - Flash point
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per imported batch of bitumen
label | Inspection / Test method - AASHTO T48 or ASTM D92
label | Acceptance Criteria - ≥ 230 ⁰C [NZTA M1-A]
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Bitumen Supplier
label | Comments - Test certficate supplied by bitumen supplier
checkpoint | 8.0.16 - Binder
label | Detail of Activity - Viscosity at 135 ⁰C
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per imported batch of bitumen
label | Inspection / Test method - AASHTO T316 or ASTM D4402
label | Acceptance Criteria - ≤ 3 Pa.s [NZTA M1-A]
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Bitumen Supplier
checkpoint | 8.0.17 - Binder
label | Detail of Activity - G*/sinδ at 64⁰C @ 10 rad/s
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per imported batch of bitumen
label | Inspection / Test method - AASHTO T315 or ASTM D7175
label | Acceptance Criteria - ≥ 1.00 kPa [NZTA M1-A]
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Bitumen Supplier
checkpoint | 8.0.18 - Binder
label | Detail of Activity - RTFOF residue: Mass change (+ve and -ve)
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per imported batch of bitumen
label | Inspection / Test method - AASHTO T240 or ASTM D2872
label | Acceptance Criteria - ≤ 1.00% [NZTA M1-A]
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Bitumen Supplier
checkpoint | 8.0.19 - Binder
label | Detail of Activity - Jnr3.2 at 64⁰C
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per imported batch of bitumen
label | Inspection / Test method - AASHTO T350
label | Acceptance Criteria - ≤ 4.5 kPa (S); ≤ 2.0 kPa (H); ≤ 1.0 kPa (V)
label | ○ ≤ 0.5 kPa (E) [NZTA M1-A]
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Bitumen Supplier
checkpoint | 8.0.20 - Binder
label | Detail of Activity - Jnr3.2 at 64⁰C
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per imported batch of bitumen
label | Inspection / Test method - AASHTO T350
label | Acceptance Criteria - Report Value
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Bitumen Supplier
checkpoint | 8.0.21 - Binder
label | Detail of Activity - PAV residue (aging temp of 100⁰C)
label | ○ G*/sinδ at 28⁰C @ 10 rad/s
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per imported batch of bitumen
label | Inspection / Test method - AASHTO T315 or ASTM D7175
label | Acceptance Criteria - ≤ 5000 kPa (S); ≤ 6000 kPa (H, V, E) [NZTA m1-A]
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Bitumen Supplier
checkpoint | 8.0.22 - Binder
label | Detail of Activity - S at -6⁰C @ 60s
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per imported batch of bitumen
label | Inspection / Test method - AASHTO T313 or ASTM D6648
label | Acceptance Criteria - ≤ 6000 kPa [NZTA M1-A]
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Bitumen Supplier
checkpoint | 8.0.23 - Binder
label | Detail of Activity - m-value at -6⁰C @ 60s
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per imported batch of bitumen
label | Inspection / Test method - AASHTO T313 or ASTM D6648
label | Acceptance Criteria - ≥ 0.300 [NZTA 1-A]
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Bitumen Supplier
checkpoint | 8.0.24 - Binder
label | Detail of Activity - Failure strain at -6⁰C @ 1.0 mm/min
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per imported batch of bitumen
label | Inspection / Test method - AASHTO T314 or ASTM D6723
label | Acceptance Criteria - ≥ 1.0% [NZTA m1-A]
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas/ Bitumen Supplier
section | 8.1 - Asphalt Mix Design -Laboratory Made
checkpoint | 8.1.1 - Asphalt mix - Lab Made Mix Design
label | Detail of Activity - Mix design report and JMF
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per site location
label | Inspection / Test method - Meets Requirements of NZTA M/10 and if appropriate approved by Auckland Transport
label | Acceptance Criteria - NZTA M/10, VMA, BFI, AirVoids, etc
label | Record documents - Mix Design report
label | Responsibility - Colas
label | Comments - Mix Design report including all testing outlined in this ITP to be issued to the Engineers Rep at least 10 days prior to paving
holdpoint | HOLD POINT
checkpoint | 8.1.2 - Asphalt mix - Lab Made Mix Design
label | Detail of Activity - TSR - Tensile Strength Ratio
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Result in last 24 months (can be production sample)
label | Inspection / Test method - ASTM D4867
label | Acceptance Criteria - ≥ 75% [NZTA M/10]
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas
holdpoint | HOLD POINT
checkpoint | 8.1.3 - Asphalt mix - Lab Made Mix Design
label | Detail of Activity - Modulus (Indirect Matta Resilient Modulus)
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Result in last 24 months (can be production sample)
label | Inspection / Test method - AS 2891.13.1
label | Acceptance Criteria - None to report for use by Pavement Designer
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas
label | Comments - Not required for compliance report of interest only
checkpoint | 8.1.3 - Asphalt mix - Lab Made Mix Design
label | Detail of Activity - Wheel Tracking (only for H and V.H DGA mixes)
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Result in last 24 months (can be production sample)
label | Inspection / Test method - AGPT/T231
label | Acceptance Criteria - ≤ 6.0mm [NZTA M/10]
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas
label | Comments - Not needed for DG7 and DG10 mixes
holdpoint | HOLD POINT
section | 8.2 - Asphalt Mix Design - 6 Monthly Validation and Refinement from Production Mix and Lab and Field Airvoids
checkpoint | 8.2.1 - Asphalt Production Mix to Validate and Refine/Adjust Lab JMF
label | Detail of Activity - Aggregate Particle Size Distribution & Binder Content
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Last three results with one test < 3 months old
label | Inspection / Test method - NZS 4407 Test 3.8.1
label | Acceptance Criteria - As per Lab JMF (BFI, Bitumen Content and Gradings) compliant with NZTA M/10
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas
holdpoint | HOLD POINT
checkpoint | 8.2.2 - Asphalt Production Mix to Validate and Refine/Adjust Lab JMF
label | Detail of Activity - Lab Compacted Mix Air Voids
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Last three results with one test < 3 months old
label | Inspection / Test method - Gyratory Servopac or
label | Acceptance Criteria - Table 3.4 [NZTA M/10)
label | ○ Light = 4% Voids 40 cycles
label | ○ Medium, Heavy = 4% Voids 80/120 cycles
label | ○ V.Heavy = 5% Voids 120 cycles
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas
holdpoint | HOLD POINT
checkpoint | 8.2.3 - Asphalt Production Mix to Validate and Refine/Adjust Lab JMF
label | Detail of Activity - Extracted Core Field and/or NDM Air Voids
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - One site less than 12 months old
label | Inspection / Test method - NZTA M10
label | Acceptance Criteria - 9.9 [NZTA M/10)
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas
label | Comments - Not needed for DG7 and DG10 mixes
holdpoint | HOLD POINT
checkpoint | 8.2.4 - Asphalt Production Mix to Validate and Refine/Adjust Lab JMF
label | Detail of Activity - VMA, BFI calculated
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - One site less than 12 months old
label | Inspection / Test method - NZTA M10
label | Acceptance Criteria - VMA and BFI as per NZTA M10 for mix type
label | Record documents - Calculated correctly from IANZ test results
label | Responsibility - Colas
checkpoint | 8.2.5 - Asphalt Production Mix to Validate and Refine/Adjust Lab JMF
label | Detail of Activity - JMF adjustment from production and field air voids results
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Once per year
label | Inspection / Test method - NZTA M10
label | Acceptance Criteria - Detailing justification from production and field results (namely lab and field air voids) a proposed new refined JMF varying within allowable limits of lab jmf as per M10. Generally only target binder content is adjusted up and down from lab JMF based on field air voids compliance
label | Record documents - Mix Design Re-validation report
label | Responsibility - Colas
holdpoint | HOLD POINT
checkpoint | 8.2.6 - Asphalt Production Mix to Validate and Refine/Adjust Lab JMF
label | Detail of Activity - Agreement of new refined JMF from Production Mix
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Once per year
label | Inspection / Test method - NZTA M10
label | Acceptance Criteria - New refined JMF submitted to Designer and Client Rep for acceptance
label | Record documents - Approval or new JMF
label | Responsibility - Colas / Client Rep
label | Comments - If adjustments to JMF needed this will be submitted to Engineer for apoproval and to support this AT approval will also be submitted
holdpoint | HOLD POINT
section | 8.3 - Asphalt Mix Design Acceptance
checkpoint | 8.3.1 - Aspahlt Mix Acceptance
label | Detail of Activity - Assessment of all test results for conformity and revised JMF based on Production and Field Results
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each mix used on the project
label | Inspection / Test method - Review
label | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | Record documents - NCR - Email Approval
label | Responsibility - Colas/Clients Rep
label | Comments - Results and reports for revalidation of mix design and associated AT approval will be submitted
holdpoint | HOLD POINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Designer's Rep Name:
textbox | Client's Rep. Name:
date | Date:
signoff | Sign ITP
checklist | ITP - AC Placement | itp |  |  |  |  | ITP - AC Placement
section | 9.1 - Pre-paving inspection
checkpoint | 9.1.1 - Pre-paving inspection
label | Detail of Activity - Weather suitable for paving
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - The day before paving and 2 hours prior to paving
label | Inspection / Test method - Contractor visual on site and weather forecasts
label | Acceptance Criteria - Confirm weather conditions are free of rain and not foggy during sealing and for next 24 hours and surface to be paved is visually dry and free of surface water'
label | Record documents - Contractor's site diary and email or verbal confirmation weather ok for sealing
label | Responsibility - Colas / Client Rep
holdpoint | HOLD POINT
checkpoint | 9.1.2 - Pre-paving inspection
label | Detail of Activity - Temperature of underlying base prior to paving asphalt is >=7 degrees
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 4 randomly located measurements in the shade
label | Inspection / Test method - Infra Red Temperature Gun
label | Acceptance Criteria - Temperature on3 out of 4 measurements > 7 degrees on underlying base prior to asphalt
label | Record documents - Contractors site diary (Photo of temperature gun reading)
label | Responsibility - Colas / Client Rep
holdpoint | HOLD POINT
checkpoint | 9.1.3 - Pre-paving inspection
label | Detail of Activity - Surface Shape
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - < 5mm using 5m straight edge and no areas that can pond water
label | Record documents - Worksheet
label | Responsibility - Colas
holdpoint | HOLD POINT
checkpoint | 9.1.4 - Pre-paving inspection
label | Detail of Activity - Surface Levels
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - +5mm, - 10mm
label | Record documents - Survey
label | Responsibility - Colas
holdpoint | HOLD POINT
checkpoint | 9.1.5 - Pre-paving inspection
label | Detail of Activity - Visual inspection of surface to be sealed
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - per paving schedule.
label | ○ 1 Lot = 1 day's production and < 1500m2
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - If surface is sealed or asphalt then surface must be clean and free of any dust and ponding water.
label | Record documents - Contractor's site diary
label | Responsibility - Colas / Client Rep
label | Comments - The surface finish, line and level, condition is checked by clients Rep. immediately prior to paving
holdpoint | HOLD POINT
checkpoint | 9.1.6 - Pre-paving inspection
label | Detail of Activity - Acceptance of Asphalt Paver
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Once per project
label | Inspection / Test method - Specifications and level controls for Paver
label | Acceptance Criteria - Specifications and level controls for levels on asphalt paver submitted and accepted by Client Rep and Contractor to demonstrate the desired slope of the surface is within plus or minus 0.1%
label | Record documents - Communications with Contractor and Client Rep on Paver Equipment and Levels controls used
label | Responsibility - Colas / Contractor/ Client Rep
label | Comments - See Cl2 determine what current method used on Paver to control smoothness and transverse slope and add in acceptance criteria
holdpoint | HOLD POINT
checkpoint | 9.1.6 - Pre-paving inspection
label | Detail of Activity - Certified full length weigh bridge
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Once per project
label | Inspection / Test method - Certificate of Calibration of full length weigh bridge
label | Acceptance Criteria - Accurate and passes certification for weighbridge by independent weighbridge certifier
label | Record documents - Weigh Bridge Certificate
label | Responsibility - Colas
holdpoint | HOLD POINT
section | 9.2 - Production
checkpoint | 9.2.1 - Production mix at Asphalt Plant
label | Detail of Activity - Particle Size Distribution
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per day and the 1 per 200 t at asphalt plant
label | Inspection / Test method - Approved JMF and NZTA M10
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas
checkpoint | 9.2.2 - Production mix at Asphalt Plant
label | Detail of Activity - Binder Content
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per day and the 1 per 200 t at asphalt plant
label | Inspection / Test method - Approved JMF and NZTA M10
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas
checkpoint | 9.2.3 - Production mix at Asphalt Plant
label | Detail of Activity - Max. Specific Gravity
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per day and the 1 per 600 t at asphalt plant
label | Inspection / Test method - Approved JMF and NZTA M10
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas
checkpoint | 9.2.4 - Production mix at Asphalt Plant
label | Detail of Activity - Lab Air Voids Gyro
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per project or 1 per 600 tonnes
label | Inspection / Test method - Approved JMF and NZTA M10
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas
checkpoint | 9.2.5 - Production mix at Asphalt Plant
label | Detail of Activity - Mix discharge temperature
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per day and the 1 per 200 t at asphalt plant
label | Inspection / Test method - Approved JMF and NZTA M10
label | Acceptance Criteria - >158 degrees as per M10 Notes for S grade binder PG64S
label | Record documents - Diary Records at Plant
label | Responsibility - Colas
section | 9.3 - Paving on site
checkpoint | 9.3.1 - Planning location of paving runs and joints
label | Detail of Activity - Determine joint locations and paving runs as acceptable by Client Rep, also agree areas that need to be hand layed
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each paver run
label | Inspection / Test method - Best Practice/ Drawings/ Visual
label | Acceptance Criteria - As agreed by Client Rep
label | Record documents - Field diary
label | Responsibility - Colas
checkpoint | 9.3.2 - Cold Joints Cut Back
label | Detail of Activity - Locate cold joints and cut back prior to adjacent paving
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each paver run
label | Inspection / Test method - Best Practice/ Visual
label | Acceptance Criteria - Visually accepted finished joints (almost invisible joints)
label | Record documents - Field diary/ Photos
label | Responsibility - Colas
checkpoint | 9.3.3 - Paving and compacting mix on site
label | Detail of Activity - Record temperature of mix in paver, on mat start of rolling and on mat end of rolling
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each paver run
label | Inspection / Test method - NZTA M10/ Best Practice
label | Acceptance Criteria - Temperatures >90 degrees (minimum compaction); First delivered in paver mix temp >130 deg - note departure from NZTA M10 Notes that require 146 deg compaction temperature
label | Record documents - Field diary
label | Responsibility - Colas
label | Comments - Experience found for thin asphalt mix cools very quickly but can still be succesfully compacted on site
checkpoint | 9.3.4 - Paving and compacting mix on site
label | Detail of Activity - Record rolling methodology, types of rollers, order, vibe and static and number of passes
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each paver run
label | Inspection / Test method - Best Practice
label | Acceptance Criteria - No Nuke Plateau and/or NDM Density and approved by Area Manager as confirm best practice has be used to achieve compaction on site
label | Record documents - Field diary
label | Responsibility - Colas
checkpoint | 9.3.5 - Paving and compacting mix on site
label | Detail of Activity - NDM or No Nuke Density Measurements on site for Air Voids
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each paver run
label | Inspection / Test method - NZTA M10
label | Acceptance Criteria - At 10m increments using NDM if required as per NZTA M10 for asphalt mixes >35mm thick
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas
label | Comments - If NDM or No Nuke used then evidence of apropriate offset is needed found from correlations between air voids from NDM or No Nuke and extracted core air voids
checkpoint | 9.3.6 - Paving and compacting mix on site
label | Detail of Activity - Extracted Core Air Voids if required
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each days production 8 on mat and 3 on joints
label | Inspection / Test method - NZTA M10
label | Acceptance Criteria - Air voids requirements as per NZTA M10. Cores not required as per NZTA M10 for asphalt thickness < 35mm
label | Record documents - IANZ accredited test cert
label | Responsibility - Colas
label | Comments - Often for surfacing mixes cores are not allowed due to visually being unacceptable and thus use NDM and NoNule methods above
checkpoint | 9.3.7 - Paving and compacting mix on site
label | Detail of Activity - Thickness
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Dipstick and field report each truck load
label | Inspection / Test method - Record
label | Acceptance Criteria - As per design requirements
label | Record documents - Field report
label | Responsibility - Colas
checkpoint | 9.3.8 - Paving and compacting mix on site
label | Detail of Activity - Layer Width/ Length and Area per truck
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Field report each truck load
label | Inspection / Test method - Record
label | Acceptance Criteria - As per design requirements
label | Record documents - Field report
label | Responsibility - Colas
checkpoint | 9.3.9 - Paving and compacting mix on site
label | Detail of Activity - Surface Shape
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - < 6mm using 3m straight edge and no areas that can pond water
label | Record documents - Worksheet
label | Responsibility - Colas
label | Comments - Or as agreed prior to sealing in terms of what practically can be achieved based on smoothness of granular base and kerb alignment
holdpoint | HOLD POINT
checkpoint | 9.3.10 - Paving and compacting mix on site
label | Detail of Activity - Surface Levels
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - +5mm, - 5mm
label | Record documents - Survey
label | Responsibility - Contractor/ Colas
holdpoint | HOLD POINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Designer's Rep Name:
textbox | Client's Rep. Name:
date | Date:
signoff | Sign ITP