## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Entranceway | itp |  |  |  |  | ITP - Entranceway Rev 0
section | 1.0. AGGREGATE ACCEPTANCE TESTING
checkpoint | 1.01 - NZTA M04
label | Detail of Activity / Test - Crushing Resistance
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
label | Inspection / Test method - NZS4407:2.4.7
label | Acceptance Criteria - > 130KN
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | Designer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.02 - NZTA M04
label | Detail of Activity / Test - Particle size distribution
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
label | Inspection / Test method - NZS4407:2.4.7
label | Acceptance Criteria - As per NZTA M04 Specfication
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | Designer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
section | 2.0. CONSTRUCTION
checkpoint | 2.01 - Earthworks
label | Detail of Activity / Test - Scarify Existing Entrance way Surface
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - As per design drawings
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.02 - M4 Placement
label | Detail of Activity / Test - M4 Placed in Accordance with Design Drawing and Survey
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - As per design drawings
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Survey Record
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.03 - M4 Compaction
label | Detail of Activity / Test - Compact in Layers no greater than 150mm.
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test Per 10m2
label | Inspection / Test method - Clegg
label | Acceptance Criteria - CIV >30
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer - I
label | Eng. Rep / NZTA - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature