## ITP Cover Page
Concrete for Minor Structures and Incidental Works Inspection and Test Plan
Project: Wellesley St Bus Interchange - WSBI
Number and Revision: DN1211 - 010 - Rev Draft
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Wellesley St Bus Interchange - WSBI |  |  |  |  | ITP Number: |  |  | 010
Project Number: |  |  | DN1211 |  |  |  |  | ITP Status: |  |  | For Construction
ITP Description: |  |  | Concrete for Minor Structures and Incidental Works |  |  |  |  | Revision: | 1000 |  | Draft
Contract Number: |  |  | WSBI-DN1211 |  |  |  |  | Drawing Sets: |  |  | DRG-LU-2312 IFC Set
Customer: |  |  | Auckland Transport |  |  |  |  | Specification: |  |  | WSBI Technical Specification, Ref: 522356-W00001-SPE-MC-0001
Quality Specified:
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
Draft | Draft for Review | 2024-09-17 |  |  |  | Concrete for Minor Structures and Incidental Works |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
0 | IFC | 2024-09-23 |  | R.Collier |  | Updated with Aurecons Comments |  |  |  | C | Check |  | DES | Designer
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – Master ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP
Concrete for Minor Structures and Incidental Works Inspection and Test Plan
Project: Wellesley St Bus Interchange - WSBI
Number and Revision: DN1211 - 010 - Rev Draft
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | MSQA signature (Blank as Req.) | Engineer Rep Signature (Blank as req.) | Comments / Closeout Details
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | Site Requirements
3.01.01 | Construction Pack | Submit a Construction Pack including a Methodology and JSEA to the Engineer before works | Downer | Construction Pack | Submit 5 days prior to commencement of works | H | PE |  |  |  | R
3.02.02 | Survey Setout | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Downer | Survey Records | Prior to Works | H | SV
3.01.02 | Service Location | Complete the Excavation permit process to identify, locate and protect all services. | Downer | Excavation Permit | Prior to Excavation | H | SE
3.02.03 | Internal Permits | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Downer | Internal Permits | Prior to Excavation | H | SE
3.01.03 | External Permits | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | Downer | External Permits | Prior to Excavation | H | PE |  |  |  | R
3.02.04 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.01 | General Material Approval
4.01.01 | Mix Design | Typical structures ‐Confirm supply of 'high grade' 20MPaconcrete; 19mm maxaggregate size.General site concrete ‐ 10MPa Where specified ondrawings, use marinegrade concrete ‐30MPaThe Contractor shallensure that the readymix supplier can provide mix designinformation andstrength testingrecords on request. | Aurecon Civil Spec Section 14.6 | Mix Design Report Approval | Upon Request / prior to Use | H | PE |  |  | R | R
4.01.02 | Motar | Consisting of two parts fine, sharp, well graded sand to one part dry cementMix by hand or mixer in small qunatities,use within 30 minutes | Aurecon Civil Spec Section 14.6.5 | In process check | Prior to each pour | I | PE
4.01.03 | Reinforcement | Reinforcement andembedded items cut, bent (cold) andaccurately placed asshown on design drawings. At least30mm cover to all reinforcing +5mm/‐0mmBar spacing as per drawings +/‐ 10mmBend locations as perdrawings +/‐5mm | Aurecon Civil Spec Section 14.6.7 AS/NZS 4671 | In process check | Prior to each pour | I | PE |  |  | R
SECTION 5 – CONSTRUCTION ACTIVITY – CONCRETE INSTALLATION
5.01 | Construction
5.01.01 | Pre Pour Inspection Concret Placement | Notify Engineer for inspection of formwork 24 hours prior to pour forinspection | _ | QA Sheet | Prior to each pour | H | SE |  |  | I | I
5.01.02 | Pour Plan | Place concrete and construction joints as per design drawings Exposed surfaces: F4 formed finish (or F5 if specified), U2 screeded finish Slabs: U3 trowel finish for internal slabs, U5 textured forexternal slabs Delivery dockets dated and showing the concrete supplier and design strength shall be collected and held for every pour. Record location and date of each pour | NZS 3124 | QA Sheet Delivery Dockets | For Each Pour | W | SE |  |  | R | R
5.01.03 | Testing | Slump test during pour to check workability of concrete or as directed by Engineer 3 cylinder tests taken for each pour. Slump target as per mix design 120 mm when measured at the point of delivery to site. | Aurecon Civil Spec; Section 14.7.12, NZS 3112 | QA Sheet UCS Test Report | Each pour / every 75m3 (one sample for pours less than 75m3) | H | SE | H |  | R | R
5.01.04 | Independent Testing | The Engineer's Rep may request site samples/cores for independent testing of fresh or cured concrete to review the grading, mix design, strength and thickness. | _ | IANZ Lab Report | Upon Request | W | SE |  |  | R | R
SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6.01 | Site Post Construction Activities
6.01.01 | Construction Record Compilation | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Downer | Records | Post construction | H | SE |  |  | R | R
6.01.02 | Survey Records | Ensure all items have been surveyed and records are assembled for asbuilting | Downer | Records | Post construction | H | SV |  |  | R | R
6.01.03 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen/RFI reference | Downer | Redlines | Post construction | H | PE |  |  | R | R
6.01.04 | Defect, Snag and Punch List | Update the project Defect, Snag and Punch List Register | Downer | Register | Post construction | H | PE |  |  | R | R