## Table 1
Concrete Inspection Record
Contract Name: | [8 empty] | Contract No:
Location: | [8 empty] | Lot No:
| Location / Description of Pour: | [8 empty] | Concrete Grade |  |  |  | MPa
[10 empty] | Concrete Quantity |  |  |  | M3
| Drawings & Revision No. used to check off Pre Pour Inspection: | [8 empty] | Pour No.
| Formwork |  |  | Result |  | Initials |  | Date |  | Comments
| Adequately braced and supported |  |  | Yes / No
| Grout tight |  |  | Yes / No
| Correct dimensions |  |  | Yes / No
| Cleaned and oiled |  |  | Yes / No
| Formed surfaces straight |  |  | Yes / No
| Major penetrations located |  |  | Yes / No
| Embedded items located |  |  | Yes / No
| Correct for specified surface finish |  |  | Yes / No
| Adequate seating Pre Cast units |  |  | Yes / No
| Permit to Load Obtained |  |  | Yes / No
| Reinforcement |  |  | Result |  | Initials |  | Date |  | Comments
| Reinforcement Content and size |  |  | Yes / No
| Confirm correct grade markings |  |  | Yes / No
| Placement, tolerance, clearance |  |  | Yes / No
| Rigidity and cover |  |  | Yes / No
| Clean steel |  |  | Yes / No
| Lap location and lengths |  |  | Yes / No
| Starters/dowels correctly located |  |  | Yes / No
| Construction Joints |  |  | Result |  | Initials |  | Date |  | Comments
| Location |  |  | Yes / No
| Roughened |  |  | Yes / No
| Clean |  |  | Yes / No
| Water bar placed if specified |  |  | Yes / No
| Other |  |  | Result |  | Initials |  | Date |  | Comments
| Correct mix ordered |  |  | Yes / No
| Independent Survey – Check off critical survey points |  |  | Yes / No
| Engineer’s Rep Notified |  |  | Yes / No
Pre-Pour Checked and Accepted – HOLD POINT – Site Engineer & Engineer’s Rep to sign
| Name: Site Engineer |  |  | Sign: | [5 empty] | Date:
Concrete Inspection Record
Contract Name: |  | Taramakau River Road Bridge | [6 empty] | Contract No: |  |  | 63202
Location: | [8 empty] | Lot No:
| Wet Concrete Checks |  |  | Result | Initials |  | Date |  |  | Comments
| Correct mix delivered |  |  | Yes / No
| Slump/flow Target |  |  | Yes / No
| Compliance Cylinders Taken |  |  | Yes / No
| Site Cured Cylinders Taken |  |  | Yes / No
| Concrete Vibrated |  |  | Yes / No
| Mandrels drawn through all ducts to verify no leakage / disconnection |  |  | Yes / No
| Finished Level: Finished to grout check / angle fillet worked to |  |  | Yes / No
| Surface to required finish eg U2, U4 |  |  | Yes / No
| Retarder applied at end of the pour |  |  | Yes / No
| Curing applied (specify type) |  |  | Yes / No
| Concrete Supply Dockets collected |  |  | Yes / No
| Pour Start Time: |  |  | Pour Complete Time: | [8 empty] | Volume Placed:
| POST CONCRETE INSPECTION |  |  | Result | Initials |  | Date |  |  | Comments
| Curing correctly carried out |  |  | Yes / No
| Concrete Strength for Striking ………. |  |  | Yes / No
| Concrete Strength for backfilling…….. |  |  | Yes / No
| Preparation of Construction Joints Completed |  |  | Yes / No
| Blow holes, tie bar holes filled |  |  | Yes / No
| Inspection of surface/s & any authorised repairs have been completed |  |  | Yes / No
| As-Built complete |  |  | Yes / No
The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
| Name: Site Engineer |  | Sign: | [7 empty] | Date: