## Table 1
|  |  |  | Process Control Plan |  | FHIMS-QA-6006 |  | Approved |  | Signature
|  |  |  | Contract Name: Pomona Road Resevoir Upgrade Procedure: Insitu Concrete |  |  |  | FH Engineer FH Quality Manager |  | Paul Huntrer Josh Turner
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Work Instruction: |  |  | PRR -CS-7052 |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria |  | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Permits | H | Obtain Permits | As required | Document Review | Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place |  | Permit attached or permit number noted | Site Engineer
2 | Pre-construction sign offs | H | Is the Work Instruction for this work complete? | Prior to commencement | Document Review |  |  | TMP on RecordsLink | Site Engineer
|  | H | Relevant non conformance of previous work signed off | As required | Document Sign Off | Relevant parties to inspect and review |  |  | Site Engineer
3 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review |  |  | Check Drawing Register | Site Engineer
4 | Material Compliance | H | Concrete mix design(s) submitted and approved by Design Engineer | Prior to commencement | Document Review | Check concrete mix design status |  | Design Engineer Approval | Site Engineer | Design Engineer
|  | W | All concrete delivered to site shall be produced in accordance with the approved mix design | Prior to pouring concrete | Concrete Delivery Dockets |  |  | Concrete Delivery Dockets | Site Engineer
|  | W | Steel reinforcement complys with drawings, specifications and standards | Prior to commencement | Document review | Steel reinforcing conforms to drawings and specification |  | Detail Sheets and Mill Certificates | Site Engineer
|  | H | Any welding or mechanical splicing to be approved in writing by the Design Engineer | Prior to welding or splicing | Document review |  |  | Mark Up As Built Drawings | Site Engineer
|  | H | Any reinforcement modifications (cutting or bending) on site to be approved in writing by the Design Engineer | Prior to cutting or bending on site | Document review |  |  | Mark Up As Built Drawings | Site Engineer
5 | Foundation Acceptance by Engineer's Rep | H | Approval given by engineer's Rep and Signed off Subgrade Approval Checksheet | Prior to commencement | Inspection by Engineer | Inspection and Acceptance of Structure Foundations |  | FHIMS - CS- 4100 | Site Engineer | Design Engineer
6 | Survey Setout | H | Set out design features as per IFC drawings (Cast in items, Ducting, Penetrations) | Prior to commencement | Survey | Consistency with Construction Drawing |  | Survey receipt | Site Engineer
7 | Blinding Concrete | H | Once blinding concrete layer has been completed the Engineer's Rep to inspect and give approval for the rest of the works to commence | Prior to commencement | Inspection by Engineer |  |  | Sign off this document | Site Engineer | Design Engineer
8 | Temporary Works (Formwork) | W | Formwork to be constructed to design and set to correct line and level as set out by the surveyor | Daily Visual Inspection | Visual inspection | Concrete Inspection Record |  | FHIMS-CS- 4008 | Site Engineer
|  | H | The Site Engineer and must sign off the formwork prior to concrete being poured | Prior to concrete pour | Visual inspection | Concrete Inspection Record |  | FHIMS-CS- 4008 | Site Engineer
9 | Reinforcing | W | Reinforcing steel shall be handled, placed and fixed as per NZS 3109 | Daily Visual Inspection | Document review | Concrete Inspection Record |  | FHIMS-CS- 4008 | Site Engineer
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria |  | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
|  | W | Check for any cast in items and ensure they are fixed correctly | Prior to concrete pour | Visual inspection | Concrete Inspection Record |  | FHIMS-CS- 4008 | Site Engineer
10 | Waterstop | W | Waterstop and Hydrophilic placement checks to ensure correct placement including welds | Prior to commencement | Visual inspection | Photos & sign off |  | FHIMS-CS- 4029 | Site Engineer
11 | Concrete Pumping Operations | W | Ensure the Permit to Concrete Pump Checksheet has been completed before concrete pumping commences | Prior to commencement | Document review |  |  | FHIMS-CS- 4029 | Site Engineer
12 | Concreting | H | The Design Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required | Prior to concrete pour | Visual inspection |  |  | FHIMS-CS- 4008 | Site Engineer | Design Engineer
|  | H | Concrete dockets checked for correct mix and concrete site testing undertaken. 1 slump test per truck. 1 sample set per 75m3 of each different mix | Prior to concrete pour | Test Results | NZS 3104 |  | FHIMS-CS- 4090 | Site Engineer
|  | H | Concrete surfaces shall be F4 or better for formed surfaces and U3 or better for unformed surfaces | Post pour | Visual inspection | Concrete Inspection Record |  | FHIMS-CS- 4008 | Site Engineer
|  | M | Curing and thermal monitoring | Post pour | Visual inspection | Concrete Inspection Record |  | FHIMS-CS- 4008 | Site Engineer
|  | W | Review concrete compressive tests results | Post pour | Visual inspection | Concrete Inspection Record |  | FHIMS-CS- 4008 | Site Engineer
13 | Remove formwork | W | Remove formwork as per the approved work method | At completion of pour | Visual inspection | Concrete Inspection Record |  | FHIMS-CS- 4008 | Site Engineer
14 | Lot Number QA File | W | Ensure all OFIs are closed and included within QA file | At completion of Lot | Document Review |  |  |  | Site Engineer
|  | W | The Concrete Test Result Spreadsheet and Test reports to be included within QA file | At completion of Lot | Document Review |  |  |  | Site Engineer
|  | W | Delivery Dockets to be included in QA file | At completion of Lot | Document Review |  |  |  | Site Engineer
15 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  |  | Asbuilt Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers: Reference Documentation (Notices/OFIs etc.):
QA Compiled By Quality Manager: QA checked By Contract Manager: Accepted By Design Engineer: |  |  |  |  | Signature: Date: Signature: Date: Signature: Date: