## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
cd4160fa-ca9b-40c6-a0ef-aca8b3a37421 | checklist | DTM-ITP-001- Clearing and Grubbing Rev0 | itp | DTM-ITP-001- Clearing and Grubbing
978d3c0a-7747-4b99-83ca-ecbaeb8ba080 | section | 1 - Preliminary Works
f221dbc5-e143-4614-a874-4554378c07a3 | checkpoint | 1.1 - Check for correct documentation
b95c5f0c-11bb-52b8-8212-813958013045 | note | FREQUENCY: Prior to commencing any activity
7d5ddbac-fbf8-5407-951e-596fa573a7c8 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
65bbcb94-b151-5b75-9c6c-e5f13f1a1dc6 | note | – using the correct and complete set of drawings & all drawings are the latest revision
e74b2e37-1e25-51eb-8460-50e28e63059f | note | – Signed onto work pack
8de91b5a-0d0d-52cf-b60c-59e914fd3a39 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
ec18207d-e8a8-5b7a-b8dd-503cf9ebe8a8 | note | INSPECTION/TEST METHOD: Visual inspection
e839934b-0753-597a-8036-ef1e53ee90de | note | RECORD OF CONFORMITY: This ITP signed
4e5ae235-e8fa-513d-ac2f-3a67d50835e2 | note | HP*
3708c0ab-c870-5cf3-ba43-31c81b715047 | note | RESPONSIBILITY: Site Engineer
56cdb1c4-b025-5088-bab0-3fde9c3bfe5c | date | Date Completed:
485cf77c-9a7f-498b-a96c-1f88289e621c | checkpoint | 1.2 - Limits of work
6986b71f-10f9-54f4-ba48-75833b69e278 | note | FREQUENCY: Prior to pre commencment inspections
b0a446b7-0218-53a5-9ecd-0fe2241b93d0 | note | ACCEPTANCE CRITERIA: Clearing extents to be marked out as per drawings and ATC's/ RFI's.
741cd4f1-9d14-5a87-b4ae-440e65898768 | note | ○ Southern Outlet Highway is Road A0171, Link 5, CH 0.33 to CH 0.00.
8d59367b-1b74-58f9-aa79-4a6d517a38dd | note | ○ Davey Macquarie Couplet Main Road A1010, Link 5, CH 0.00 to CH 0.09.
dafe03b4-ea83-5376-bf7f-af0407061411 | note | ○ Davey Macquarie Couplet Main Road A1010, Link 10, CH 0.00 to CH 0.1 (approx.)
0e3b2984-c822-5138-991f-d734420bfdcb | note | REFERENCE DOCUMENTS: Cl 201.03
fd521529-655f-5dfa-9bb9-a25048f004a0 | note | INSPECTION/TEST METHOD: Visual inspection
8819e083-54f0-5acf-a92f-0622bf7eebbb | note | RECORD OF CONFORMITY: This ITP signed
9aace2a4-9a2e-5a85-a0ec-9b99f2c7034a | note | HP*
74b43e52-8f8d-5b71-a688-bd3a280e6fed | note | RESPONSIBILITY: Surveyor / Site Engineer / Foreman / Clearing Contractor
db282bd0-48fb-5114-bbd9-ef6fa91da74c | date | Date Completed:
2961961f-5fef-4f51-8943-fcb98c4d8a99 | checkpoint | 1.2 - Implementation of all measures and controls
d1b594a0-25e2-5e19-ba71-c53e42dc6be2 | note | FREQUENCY: Prior to commencing any activity
622630fc-0fa2-5d8a-ba35-eca41bf2df2a | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: PSP, EMP, TMP, SWMS & WP
483316a1-2d33-5271-9e9f-601953098e53 | note | REFERENCE DOCUMENTS: PMP, EMP, TMP, SWMS, Work Pack
ce3d923e-2652-59b7-83e0-cc1eec4f4dc0 | note | INSPECTION/TEST METHOD: Visual Inspection
b657f43c-adc2-5903-a1a4-d1832bdc43f7 | note | RECORD OF CONFORMITY: This ITP signed
a55ecc6e-2c88-5290-8f39-cc98916bc127 | note | HP*
ac66bc81-0d6e-5fa2-8a64-271cec937abf | note | RESPONSIBILITY: Site Engineer
9d26fd4d-7426-50f3-ab1f-dce4021aa70e | date | Date Completed:
4c336d60-d2ac-46e9-b845-a15843fc929f | checkpoint | 1.3 - Implementation of environmental measures and controls
87dda4f8-f8d5-57a6-bff3-eca8184cc618 | note | FREQUENCY: Prior to commencing any activity
c380380e-9686-5547-bb60-51ec3bfdf8a4 | note | ACCEPTANCE CRITERIA: Hold Point
68d7c897-9ed6-5daf-ad2d-32d51ba29215 | note | ○ EMP meets the requirements of the specification and all controls have been implemented as per approved EMP
72481796-685e-507a-99c7-533a9209f0e7 | note | REFERENCE DOCUMENTS: Project Spec Cl160.24 EMP
f4cd4980-7ba3-5189-abba-8166853b77da | note | INSPECTION/TEST METHOD: Verify
09fdd594-e413-57a8-90df-9f6a7e57c6f1 | note | RECORD OF CONFORMITY: This ITP signed
69a8138c-3d07-5fbe-9a62-5414570075c0 | note | HP*
2e582631-845e-5355-8dd6-237fdb21550a | note | RESPONSIBILITY: Site Engineer
01112224-bd0d-5660-b162-13ddebad2ccd | date | Date Completed:
29876525-1f8e-4b96-ba43-fa34e1528849 | checkpoint | 1.4 - Flora and Fauna
6d201ff0-31ce-5bba-82b0-ac109cacfbb8 | note | FREQUENCY: Prior
768182a0-d263-515e-87a6-004ac0d8c2eb | note | ACCEPTANCE CRITERIA: Hold Point
b6baab11-a1f3-52d9-871a-64dd8471c6cf | note | ○ Vegetation to be removed clearly marked and agreed. All removal consistent with contract drawings and permits.
d56bdb8d-be0f-5e29-864f-6109f6309b50 | note | REFERENCE DOCUMENTS: EMP Cl176.I1(c)
80961749-d9ae-5a3e-904f-bb21e2424a68 | note | INSPECTION/TEST METHOD: Verify
c254e81d-846c-52f9-a90a-865e56fb2bc5 | note | RECORD OF CONFORMITY: This ITP signed, Vegetation Removal and Clearing Permit
6666e963-96af-55dc-967e-33581ec66f46 | note | HP
0c8aa277-1f1d-54cc-a94c-c144b44412d4 | note | RESPONSIBILITY: Site Engineer / QAV
6688cf9c-28c0-52ca-b77c-b311608985bb | date | Date Completed:
cc49166c-f91d-4348-b875-c39c1adb8494 | signoff | AUTHORITY HOLDPOINT
7d3152d4-3bea-43c4-933d-9bbf5896589d | checkpoint | 1.5 - Protection of Existing Vegetation
2d264ab3-fd01-5487-b6a4-7ab60d913fc0 | note | FREQUENCY: Prior to comencement of any work
4eb5b136-d200-52c3-9f6c-82b0718ba33a | note | ACCEPTANCE CRITERIA: Prior to the commencement of any work, the Contractor and the QAV shall conduct a joint inspection of the site to identify vegetation to be retained and protected.
e46c452f-1e38-53fa-ba91-121421d7dda7 | note | ○ If directed by the QAV, existing trees, shrubs, native grasses and groundcovers and other areas of existing vegetation shall be protected by temporary fencing and incorporated into the works by the Contractor.
a4680e63-bed2-551b-ac47-b56eeb481e31 | note | REFERENCE DOCUMENTS: EMP Cl201.10,Cl160.24, 176.I1
886d51df-c7dd-5730-90eb-0aa0d1df30ef | note | INSPECTION/TEST METHOD: Visual inspection
4ac6c785-e3b2-5ec1-b07e-a5a5e1c9d48e | note | RECORD OF CONFORMITY: Vegetation Removal and Clearing Permit, Tree Protection Plan
f8e94bad-5992-5597-ba14-961f028d1835 | note | IP
29bd3e7a-66e8-5acf-a88c-56283241438d | note | RESPONSIBILITY: Site Engineer / QAV
6e0f9275-cbf8-5c84-b3d9-0f35c8cc2c37 | date | Date Completed:
632d5c5d-6ee8-424f-a136-35784a7aff7e | checkpoint | 1.6 - Cultrual Heritage
6e651572-afdc-5e9c-8573-43e023289f16 | note | FREQUENCY: Prior to removal of vegetation
4c30c36c-95fd-5c4c-b790-8e4d14cea67f | note | ACCEPTANCE CRITERIA: Hold Point
7568c301-9bc8-57e1-8548-c5e2ff08c7ef | note | ○ Nominated sites of archaelogical and / or heritage significance inspected on-site and clearly identified and protected as No-Go zones
8f5da0ed-aea7-5d96-ba36-444ed2354b54 | note | REFERENCE DOCUMENTS: EMP Cl176.J1(e)
3cfd59fa-295f-58f7-824d-4588055cbb06 | note | INSPECTION/TEST METHOD: Verify
22ad1479-77ac-5bbf-9337-bec46374c948 | note | RECORD OF CONFORMITY: Vegetation Removal and Clearing Permit, Tree Protection Plan
35b0fe92-ed26-5caa-95bb-c05ed4f9dd59 | note | HP
f5d0a6a8-87d1-5fcd-b233-1a85e8022573 | note | RESPONSIBILITY: Site Engineer / QAV
3a91009f-fcdf-5b63-b0b9-a92effc19bfa | date | Date Completed:
084ca863-f8ae-4ed2-984e-149419237db6 | signoff | AUTHORITY HOLDPOINT
cd370f2f-489b-453b-b982-deb672d58016 | checkpoint | 1.7 - Authorisation for works
36a3075a-7ad4-51ef-af56-03609344b910 | note | FREQUENCY: Prior to commencing works
fb3b54b8-71e3-59b4-b5d8-3679e0c7828d | note | ACCEPTANCE CRITERIA: Check that all relevant approvals (Access to 241 Davey, 326 Macquarie) have been granted including verification of the works area.
8e29ec26-dc8c-59d0-95c9-84118d80b584 | note | ○ Ensure work pack is reviewed & signed
68988739-b1ff-5959-b3b2-9dfdd09b1baa | note | REFERENCE DOCUMENTS: Work Pack 160.08
e2f3e977-804f-5f01-bc43-fc17b7586dfb | note | INSPECTION/TEST METHOD: Verify
14c63dc5-315f-5208-a91d-17b01abeaa6e | note | RECORD OF CONFORMITY: This ITP signed, Property Access Approval
78e054fc-418b-5d40-b724-3972ee32e47d | note | HP*
5611b064-7a63-5466-9202-4c5bd47f3072 | note | RESPONSIBILITY: Site Engineer
11105919-1f33-541c-8ac9-bbaeb6797e7d | date | Date Completed:
b263f5cf-4f17-494e-b51e-6ce510fa3e8b | checkpoint | 1.8 - Utilities
db61a8cf-77a4-544f-ab50-2b7d82468a15 | note | FREQUENCY: Prior to commencing works
b3bb7563-761e-5939-9af0-c4720ace3635 | note | ACCEPTANCE CRITERIA: DBYD - locate and mark all existing services and confirm clearance from proposed work
1d8c708a-7a7f-553c-aa4c-d630e5890074 | note | REFERENCE DOCUMENTS: DBYD Records, Plan Mark-Ups, Excavation Permit
9742321b-ec0a-5d37-8374-db933beb50f6 | note | INSPECTION/TEST METHOD: Verify
f1000026-16aa-5393-8910-95be20fa72a0 | note | RECORD OF CONFORMITY: This ITP signed
a385f50f-ae0c-5b03-ac1c-1235b819d039 | note | IP
caf65a5d-d16e-593e-b1ab-5354174010bb | note | RESPONSIBILITY: Site Engineer
a53d7a95-6a9c-5403-9202-880c83cbaa06 | date | Date Completed:
35d9a4b5-99b5-427b-b648-00ba29e210b0 | checkpoint | 1.9 - Traffic Management
4f8f2031-f747-5de6-a207-0b98f72fa2b5 | note | FREQUENCY: Prior to commencing works
6e92de9e-223d-5029-adee-78d80c4a1f20 | note | ACCEPTANCE CRITERIA: Consider the requirements for traffic management, ensuring all works comply with required TMS, TMP and TGS. Where localised speed reductions are required they shall be at the discretion of the QAV. TGS shall be submitted and approved by the Superintendent.
5f036104-e406-5f90-a630-7f70a5c18b8c | note | REFERENCE DOCUMENTS: TMS, TGS, TMP, 160.07
f6d0534b-ef37-5413-91a6-cc1a59a91203 | note | INSPECTION/TEST METHOD: Verify
4c1ccd6b-22e2-54c0-988e-b0845e902e23 | note | RECORD OF CONFORMITY: This ITP signed
5521c832-8b66-54b9-aa1e-28a75edd2097 | note | IP
e1a95a07-9a49-53de-a511-71512b6549fc | note | RESPONSIBILITY: Site Engineer
145d7c15-0390-5793-ad0b-874974fe4ca4 | date | Date Completed:
e75dcb2a-eff8-4502-9bd9-1c4c9c48064b | section | 2 - Clear & Grub
7b3e8eaa-2984-4daf-9625-fcb2227531df | checkpoint | 2.1 - Clear and grub trees and vegetation
50186ea9-b68d-5954-8064-716aa7df6b73 | note | FREQUENCY: Each Lot
fdd95a45-b152-5755-8866-d27b4c95f642 | note | ACCEPTANCE CRITERIA: Area within specified limits cleared of all vegetation, refuse and obstructions down to natural surface. Trees brought down in a manner so as to avoid danger to personnel and traffic as well as damage to other trees, structures and property.
4b0a80d2-f9e7-551f-a25d-4ab78b92af91 | note | REFERENCE DOCUMENTS: Cl201.04
0e71f4f6-4d4b-5d47-a6b5-2968ac2e7554 | note | INSPECTION/TEST METHOD: Visual Inspection
a07841ef-527b-566e-ad41-314a557d1877 | note | RECORD OF CONFORMITY: This ITP signed
e04997f7-5156-5e72-9217-75db12823421 | note | IP
1fb784be-af17-5b63-950d-f406fbf0df85 | note | RESPONSIBILITY: Site Engineer
8de3606e-462f-54c1-892e-a6baa3b38c59 | date | Date Completed:
0c70dc08-416c-402e-9b0d-6390a2b081be | checkpoint | 2.2 - Clear and grub trees and vegetation
9f1575bf-8394-5bc9-b565-f7413de4d6b6 | note | FREQUENCY: Each Lot
429f80ac-4467-5202-a587-ea86216e2e62 | note | ACCEPTANCE CRITERIA: In areas where excavation is to occur: all vegetation, refuse and obstructions totally grubbed or grubbed > 0.3m below subgrade and batters (whichever is the lesser treatment)
c4b0f60c-ef0f-580a-a35f-478cef69d5c4 | note | REFERENCE DOCUMENTS: Cl201.05
51a4a279-8076-5c7b-888a-6eb82301c676 | note | INSPECTION/TEST METHOD: Visual inspection
72d28079-259c-5101-924d-a4a6fafd39a7 | note | RECORD OF CONFORMITY: This ITP signed
d5d4d87e-deec-5595-ae64-8aabbd47354a | note | IP
0363a4b8-9e4c-5b08-8b9a-c22c546ed2a0 | note | RESPONSIBILITY: Site Engineer
6f2c79ce-9b79-5b84-aef1-09b9e2e5387c | date | Date Completed:
3fea4e0e-64e0-4dd8-8ebd-3243cf88c6c3 | checkpoint | 2.3 - Clear and grub trees and vegetation (embankment areas)
871b09e6-b563-5344-9466-86e9049f3f9d | note | FREQUENCY: Each Lot
4abdea04-bafc-5aeb-9d07-2d58eb933b02 | note | ACCEPTANCE CRITERIA: In areas to be covered by embankments < 1.0m in height: all vegetation, refuse and obstructions grubbed > 0.3m below stripped surface OR > 0.6m below subgrade level (whichever is the lesser treatment)
1fb1d363-cd1a-5d44-a20d-410e29e6551b | note | ○ In areas to be covered by embankments > 1.0m in height: foundations may remian if located or cut off not more than 0.4m above natural surface but not less than 1.0m below subgrade
36fe859e-d562-5171-8842-c3ef83cffda9 | note | REFERENCE DOCUMENTS: Cl201.05
347372dd-857a-5305-a489-a82cc7a3ccf5 | note | INSPECTION/TEST METHOD: Visual inspection
36349761-d9bc-5976-9713-2f5a00dddaee | note | RECORD OF CONFORMITY: This ITP signed
d12603bf-3aef-5728-abb9-04ae5f94b3bb | note | IP
826bcc99-4c54-5121-abbb-cf208e26d95e | note | RESPONSIBILITY: Site Engineer
70aa8aa3-27d0-569d-a98f-9dd9e2f8c819 | date | Date Completed:
e4492093-5490-4bf5-859d-5865dae265ab | checkpoint | 2.4 - Clear and grub trees and vegetation at culvert sites
86a86409-02e9-5239-9587-0ef9571bdc39 | note | FREQUENCY: Each Lot
fc162fa0-733c-5544-ba01-4f443cd00570 | note | ACCEPTANCE CRITERIA: Clear and grub trees and stumps within 10m of any proposed bridge or culvert having a waterway area > 6m2 (unless otherwise shown on drawings)
5402f6e0-43c7-5089-9b94-8a0617a183d2 | note | REFERENCE DOCUMENTS: Cl201.06
c51e21a3-43a7-5bbc-a485-49d8103291f2 | note | INSPECTION/TEST METHOD: Verify
c7783ec9-28ad-56e6-bbb5-1ea14270ca92 | note | RECORD OF CONFORMITY: This ITP signed
bfff7fde-82d1-5ac1-b1c3-7979ac7f4ef2 | note | IP
fe634f17-c416-5434-8144-52aa5fe04379 | note | RESPONSIBILITY: Site Engineer
6ff5f44b-db46-5961-adc0-b0326d95bcba | date | Date Completed:
7238c519-32d0-44cb-b878-03d93b64ae75 | checkpoint | 2.5 - Backfill holes
9d70a48c-e269-59dd-8e76-c7ca935e7fb2 | note | FREQUENCY: After clearing
6c7b5e58-0a6b-5502-8c20-3d8a8eb66bca | note | ACCEPTANCE CRITERIA: Any remnants of pits shall be backfilled with similar material and compacted to a density ratio of not less than 95%. The calculation of density ratio shall be based on Standard compactive effort.
2405bb84-105d-562a-b305-3d027d77b53b | note | REFERENCE DOCUMENTS: Work Pack Cl201.05
375985ca-7351-5e79-8975-4a65964c7456 | note | INSPECTION/TEST METHOD: Verify
a11d151d-fcb2-56d0-84cc-0e56a6b81321 | note | RECORD OF CONFORMITY: This ITP signed
6113525d-a67d-52d4-904e-72e6de7205b5 | note | TP
96d532c1-fb1d-5475-b2cd-4bdde76b94ae | note | RESPONSIBILITY: Site Engineer
3f3d4923-203c-5928-b904-059d3c47df76 | date | Date Completed:
2fb30172-3a6a-4bde-8553-4ce009c86671 | checkpoint | 2.6 - Dispose of Trees and vegetation
eed877d1-f64c-56fc-b17b-f799ab710708 | note | FREQUENCY: After clearing
a410877f-4afc-51ba-89a3-bb96c4f9ab2e | note | ACCEPTANCE CRITERIA: All vegetation within clearing limits shall be removed from site. Weeds not to be mulched and disposed of appropriately.
945b3756-20bc-5603-959c-de2aac83f47d | note | REFERENCE DOCUMENTS: Cl201.07
fe801138-cd85-503c-9c4a-7aeffc4d6f88 | note | INSPECTION/TEST METHOD: Verify
9b4cc6ec-a2b4-502f-b75b-3502b6b6f8c7 | note | RECORD OF CONFORMITY: This ITP signed
bee1236d-395f-5e33-b326-5abecacc03a3 | note | IP
7af4b583-d0e0-53bf-9b39-ba7ea70fc531 | note | RESPONSIBILITY: Site Engineer
7d2501bf-115b-543e-87c7-53cd986e7e86 | date | Date Completed:
1dac20ce-7d06-40b7-81e7-998ca642f827 | checkpoint | 2.7 - Damage to Fencing
98b70d25-b997-56df-ad11-b88d2f4f0d05 | note | FREQUENCY: During Clearing
c4093e29-5214-5216-ae3f-9f4e9d14718f | note | ACCEPTANCE CRITERIA: Immediately repair any damage to fences to a condition at least equal to that before damage
c93ee17f-8c34-512e-b4e9-a2bce4dc8e4a | note | REFERENCE DOCUMENTS:
7f21f095-b9f6-5dc3-8d5c-019cc5aa86b2 | note | INSPECTION/TEST METHOD: Verify
f93c19e4-0427-5a3b-ba41-38c0c42c578f | note | RECORD OF CONFORMITY: This ITP signed
92c25d65-4cf3-574b-b562-ed02251f1281 | note | IP
757cadaa-1d83-52f2-a79d-de725a5da008 | note | RESPONSIBILITY: Site Engineer
0a1320b5-a237-523f-987d-41c97d79a9d3 | date | Date Completed:
0cc48126-9a7f-44f7-8948-9daf8e9d31f4 | checkpoint | 2.8 - Salvage of Vegetation
c4e5ae7b-9cd0-5526-b180-181c64792695 | note | FREQUENCY: During Clearing
33337043-e448-519a-a7b5-09e81fe84368 | note | ACCEPTANCE CRITERIA: Co-ordinating works with activities involving the salvage of plants and the collection of cuttings and available seed from areas of native vegetation on the site.
ea752a98-2893-54cc-ae5f-c5c1710326a2 | note | REFERENCE DOCUMENTS:
4235e68d-d813-5542-8848-aaad66ac5a34 | note | INSPECTION/TEST METHOD: Verify
96b6ca11-d379-5431-92df-fda6caca8d26 | note | RECORD OF CONFORMITY: This ITP signed
78c9f3d2-f55a-577c-a408-3e757735b698 | note | IP
d9414b16-d038-55f8-bb95-8fc25afc98b6 | note | RESPONSIBILITY: Site Engineer
7b68940d-888f-5cec-bd79-628f7fce2b6a | date | Date Completed:
4b3ff4e1-ec59-44ea-990c-1779139eb4bf | checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
c95c5dad-a2d5-5357-822d-56696a2a3fa9 | textbox | QAV - Print Name:
43162616-6a77-5bb5-9387-59e4242d2329 | textbox | QAV - Position:
ed646561-6cc6-52f1-86c3-8f5f8defd656 | textbox | Fulton Hogan - Print Name:
1564af1a-5ea5-5f2a-a445-60f29007d5d1 | textbox | Fulton Hogan - Position:
6b45587f-aa7b-5edf-baac-d8b136e3fbe1 | date | Work Completed On:
aa8f376b-2657-4dee-aa1b-40042ea2a8ed | signoff | Add Signature
21401525-0012-46e5-a968-0d0b2a27afd9 | checklist | DTM-ITP-003- Earthworks Demolition Rev0 | itp | DTM-ITP-003- Earthworks Demolition
35832db6-d0bb-4f06-9f0e-b770577bfb82 | section | 1 - Preliminary Works
87a550e6-0823-455c-89c2-8025f6dfee9e | checkpoint | 1.1 Check for correct documentation
f0eb97b3-8884-596f-abaa-8e5b31c89424 | note | FREQUENCY: Prior to commencing any activity
7bde79dc-68f9-553f-9cdf-02f244d9539d | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
b267049b-4f74-5b2a-9c89-b8d00a2189c0 | note | – using the correct and complete set of drawings
d522b19d-258e-5e07-899f-329031c6f2bd | note | – all drawings are the latest revision
94ce975c-6385-5712-a5d2-1fb6cc36f580 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
1ecbc5e7-8191-5398-a2b1-3b7962442904 | note | INSPECTION/TEST METHOD: Visual inspection
a5e9656f-e3a3-5a44-9234-49e0d75b552f | note | RECORD OF CONFORMITY: This ITP signed off
3ba874b5-de5d-5e5a-98e1-9504da249f5f | note | HP*
3491bcb4-f82a-5df7-b394-f04cb5b819b3 | note | RESPONSIBILITY: Site Engineer / Site Foreman
0a4be045-86ab-500f-90a7-fcec3db23047 | date | Date Completed:
032acfb9-6dda-4e9c-ad6f-f84cc679b8f9 | checkpoint | 1.2 Implementation of all measures and controls
d9b7d730-67a0-52d9-8ba8-8cefb94abd0c | note | FREQUENCY: Prior to commencing any activity
a82ea240-8562-5539-b354-6bb766749e3e | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PMP, EMP, TMP, JSEA, SWMS & Work Pack
d918cc24-2253-517a-99eb-8fa99dc63b2f | note | REFERENCE DOCUMENTS: PMP, EMP, TMP, JSEA, SWMS, Work Pack
75ff653f-05fa-55e3-848d-e1aedd909702 | note | INSPECTION/TEST METHOD: Visual Inspection
b6df93bb-63bb-5dc2-af80-bd1716fa4026 | note | RECORD OF CONFORMITY: This ITP signed off
408bb220-1a1a-5a27-89cb-7b70c47334de | note | HP*
e499f18c-a063-5160-a3a4-d1cc0bcb364d | note | RESPONSIBILITY: Site Engineer / Site Foreman
25863c8f-39b9-556c-9050-76f58ae23774 | date | Date Completed:
3f1f832a-0615-469e-99ef-e735ff17c243 | section | 2 - Construction Works
ecf8d1d9-4189-4cc7-a17e-d01a5f229498 | checkpoint | 2.1 Survey Set-Out
fc9dffbd-3174-552c-b711-d84a9ae21816 | note | FREQUENCY: Prior to commencement of excavation
77546868-73df-59de-971c-813bc2f7776a | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
4e97442e-f261-5375-83a3-de1af1ce7fbd | note | REFERENCE DOCUMENTS: Work Procedure
f3102c44-38f5-51f2-9cce-bb8a5cd55897 | note | INSPECTION/TEST METHOD: Verify
8d576cb8-adff-5460-819a-65845488b1c0 | note | RECORD OF CONFORMITY: This ITP signed off
c3360caa-8efc-52ec-8d40-01de15685fd8 | note | IP
393a68e8-dae2-5138-8f38-30f1e9499771 | note | RESPONSIBILITY: Site Engineer/ Surveyor
c64eeaa5-60f0-5ef3-a37f-4f6340830527 | date | Date Completed:
799d83a3-4f60-4da3-a129-c9650fedeb28 | checkpoint | 2.2 Excavation Permit
03eb3bad-7ee9-50b3-b054-d02a81a33a55 | note | FREQUENCY: Each lot
05b20a37-81a5-5cf8-9b91-985e561ce0e5 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
3aeecd28-b75a-5483-84db-bd898de9d456 | note | ○ Plant and equipment shall be appropriate for the task.
d88258eb-17bc-57de-a38a-45b790172f74 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
33018481-990d-53f4-bc09-839027b492cd | note | REFERENCE DOCUMENTS: Excavation permit
c0f8ad95-80c9-56c5-a750-a969cc6f066e | note | INSPECTION/TEST METHOD: Verify
5dafb385-edab-5d89-9c4a-14050ad9a859 | note | RECORD OF CONFORMITY: This ITP Signed Off
17f183a9-6bb2-5fc6-9d4d-898311581265 | note | HP*
caa09739-1063-5027-8877-e1fd60810f81 | note | RESPONSIBILITY: Site Engineer
cd9def00-e488-5dce-b086-8294d98cbf22 | date | Date Completed:
01e0efe8-6555-4cfa-92fc-46f32da51b2f | checkpoint | 2.3 Material Categorisation
2e2a43ac-dda0-5624-9ebd-6848c33f50b0 | note | FREQUENCY: Each lot
f66df72f-eaa7-55c3-a4f8-c1d1bcaa2692 | note | ACCEPTANCE CRITERIA: HOLD POINT
8e9c4190-083b-5d8c-b240-29abbc4a92a5 | note | ○ Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
102ad923-cc7b-5f18-b693-32a5841f0d23 | note | REFERENCE DOCUMENTS: 204.06(c)
bf2fe195-4921-572f-8140-c77901b61772 | note | INSPECTION/TEST METHOD: Verify
2a43679b-e731-5176-93b3-5dd905e9305f | note | RECORD OF CONFORMITY: This ITP Signed Off
e77b0694-6eb8-55dd-8508-c6848e4971ec | note | HP
719594ee-7180-545b-aaac-1febda669b93 | note | RESPONSIBILITY: Site Engineer/ Superintendent
3003c5aa-8f02-5f51-a752-630c9cf8f867 | date | Date Completed:
112364dd-e9fd-4bcb-8993-955052ee4a4e | signoff | AUTHORITY HOLDPOINT
96b08bd4-bdac-408a-a1f7-45c225d32790 | checkpoint | 2.4 Stripping of Topsoil
3f4ef5b5-67e5-5e33-8d7b-586726814c51 | note | FREQUENCY: Each lot
08a89dc1-0e50-5da8-95de-ef0c137739bd | note | ACCEPTANCE CRITERIA: Topsoil stripped to full width of the formation and placed in approved stockpile location. Stockpile shaped to shed water and stripped surfaces graded to be self draining. Topsoil shall not be removed from site unless approved by the superintendent.
6d71dd34-8267-5d72-9939-ef4c0eddd28e | note | REFERENCE DOCUMENTS: 204.05
7e7f9716-06e9-5751-836e-9100dc68ee5f | note | INSPECTION/TEST METHOD: Visual inspection
45faca66-4638-5ed4-ac6d-a7bf4b16fa80 | note | RECORD OF CONFORMITY: This ITP Signed Off
39a5732f-1070-5922-9a22-59783bafaa49 | note | IP
fa042f8e-bf1c-5596-ad26-9e30cb195214 | note | RESPONSIBILITY: Site Engineer
40d0c638-78f3-5b9a-951e-2930651098e6 | date | Date Completed:
e85876a2-2a79-4e3f-a47f-468eb41f12d0 | checkpoint | 2.5 Type A Material
c6385ed8-e19a-5063-bde7-dc62970bf13a | note | FREQUENCY: Prior to Commencing
486f9b1a-7cbe-5f77-843f-cf17f3891565 | note | ACCEPTANCE CRITERIA: Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
14364c38-6933-5ce8-bf19-0a09eec74b08 | note | ○ HOLD POINT
0adca298-cf97-5c83-a2fa-d17a3c4ed838 | note | ○ Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Superintendent.
414e8c1b-e78d-5a9d-b224-880ac1b5d245 | note | REFERENCE DOCUMENTS: 204.04(b)
3bec5ae9-ecd0-550c-b528-3412cf682347 | note | INSPECTION/TEST METHOD: Document Review
18f95cb7-f662-5205-b412-59f76a60b16c | note | RECORD OF CONFORMITY: Superintendent satisfied with Stabilisation, Signed ITP/ records
0dbe48c2-e32a-5dd9-8498-807147e38d1b | note | HP
9556e1d4-47c2-581a-be78-7a4fb7053085 | note | RESPONSIBILITY: Site Engineer/ Superintendent
fa5b24e3-f84d-5e85-b64f-266c2f54be93 | date | Date Completed:
8d12b47e-76a7-40f8-883d-5e8cfddb8078 | signoff | AUTHORITY HOLDPOINT
3a3b3349-32b3-4155-a2d3-57ec1a873ac3 | checkpoint | 2.5 Type B Material
b6de7786-2ebb-59e3-bdd2-88b08901c7fc | note | FREQUENCY: Each Lot
2d7717db-2730-56f6-9f51-e768f533654a | note | ACCEPTANCE CRITERIA: Type B material shall be free of topsoil, deleterious and/or perishable matter. Type B shall have a minimum assigned CBR >5% and Assigned Percent Swell < 2.5%. Materials with swell greater than 2.5% can only be used as Type B material if approved by the superintendent.
de4c311e-4fad-5813-b20a-d43eaeac8a99 | note | REFERENCE DOCUMENTS: 204.04(c)
ebb5d02e-b628-5f42-930e-7d8d35bf6e99 | note | INSPECTION/TEST METHOD: Test Point
4f70ade5-0698-530e-8b70-ad08da4fab16 | note | RECORD OF CONFORMITY: Test Reports
c71bb65d-9aac-50fd-a36b-01f64f4c6ee5 | note | IP
1458fd14-f723-5c3b-b46f-e4c74f217a23 | note | RESPONSIBILITY: Site Engineer / Superintendent
18cbd72d-7a3b-5440-af0b-695ce57f08e2 | date | Date Completed:
81ed21a7-f55a-4363-b766-4a08a7efa18e | checkpoint | 2.6 Acceptance of Rock Subgrade (when applicable)
db11a445-a0be-5af9-b5b4-8184e3dc76b9 | note | FREQUENCY: Prior construction of the regulating layer
e22ce874-a3d7-5210-8e47-53405c59624a | note | ACCEPTANCE CRITERIA: HOLD POINT
1f4d7da2-f230-55e4-8338-461948c4454e | note | ○ Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
f2d75627-e524-5667-bac6-e243cf368281 | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
72e91fa5-48d8-598d-b469-ac303dae96b8 | note | REFERENCE DOCUMENTS: 204.06(f)
fac5d2db-1cae-527c-83a4-a47c62b36c21 | note | INSPECTION/TEST METHOD: Site Inspection/ Document Review
2d667551-9b67-5e52-939a-910a4f732a0b | note | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
61d3dceb-6934-51a1-ac6c-c4b515315204 | note | HP
09119aea-7373-5cbe-a486-b184ba43328b | note | RESPONSIBILITY: Site Engineer/ Superintendent
4a91920e-4536-5ac2-8f0b-650fcbc5892e | date | Date Completed:
68e5c353-724f-405c-9f5a-adaabdfa86e8 | signoff | AUTHORITY HOLDPOINT
520847a1-7c23-490b-97a4-6df72926d306 | checkpoint | 2.7 Unsuitable Material
323daa7c-a5ac-5900-8e6f-e6ec0fb7c1a7 | note | FREQUENCY: Each Lot
a2ecb495-4483-5a2e-957f-71db8672a6f1 | note | ACCEPTANCE CRITERIA: HOLD POINT
c09e2b2d-1596-57d1-b740-1d9cbd7c05dd | note | ○ Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review.
548698ef-8757-54ef-87b5-421884ef1556 | note | REFERENCE DOCUMENTS: 204.07(d)
20aaa280-b18c-515b-bb26-e69b506acbbc | note | INSPECTION/TEST METHOD: Visual Inspection
81791d72-cb0d-54c9-b5a3-6a287116a44a | note | RECORD OF CONFORMITY: This ITP Signed Off, Work Procedure
99f652d2-38cf-5453-9531-48fcd6fe6491 | note | HP
9b104fb8-17ab-5f65-ad13-24b3a76b19f3 | note | RESPONSIBILITY: Site Engineer/ Superintendent
f6ccb8a5-6d8c-5dda-bfc7-ab1af2764bbc | date | Date Completed:
348cbeab-bae8-463b-8676-8d6a00709b19 | signoff | AUTHORITY HOLDPOINT
c63d6ada-d230-4e34-a13e-bd4a2d0278c4 | checkpoint | 2.8 Groundwater
48d3b861-9fbc-5f42-aedd-2530ff07913b | note | FREQUENCY: Each Lot
ba66d295-176e-5106-8aff-817ba6356966 | note | ACCEPTANCE CRITERIA: HOLD POINT
6d6ee4d2-1332-53db-a2dc-4632119ffceb | note | ○ Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
d831d6a0-810a-5c2c-a519-2823043c86c7 | note | REFERENCE DOCUMENTS: 204.06 (h)
0d25939a-de83-58f8-b59b-63fa53ad254f | note | INSPECTION/TEST METHOD: Visual inspection
69a2eb79-73f9-5cbb-87c1-21251d6b783d | note | RECORD OF CONFORMITY: This ITP signed off, Work Procedure
84bea4da-5652-58b3-b50d-b8377048b3ab | note | HP
cdff3982-fd09-56b1-960a-68de902c5242 | note | RESPONSIBILITY: Site Engineer/ Superintendent
8540a718-eca2-59bf-a535-996c9d0e0bb7 | date | Date Completed:
f2843205-91b0-41e8-b4f7-44d4aef2e735 | signoff | AUTHORITY HOLDPOINT
529633bb-7275-4f85-b94f-4a96b82225bd | checkpoint | 2.9 Trimming and Level conformity
4ee68268-b510-5d45-b984-811e1bdcda75 | note | FREQUENCY: Each Lot
5cd83eca-144c-5154-8c2d-78fdeb22fc05 | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
95f78799-1a3f-57da-9a65-5f3696188661 | note | ○ Level tolerances:
b917797b-c3fc-51d5-a5e2-02cc75a9a8e9 | note | – Range x = +5, -15mm
5d207bd9-0148-5446-bed9-621d68e0d702 | note | – Max S = 12 mm
59ef12d0-833d-5c68-a6d0-a0947c31495c | note | ○ 80 measurements per lot (Scale A)
b63ccf20-6014-5a75-9884-9892740cb4f3 | note | – Range x = +5, -25mm
8d4298a9-283e-5262-8f7d-1565cf406271 | note | – Max S = 15 mm
5ef8f02e-ff2f-523b-a2e1-877dfa697eac | note | ○ 40 measurements per lot (Scale B)
b2f023de-ee30-5292-9c70-4e4fe4d97d67 | note | REFERENCE DOCUMENTS: 204.03(f)(g)(h)
bdd35211-3e11-550d-87d9-b60ad9f78bd4 | note | INSPECTION/TEST METHOD: Survey Report
f03d3755-7c5d-586a-ab69-a45bad93d1ca | note | RECORD OF CONFORMITY: Survey Record
c0fe898f-30c1-51cd-bc79-18943c7c4031 | note | SCP
11106bc9-a8bd-55c0-afea-fcf70dc7671c | note | RESPONSIBILITY: Site Engineer/ Surveyor
af574adb-b15b-5696-a94d-72f8e9cd9e70 | date | Date Completed:
0f86b799-5844-47a6-8f4e-b1070736e7dd | section | 3 - Testing
bc9cc799-b643-41c8-9c20-975c243250ec | checkpoint | 3.1 Proof Rolling
ddaba18d-d39f-5410-a4f6-aee6a6cefeeb | note | FREQUENCY: Each Lot
57b502ae-556d-5308-98b9-2222bcb83eaf | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173, before proceeding to subbase construction.
68753619-4725-59cf-a1dd-c590823aa400 | note | ○ The Contractor shall submit a test rolling procedure to the Superintendent including the method of preparing an area for test rolling, the extent of test rolling and a requirement to provide not less than 24 hours notice of the location and commencement time for the test rolling to the Superintendent.
cd64ca2b-49d5-50c3-adab-81adf5d36d66 | note | REFERENCE DOCUMENTS: 173.03, 204.12
db4fc166-42d7-5d70-9306-f02162f10c46 | note | INSPECTION/TEST METHOD: Visual Inspection
bfe32bb9-084e-5c7d-880f-9046f3cf4fa0 | note | RECORD OF CONFORMITY: This ITP signed off
f17fc5ac-e72a-5422-807e-18c8dfaf44bf | note | HP* WP
a79c5175-5624-58b8-9fff-134715fa6aae | note | RESPONSIBILITY: Site Engineer/ QAV
dcb079dd-777b-59e0-b082-2d8debdba3d6 | date | Date Completed:
13e1b6d0-9e53-48e9-8e9b-1f6f5005eddd | checkpoint | 3.2 Compaction Testing
abc22811-c840-5992-b948-9ae3df6fe68e | note | FREQUENCY: Each Lot
3bc05732-42e1-533e-b5b7-8542046feb10 | note | ACCEPTANCE CRITERIA: Ripped and re-compacted material below Cut Floor Level = minimum compaction 99% MDD.
9ec8cb80-5601-5d82-b310-d3ed9e798577 | note | ○ Type B Material placed within 400 mm of top of Type B Material = minimum compaction 99% MDD.
10b66637-9338-5571-a90b-b907fb6cbc95 | note | ○ Type B material 400mm below the top of Type B material and Top 150mm of where fill is to be constructed = minimum compaction 97% MDD.
17c76ed2-2355-58be-b819-26960a36b8b8 | note | REFERENCE DOCUMENTS: Table 204.131
d1c596e3-d5f1-5be9-bb49-7103663b4fad | note | INSPECTION/TEST METHOD: Test Point
2fe9e162-11c2-515e-a885-0237346cf665 | note | RECORD OF CONFORMITY: Test Records, Lot Register
0d401493-e3dc-5d24-8e3e-db5a45584a08 | note | TP
d12ba0f2-dc20-5804-9b58-0cf190840ab8 | note | RESPONSIBILITY: Site Engineer
5307e531-53aa-582c-acb4-cf9e33d6ada1 | date | Date Completed:
322d4055-e4d5-4161-8f24-fea433470604 | checkpoint | 3.3 Materials Property Testing
654718eb-72fb-5ba3-bf09-696db7c57dcc | note | FREQUENCY: Each Lot
ff0045d9-c52e-5807-9d19-e190ce2d27e0 | note | ACCEPTANCE CRITERIA: Refer to Reference Documents for particular Frequency of Testing and Material Properties Testing Requirements.
52aca5c9-3c21-5ef4-9e14-f7d43aa52643 | note | ○ Table 204.161 for Project Specific Scales for each applicable Road Name or Area.
fa1b8d13-3232-5b31-8058-1edda881493f | note | REFERENCE DOCUMENTS: Tables 204.141, 204.142, 204.161
84f993c5-4f09-51f8-bf92-7d863e18d7aa | note | INSPECTION/TEST METHOD: Verify
25e52858-1eae-51e1-80c6-0bbbb4d9fa0e | note | RECORD OF CONFORMITY: This ITP Signed, Test Records
b8cd9b0e-4a01-5a84-835f-5dd297ad718c | note | TP
2730d33c-f14b-50c2-9af1-fd92b2659ce9 | note | RESPONSIBILITY: Site Engineer
bc563173-1b81-5226-a628-d8f4db97854f | date | Date Completed:
39ac548f-3700-4231-beba-9becf60e8c94 | checkpoint | Final Inspection
1824ad7b-2037-5e72-923e-c95f1c4c7009 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
98480b67-069c-5523-b958-20807d491c24 | textbox | Print Name:
c6dac621-e790-528a-a936-7af5f6ae13a3 | textbox | Position:
71550dec-7b12-55ef-a6cb-542898c0718f | date | Work Completed On:
fce7aed6-771a-47b2-bdb4-e0a52c44e5aa | signoff | Add Signature
86c7edee-b38e-4391-b135-bbba6c1d17e9 | checklist | DTM-ITP-006- Unbound Flexible Pavement Construction Rev0 | itp | DTM-ITP-006- Unbound Flexible Pavement Construction
1a8775ca-8808-4828-be75-2ee2b40877ad | section | 1 - Preliminary Works
5eddf287-a6f1-4e48-abac-dad025f95fbd | checkpoint | 1.1 - Check for correct documentation
e05b1258-b4c6-54ec-a92f-959fc204c337 | note | Frequency - Prior to commencing any activity
a0756a10-4aa1-5475-a467-03928b5cef17 | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
2ac1746c-a1ab-5955-a62d-9e69207e7b0a | note | – using the correct and complete set of drawings
73568102-2ed7-5fb3-b92c-f5964bed16af | note | – all drawings are the latest revision
34696bd9-bf22-5ef8-885b-1e66054b2e9a | note | Reference Documents - IFC Drawings
b9ea98d3-758f-56c4-aed2-4cb2c33082de | note | Inspection/Test Method - Visual inspection
fa53e52c-57b5-51df-9e5e-4fe215d03c18 | note | Record of conformity - This ITP signed
5a5efa5c-a2dc-56ae-a7d6-b9c607924274 | note | HP*
0ad274df-2c8b-5d9a-84ee-c8403439b2a1 | note | Responsibility - Site Engineer
9145bf74-02d9-54d4-8292-89ab14a5dc9f | date | Date Completed:
e3d763b4-d05b-4437-b648-a8952cd9ec03 | checkpoint | 1.2 - Material Mix Design
efce4ed2-f7d0-52db-95de-4fe0e0fa5487 | note | Frequency - Prior to commencing works
66205b41-111a-5751-b121-5500c25fe130 | note | Acceptance Criteria - Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175.
3f325e40-6cce-5bfd-9729-cdb6fe74cbde | note | Reference Documents - 812.04, VicRoads RC500.02
87fdf747-4978-5281-b676-f39ad1b198f2 | note | Inspection/Test Method - Document Review
db1b15b3-cdd3-56df-981a-890f8c7eb3ef | note | Record of conformity - Crushed Rock Registration, This ITP signed
2367df4c-24b9-5f02-a72a-28c7aef4852a | note | HP
cc66152d-9eb9-50e1-a3ed-5f1f02f4290d | note | Responsibility - Site Engineer / QAV
3510e962-d684-530b-8eae-d48d1936fb71 | date | Date Completed:
f54053d9-69ff-4bdb-be08-e864b9434296 | signoff | AUTHORITY HOLDPOINT
7bb1899d-ef75-43c6-a077-08316a5628bc | checkpoint | 1.3 - Material Quality
3dedca60-ea26-5995-8b06-f7eaa549da80 | note | Frequency - Prior to commencing works
445e555d-e4d0-5439-a734-4e3803f790bd | note | Acceptance Criteria - Material complies with the Class 4 specification for crushed rock
e1effdb3-545c-5927-93fc-b7a2fbe7cc09 | note | Reference Documents - 812, Table 812.121
1060e3f6-cc1d-5052-8114-88cef4ef8e05 | note | Inspection/Test Method - Measure
10395d39-0e6d-5f2f-96ae-ab051e277063 | note | Record of conformity - Test Results
08ebec4d-3c23-595e-a057-f1fea8f07a09 | note | IP
7c7857cd-aa37-58bc-9aae-105293ce53b3 | note | Responsibility - Site Engineer
7bf14732-7239-593d-8158-cfbd8f78b720 | date | Date Completed:
71ca29a6-b1d3-4b76-96fa-2b069695d14a | section | 2 - Placement
a8574eba-4b79-408f-80ec-d218634417a8 | checkpoint | 2.1 - Layer Thickness
01aa338c-6f4c-5883-bf53-60c31453ce81 | note | Frequency - Each layer
b9be0ccc-cd61-5695-b974-9b052f97db5c | note | Acceptance Criteria - In addition to complying with pavement layer surface tolerances specified in Clause 304.06(b), the following tolerances shall apply to the thickness of any pavement layer:
96f633b2-02d4-5565-8694-df1c2076620c | note | (i) the subbase course shall be not less than the specified thickness by more than 15 mm;
4afb7f21-810c-5c38-b010-c01a1717e69a | note | (ii) the base course shall be not less than the specified thickness by more than 10 mm and the average thickness of base over every 100 m section, over the full carriageway width, shall be not less than the specified thickness;
3731f1e3-52ad-5b9d-81c9-35477fbfb62a | note | (iii) the combined thickness of subbase and base courses shall be not less than the specified thickness by more than 15 mm.
718ea684-c783-593c-9bdc-55edf1e0705a | note | Reference Documents - Drawings and 304.06(c)
3d28ebb9-d6a4-567c-8c40-353b74407110 | note | Inspection/Test Method - Visual and Measure
af432db7-84ad-5584-afda-fe469c64dbd8 | note | Record of conformity - This ITP signed
2d737984-8822-5e49-bceb-4a921cedb5fa | note | IP
8efe5d45-7fce-55d3-8379-fd1ced244ba9 | note | Responsibility - Site Engineer
443f77d9-f154-5c6e-aa50-42f7e14f0d85 | date | Date Completed:
62cf241d-6e12-464f-b479-2e259baba906 | checkpoint | 2.2 - Jointing
1febb21e-ab73-5d4b-99de-4e5e947ed256 | note | Frequency - Each lot
80d1b681-0354-507b-934a-f00d2ea84d37 | note | Acceptance Criteria - The layout of joints shall conform to the following requirements:
c512cd25-58da-5d43-962a-2d1c865e9c55 | note | (a) material shall be spread in such a manner as to minimize the number of joints;
9a94eac2-c6ad-5759-ae24-4069fe963a81 | note | (b) for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
63921b0e-d161-50be-8422-f3118dff2a40 | note | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
81a1dbbc-58d6-57cf-ae19-557e05516638 | note | (d) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
77a0305c-a928-5ffe-817d-56611733b9a5 | note | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
2968fb0f-887c-57f4-8c7a-6282657de1fa | note | Reference Documents - 304.07
ccd9c6a2-3c9e-553f-94bb-a863e3099ec3 | note | Inspection/Test Method - Visual Inspection
6fc41273-9e14-51ad-97af-4e60cbbcb55c | note | Record of conformity - This ITP signed
2ef0ba38-335f-57ee-b854-6298b3141c87 | note | IP
7dc5dec1-74f3-5df8-9dbc-adaadb6aa6e8 | note | Responsibility - Site Engineer
9eeefbfb-3ee5-5f12-b4d4-448167661dfb | date | Date Completed:
0df55d27-e8a1-4c0a-a3bc-6a8969eedcc9 | checkpoint | 2.3 - Test Rolling
2f71ffd5-7bf9-51e2-8afc-14b7f476ea22 | note | Frequency - Each lot
18ca211a-b7e4-5ae8-8c79-840b0b5db85d | note | Acceptance Criteria - All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173, prior to acceptance of the layer.The Contractor shall provide for the Superintendent to be present during all test rolling.
09ea5a48-5a25-5199-a05a-985fb2944899 | note | Reference Documents - 304.08
8cabdd34-716b-5371-835d-06fd43f6f254 | note | Inspection/Test Method - Test Roll
fe1290bd-5dbd-5bc9-af6d-3c519a8bc20a | note | Record of conformity - Witness Point
fb993113-0f33-51c5-9691-31242a05f680 | note | HP
84a099d2-9477-5585-9778-37cf4f6dfd40 | note | Responsibility - Site Engineer / QAV
4ae2c90c-f022-56b2-9344-ad6d64fcc93a | date | Date Completed:
049e51fd-ce8d-41f9-b9b2-7b6750f138bd | signoff | AUTHORITY HOLDPOINT
1efc5127-2654-4b11-bc08-9f7da2354171 | section | 3 - Testing and Conformance
98dde69d-9e6a-4a4c-a0c0-d9b6155ded2d | checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
351f6066-fce6-5750-b37c-dd65d1cb8993 | note | Frequency - Prior to Testing
90f8f1a0-4bac-58df-86cc-ebd5f1c74394 | note | Acceptance Criteria - Scale B - The first lot of each material type shall be tested to demonstrate compliance with the material property requirements specified in Clause 204.04. Where the first lot of each material type satisfies the material property requirements in, no further testing will be required unless changes are observed or where directed by the Superintendent.
a9c48088-e400-5a16-bf5d-8f248fe6a238 | note | Reference Documents - 204.161
056c3e23-ec99-5b12-a2d5-8dacc1833f35 | note | ○ 304.08 (a)
f4870894-c595-5676-89c1-3655dcb6d411 | note | ○ 304.11 (b)
1499bbc4-97d8-5445-b40f-dc63e62c8c3c | note | ○ 304.11 (c)(iii)
6bea931e-dc01-5ca3-ada1-c4bb28aa466e | note | ○ Table 304.111
1a4801c9-34db-5be8-9348-8fea4a05c46e | note | ○ Table 304.121
5e276bec-eb13-548c-8c42-393c0d553f7e | note | Inspection/Test Method - Document Review/ Site Inspection
73c78cc6-768c-545a-9ada-7898de088814 | note | Record of conformity - Signed ITP
dd044276-bd46-5e64-962e-b0711eb1955a | note | AP
414f04fb-dca9-5aff-9256-00bbdc1abaea | note | Responsibility - Site Engineer
197ba428-6e86-5104-8ea1-ffe601920e8d | date | Date Completed:
d41c5992-c0db-4ecb-8171-975cab200ba7 | checkpoint | 3.2 - Compaction Testing
a472dce2-9ff2-5994-932e-362682476d9a | note | Frequency - Every Lot, Every second lot (reduced frequency)
bb0d979a-b833-5736-9686-a1e6fa708150 | note | Acceptance Criteria - Minimum Characteristic Density Ratio (CDR) of not less than 97% (subbase) for Scale B, using Modified compaction effort. Material during compaction shall have a moisture content of not less than 85% of optimum.
e0505b7c-c60f-54a8-960b-01b8591bc482 | note | Reference Documents - 304.081, 304.11 (b), Table 304.111
d26f15f8-7c89-59b5-98c3-8bab5b325761 | note | Inspection/Test Method - Test point
3e45ed57-aae7-567c-b1b6-fec8751a6f2d | note | Record of conformity - This ITP signed off; Test reports
c008aed0-3675-51ef-ae40-e0afede0af49 | note | TP
b50aa93d-9ce8-529d-b693-bdd2285e2fe6 | note | Responsibility - Site Engineer
4501c3ee-d325-5362-ba4c-4b16adbc3d75 | date | Date Completed:
706b13e7-d288-40bf-b151-8a4655b98238 | checkpoint | 3.5 - Completed Surface Level Compliance
ff2c3ae3-d37a-5419-bbbf-b7d9e2e63b1a | note | Frequency - Each lot
e75f8fd1-102a-5a01-be58-1ef58ec3d89e | note | Acceptance Criteria - Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
fbe73e80-9490-5885-87a9-ed82737f6d98 | note | ○ Shape: no point deviation > 8mm from 3m straight edge in any direction
ba3534f3-4f9f-559e-9177-c43499e4bc11 | note | ○ Surface level tolerances: As per table 304.062 below
8bfe2e7d-29cb-53e9-af9c-7daea85c14ae | note | – 40 measurements per lot (Scale B - Davey Street, Macquarie Street, Southern Outlet)
0e1f2ab3-3508-5de6-ae4e-3db3213e78ce | note | Reference Documents - 304.06, IFC Drawings Table 304.062
c12859b6-4009-5df4-a6ea-511f6a6d619f | note | Inspection/Test Method - Survey
a42b464b-e520-596e-b5ac-b88f63744b8c | note | Record of conformity - This ITP signed off; Survey Report
e447ac31-dce0-593e-8013-e7971a73ddb2 | note | TP
b798766c-d316-5000-92ab-3e699d2496e9 | note | Responsibility - Site Engineer
4c6ab624-8013-5ec4-9fd1-8db368c92a2e | date | Date Completed:
075f394c-80ce-4057-a11e-ef7e5dc8cf54 | checkpoint | 3.6 - Pavement Dryback and Embedment
d1c0858a-1de0-5165-9097-50d7128ee45f | note | Frequency - Prior to sealing works (only for uppermost layer below asphalt)
ce41f9eb-42b7-5f2a-ad75-d6c0ae059d08 | note | Acceptance Criteria - Scale A - The uppermost pavement layer after preparation of the surface and prior to sealing shall be allowed to dry back so the moisture content of the layer meets the requirements of Table 310.031 for each test lot. Also, pavement embedment shall be assessed by Ball Penetration testing when required as detailed in Table 310.031
9a02ee6a-2e52-590e-9887-d6a1df98ff69 | note | Reference Documents - 310.03, Table 310.031
507695b9-a376-56a0-bdc2-769c1fdac2ce | note | Inspection/Test Method - Review
280075d4-4c40-558c-9e3d-558fbb8ff1df | note | Record of conformity - Test Results
f870b41d-28c1-588a-9508-ffae6031b3b0 | note | TP
5b9531e0-7048-50dd-9331-94940801f093 | note | Responsibility - Site Engineer
d667f806-b586-545b-83e1-9ef7b9efce8d | date | Date Completed:
e82ffce7-6014-48f3-a443-0291bd6dd3c5 | checkpoint | Final Inspection
c0d66bd6-2c7f-5526-bc16-161f4f316dba | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
4b4094f9-cca4-5ada-812b-56aaf4886a19 | textbox | Print Name:
3ce844e7-d77d-5973-86a8-df16e2cf17d6 | textbox | Position:
a2539846-c8ab-5499-b45b-9ecd077a6fdc | date | Work Completed On:
85fd8af8-39c4-474d-ae23-c75ec95c4642 | signoff | Add Signature