## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DTM-ITP-004- Service Relocations - Telstra and NBN | itp |  |  |  |  | DTM-ITP-004- Service Relocations - Telstra and NBN Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP/TGS, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 1.3 - Scheduling trenching works with Telstra/NBN contractor
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Provide Telstra with an accurate date for when the trenches will be available for cable installation and when final ground levels will be established
label | REFERENCE DOCUMENTS: APPENDIX L
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Service Installation Programme
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 1.4 - Proving Services
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Underground services shall be proved by clearly marking the location of the service on the ground and physical exposure of relevant services at appropriate locations, in accordance with service authority requirements.
label | REFERENCE DOCUMENTS: 160.12B
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer/QAV
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.1 - Survey set-out
label | FREQUENCY: As required
label | ACCEPTANCE CRITERIA: Prior to setting out trench, advice should be sought from Telstra/NBN for accuracy of cable routes. Cable routes shown on drawing are only approximate.
label | REFERENCE DOCUMENTS: APPENDIX L
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 2.2 - Excavation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The edges of all trenches located within a road pavement shall be sawcut
label | ○ Trench to be excavated to the nominal trench depth of 1.8m with a minimum width of 1.0m.
label | ○ If trench depth is greater than 1.5m; bench, batter or shore
label | ○ 5m EW shall be provided for all conduit bends
label | REFERENCE DOCUMENTS: APPENDIX L
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 2.3 - Material Assessment
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04.
label | REFERENCE DOCUMENTS: 204.06
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer/Superindentant
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Bedding
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bedding material shall be placed and compacted for the full width of the trench to a depth of not less than 80 mm on an earth foundation or 200 mm on a rock foundation.
label | REFERENCE DOCUMENTS: 733.06(B)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 2.5 - Installation of Conduits and Cables
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Conduits and cables to be installed by Telstra/NBN contractor.
label | ○ Once the bedding material has been laid and the conduits put in place, works shall not proceed prior to inspection by superintendent or representative.
label | ○ Conduit bends to be concrete encased as per Telstra Specifications
label | REFERENCE DOCUMENTS: 160.12A, 733.06(B)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed WP
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Back Fill of Trenches
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Conduits to be backfilled as per Table 733.061
label | ○ Conduits shall be backfilled with stablised sand to 100mm above top of conduits as per AS3000.
label | REFERENCE DOCUMENTS: 733.06, APPENDIX L
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 2.7 - Compaction
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bedding, and backfill shall have during compaction a uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Standard compaction test.
label | ○ All pavement material shall have during compaction, uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Modified Compaction test.
label | ○ Backfilling beneath areas to be paved shall be assessed for compaction:
label | – The number of tests per lot shall be three
label | – Compacted to a mean value of density ratio of not less than 95% (passing 37.5mm AS sieve)
label | ○ Backfilling of pavement materials shall be assessed for compaction:
label | – Compacted to a mean value of density ratio of not less than 98%
label | REFERENCE DOCUMENTS: 733.06 (D)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports
label | TP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 2.8 - Installation of marker tape
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Marker tape to be installed by Telstra/NBN contractor
label | REFERENCE DOCUMENTS: 160.12A
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 2.9 - Cable Pits & Pit Lids
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Cable pit excavation to be provided by Fulton Hogan
label | ○ Cable pit bedding to be installed and approved by Telstra/NBN contractor
label | ○ Cable pits and lids to be installed by Telstra/NBN contractor
label | ○ Lift Analysis to be provided to Fulton Hogan by Telstra/NBN contractor 24-48hrs prior to lift.
label | REFERENCE DOCUMENTS: 160.12A
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
section | 3 - Completion
checkpoint | 3.1 - Cleaning of Site
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Surplus excavated material shall be removed from road reserve. All affected areas shall be restored to similar conditions that existed prior to work.
label | REFERENCE DOCUMENTS: 733.09
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 3.2 - Recording/As Built
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Record any changes to cable routes on red line mark-ups. The final alignment of installed Telstra and NBN conduits shall be updated on the service plan
label | REFERENCE DOCUMENTS: 160.12A
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed, As Built Drawing
label | *HP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
holdpoint | Add Signature
checklist | DTM-ITP-005- Service Relocations - Power (TasNetworks) | itp |  |  |  |  | DTM-ITP-005- Service Relocations - Power (TasNetworks) Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP/TGS, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 1.3 - Scheduling trenching works with TasNetworks
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Provide TasNetworks with an accurate date for when the trenches will be available for cable installation and when final ground levels will be established
label | REFERENCE DOCUMENTS: AS-32433
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Service Installation Programme
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 1.4 - Proving Services
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Underground services shall be proved by clearly marking the location of the service on the ground and physical exposure of relevant services at appropriate locations, in accordance with service authority requirements.
label | REFERENCE DOCUMENTS: 160.12B
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer/QAV
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Excavations within 3m of poles or stays, Exacavtions within 1m of Underground Assets
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Advice must be sought for any excavations within 3m of poles or stays, or 1m of Underground assets
label | REFERENCE DOCUMENTS: 160.12A
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer/ TasNetworks
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Survey set-out
label | FREQUENCY: As required
label | ACCEPTANCE CRITERIA: Prior to setting out trench, advice should be sought from TasNetworks for accuracy of cable routes. Cable routes shown on drawing are only approximate.
label | REFERENCE DOCUMENTS: AS-32433
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 2.2 - Excavation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Check drg AS-32433 to confirm trench detail
label | ○ The edges of all trenches located within a road pavement shall be sawcut
label | ○ Trench to be excavated to the nominal trench depth shown on drg AS-32433
label | ○ If trench depth is greater than 1.5m; bench, batter or shore
label | REFERENCE DOCUMENTS: AS-32433
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 2.3 - Material Assessment
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04.
label | REFERENCE DOCUMENTS: 204.06
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer/Superindentant
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Bedding
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: TasNetworks to place sand bedding
label | REFERENCE DOCUMENTS: 160.12A
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 2.5 - Installation of Conduits and Cables
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Conduits and cables to be installed by TasNetworks.
label | ○ Once the bedding material has been laid and the conduits put in place, works shall not proceed prior to inspection by superintendent or representative.
label | REFERENCE DOCUMENTS: 160.12A, 733.06
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed WP
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Back Fill of Trenches
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Conduits to be backfilled with approved FCR or site won backfill material under the approval of TasNetworks
label | ○ Conduits may be backfilled with stab sand under the approval of TasNetworks
label | REFERENCE DOCUMENTS: 733.06, AS-32433
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 2.7 - Compaction
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bedding, and backfill shall have during compaction a uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Standard compaction test.
label | ○ All pavement material shall have during compaction, uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Modified Compaction test.
label | ○ Backfilling beneath areas to be paved shall be assessed for compaction:
label | – The number of tests per lot shall be three
label | – Compacted to a mean value of density ratio of not less than 95% (passing 37.5mm AS sieve)
label | ○ Backfilling of pavement materials shall be assessed for compaction:
label | – Compacted to a mean value of density ratio of not less than 98%
label | REFERENCE DOCUMENTS: 733.06 (D)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports
label | TP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 2.8 - Installation of marker tape
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Marker tape to be installed by TasNetworks
label | REFERENCE DOCUMENTS: 160.12A
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 2.9 - Cable Pits & Pit Lids
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Cable pits and lids to be installed by TasNetworks
label | REFERENCE DOCUMENTS: 160.12A
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
section | 3 - Completion
checkpoint | 3.1 - Cleaning of Site
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Surplus excavated material shall be removed from road reserve. All affected areas shall be restored to similar conditions that existed prior to work.
label | REFERENCE DOCUMENTS: 733.09
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 3.2 - Recording/As Built
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Record any changes to cable routes on red line mark-ups
label | REFERENCE DOCUMENTS: 160.12A
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed, As Built Drawing
label | *HP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
holdpoint | Add Signature