## Concrete
CIVIL INSPECTION & TEST PLAN
Concrete - ITP |  |  |  |  | Rev: | Originator | Date | Approved | Date
[5 empty] | 0 | Cameron Hinge | 2024-06-14
| H - HOLD |  |  |  | 1
P - PERFORM
W - WITNESS
R - REVIEW
ITEM | TASK | SPECIFICATION REFERENCE | ACCEPTANCE CRITERIA | DATE/SIGN |  |  | COMMENTS
1 | Issued For Construction Drawings | IFC Drawings Issued by Client/Engineer | Issued For Construction Drawings Available | Contractor Rep - H
2 | Excavate to depth to ensure adequate cover over the batten to gain minimum cover as per drawing detail | Drawing detail Permit to Work | Permit to Work issued Excavation enough to ensure formwork can be constructed to give minimum cover to concrete over batten | Contractor Rep - P
3 | Formwork & Steel | IFC Drawing | All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's. All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted. All reinforcing and formwork to comply with IFC drawings | Contractor Rep - P
4 | Pour Concrete | Prepour Inspection | Prepour Inspection completed and signed off prior to pouring concrete | Civil Inspector - H
5 | Apply Sealant | IFC Drawing | Sika Flex Fire400 applied as per manufacturers instructions and IFC Drawing | Contractor Rep - P Civil Inspector - W
6 | As Built & Final Design Documentation |  | Final ASBUILT data picked up of what foundations have had concrete beams added to them | Contractor Rep - H