## Cover
| Project: | TLC- General Project
CONTENT:
1 | Module Structure
2 | Sub-Structure
3 | Drain Water & Vent System
4 | Hot & Cold Water System
5 | Sprinkler System
6 | Duct System
7 | Electrical Works
8 | Internal Wall Linings
9 | Internal Painting
10 | Water Proofing System
11 | Tiling & Grouting
12 | Sanitary Wares
13 | Glazing Works
14 | Internal Finishes
15 | Doors
16 | Sliding Doors
17 | Windows
18 | External Wall Linings & Finishes
19 | Roof Water Proofing
20 | Passive Fire System
21 | Final Inspection
TLC Inspection Check Sheet

## Module Structure
STRUCTURAL - INSPECTION CHECK SHEET
Organization: | TLC Modular
Project Name: | TLC- General Project
DETAILS
Consent Number: |  |  |  | Date:
# | Item Descriptions | Response Type |  |  | Pictures
PREPARATORY WORKS
1 | Inspect - Preparatory Steel works (Shearing,Drilling & Cutting) | Yes | No | N/A
2 | Inspect - Blasting works for steel materials (SA-2.5) | Pass | Fail | N/A
3 | Inspect - Painting (D.F.T) works for steel materials (ISO 8503 or required Project Painting Specifications) | Pass | Fail | N/A
4 | Inspect - Bottom, Top & Ceiling Frames on JIG (Length & Width and Diagonal Dimensions as per approved Drawing) | Yes | No | N/A
FABRICATION - FRAMES ASEMBLY
5 | Ensure & Check - Partial Frames, Main Columns, Ceiling & Floor Joists | Yes | No | N/A
6 | Inspect - Full Welding | Pass | Fail | N/A
7 | Inspect - Painting touch up or Final coat (D.F.T) as per ISO 8503 or required Project Painting Specifications | Pass | Fail | N/A
FINAL INSPECTIONS
8 | Inspection - Completed Work and Record As Built Dimensions | Yes | No | N/A
INSPECTOR SIGNARUTE
9 | TLC Inspector Name - | Signature - Date of Sign Off's -

## Sub-Structure
SUB-STRUCTURE - INSPECTION CHECK SHEET
Organization: | TLC Modular
Project Name: | TLC- General Project
DETAILS
Consent Number: |  |  |  | Date:
# | Item Descriptions | Response Type |  |  | Pictures
PREPARATORY WORKS
1 | Inspect - Preparatory Steel works (Bending,Drilling & Cutting) | Pass | Fail | N/A
2 | Inspect Section Length/Width/ Drill Holes Dimension/Location | Pass | Fail | N/A
FIT-UP WORKS
3 | Inspect - Fit-Up as per Drawing | Pass | Fail | N/A
WELDING WORKS
4 | Inspect - Full Welding | Pass | Fail | N/A
NON DESTRUCTIVE EXAMINATION
5 | Inspect - MPI/UT | Pass | Fail | N/A
SURFACE PREPARATION
6 | Inspect - Blasting | Pass | Fail | N/A
ANTI CORROSION
7 | Inspect - D.F.T - Painting/Hot-Dip Galvanizing as per Painting Specification | Pass | Fail | N/A
PART IDENTIFICATION
8 | Inspect - TAG/Part Mark | Yes | No | N/A
INSPECTOR SIGNATURE
9 | TLC Inspector Name - | Signature - Date of Sign Off's -

## DWV System
DRAIN, WASTE & VENT SYSTEM - INSPECTION CHECK SHEET
Organization: | TLC Modular
Project Name: | TLC- General Project
DETAILS
Consent Number: |  |  |  | Date:
# | Item Descriptions | Response Type |  |  | Pictures
PREPARATORY WORKS
1 | Ensure the Materials are Approved as per the Specification | Yes | No | N/A
DRAIN, WASTE & VENT - INSTALLTION
2 | Ensure the Pre-cut Pipe Penetrations (holes) | Yes | No | N/A
3 | Install waste service in accodance with drawing design | Yes | No | N/A
4 | All pipework secure and supported with Brackets and Clips | Yes | No | N/A
5 | Pipework installed with correct grades and falls | Yes | No | N/A
FINAL INSPECTIONS
6 | Test DWV As Per The standard (AS/NZS-3500) 15kpa-3 min | Pass | Fail | N/A
7 | Cleaning & Protection | Yes | No | N/A
INSPECTOR SIGNARUTE
8 | TLC Inspector Name - | Signature - Date of Sign Off's -

## HWC System
HOT & COLD WATER SYSTEM- INSPECTION CHECK SHEET
Organization: | TLC Modular
Project Name: | TLC- General Project
DETAILS
Consent Number: |  |  |  | Date:
# | Item Descriptions | Response Type |  |  | Pictures
PREPARATORY WORKS
1 | Ensure Materials as per Specification/Drawing | Yes | No | N/A
INSTALLATION - HOT & COLD WATER SYSTEM
3 | Ensure the Pipes Sizes | Yes | No | N/A
4 | Install Hot & Cold water service in accordance with drawing design | Yes | No | N/A
5 | Connection Valves/Taps(Wherever Required) | Yes | No | N/A
6 | Install Sleeves (While Run through Metals) | Yes | No | N/A
8 | Secure Hangers, Clips, Brackets | Yes | No | N/A
9 | Ensure no cross connection between Hot and Cold services | Yes | No | N/A
Final Testing - Hot & Cold Water System
10 | Test Hot and Cold Water Service As Per The Standard AS/NZS: 3500 1500 Kpa - 30 mins or Relevant country standard | Yes | No | N/A
11 | Remove All Residual Water From Pipe Sections | Yes | No | N/A
INSPECTOR SIGNARUTE
12 | TLC Inspector Name - | Signature - Date of Sign Off's -

## Sprinkler System
SPRINKLER SYSTEM- INSPECTION CHECK SHEET
Organization: | TLC Modular
Project Name: | TLC- General Project
DETAILS
Consent Number: |  |  |  | Date:
# | Item Descriptions | Response Type |  |  | Pictures
PREPARATORY WORKS
1 | Verify the materials, pipe and sprinkler type as per the drawing or spec. | Yes | No | N/A
INSTALLATION - SPRINKLER SYSTEM
2 | Location of sprinkler, ensure the distance from ceiling and wall as per the drawing and standard | Yes | No | N/A
3 | Ensure piping adequately supported by brackets, clips or hangers. | Yes | No | N/A
4 | Pipeline shall be identified in accordance with as NZS 5807 | Yes | No | N/A
5 | Freezing protection if applicable | Yes | No | N/A
7 | Check the joints | Yes | No | N/A
FINAL TESTING - SPRINKLER SYSTEM
8 | Test Hot and Cold Water Service As Per The Standard AS/NZS: 4541. 1400 Kpa - 120 mins | Yes | No | N/A
9 | Remove All Residual Water From Pipe Sections | Yes | No | N/A
INSPECTOR SIGNARUTE
10 | TLC Inspector Name - | Signature - Date of Sign Off's -

## Duct System
DUCT SYSTEM- INSPECTION CHECK SHEET
Organization: | TLC Modular
Project Name: | TLC- General Project
DETAILS
Consent Number: |  |  |  | Date:
# | Item Descriptions | Response Type |  |  | Pictures
PREPARATORY WORKS
1 | Verify the Duct Materials are Approved as per drawing/Specification | Yes | No | N/A
INSTALLATION - DUCT SYSTEM
2 | Ensure all duct work installed as per drawing | Yes | No | N/A
3 | Ensure ducting adequately supported by brackets, clips or hangers. | Yes | No | N/A
4 | Duct Joint Shall be Sealed | Yes | No | N/A
5 | Check exhaust air intake and outlet grill locations | Yes | No | N/A
INSPECTOR SIGNARUTE
6 | TLC Inspector Name - | Signature - Date of Sign Off's -

## Electrical Work
ELECTRICAL WORK INSTALLATIONS - INSPECTION CHECK SHEET
Organization: | TLC Modular
Project Name: | TLC- General Project
DETAILS
Consent Number: |  |  |  | Date:
# | Item Descriptions | Response Type |  |  | Pictures
PREPARATORY WORKS
1 | Ensure the Materials are Approves as per Specifications | Yes | No | N/A
2 | Ensure the Cable Protection (Cable penetrates through steels) | Yes | No | N/A
INSTALLATIONS - CABLE RUN THROUGH
3 | Check the Cable Run through | Yes | No | N/A
4 | Verify the Proximity between power cables and other services (ex..Data Cable, Drain pipe, Hot & Cold Water Pipe, Gas Lines, etc…) | Yes | No | N/A
5 | Ensure the Connection Power points, Switch box, ceiling lights, LED lights & Main DB | Yes | No | N/A
6 | Ensure the screws are fastened tightly on steel plate support for Power points, Switch box, ceiling lights, LED lights & Main DB | Yes | No | N/A
FINAL INSPECTION
7 | Work Acceptance and Functional Test | Yes | No | N/A
INSPECTOR SIGNARUTE
8 | TLC Inspector Name - | Signature - Date of Sign Off's -

## Internal Wall Linings
INTERNAL WALL LININGS - INSPECTION CHECK SHEET
Organization: | TLC Modular
Project Name: | TLC- General Project
DETAILS
Consent Number: |  |  |  | Date:
# | Item Descriptions | Response Type |  |  | Pictures
WALL STUD/PARTITION WALLS
1 | Ensure the Section Sizes of the Material Used is as per Approved Shop Drawings | Yes | No | N/A
2 | Ensure the spacing of studs are as per Approved Shop Drawings | Yes | No | N/A
3 | Ensure the fastners are Fixed with correct spacings as per approved Shop Drawings | Yes | No | N/A
4 | Ensure all MEP Penetratins are done as per approved typical details | Yes | No | N/A
5 | Ensure all connections at Corner/Top/Bottom are fixed as per typical details in drawings | Yes | No | N/A
CFC or GYPSUM BOARDS
6 | Ensure Internal Celing Boards are Fixed as per approved Shop Drawings | Yes | No | N/A
7 | Ensure Internal Wall Boards are Fixed as per approved Shop Drawings | Yes | No | N/A
8 | Ensure Internal Floor Boards are Fixed as per approved Shop Drawings | Yes | No | N/A
9 | Ensure the Screw Fixing is followed as per approved screw spacing Matrix | Yes | No | N/A
10 | Internal Insulation Material Installation Check | Yes | No | N/A
11 | Internal Fire Selant Application Check | Yes | No | N/A
12 | Internal Boards Alignment,Joint Spacing Check | Yes | No | N/A
13 | Secondary Ceiling or Bulkhead Installation Check | Yes | No | N/A
14 | Joints, Corner and Interfacing & Repairs Check | Yes | No | N/A
FINAL INSPECTIONS
15 | Final Acceptance | Yes | No | N/A
INSPECTOR SIGNARUTE
16 | TLC Inspector Name - | Signature - Date of Sign Off's -

## Internal painting
INTERNAL PAINTING - INSPECTION CHECK SHEET
Organization: | TLC Modular
Project Name: | TLC- General Project
DETAILS
Consent Number: |  |  |  | Date:
# | Item Descriptions | Response Type |  |  | Pictures
PREPARATORY WORKS
1 | Ensure the Painting Surface Condition Check and Protection works | Yes | No | N/A
2 | Painting Surface Joint Treatment and Corner Bead installation Check | Yes | No | N/A
IN-PROCESS WORKS
3 | Internal Skimcoat application and Sanding Works Check | Yes | No | N/A
4 | Ensure the sealer undercoat application | Yes | No | N/A
5 | Ensure the correct application of Coating System With Recommended tools | Yes | No | N/A
6 | Ensure Final Coat Paint application (2 Coats) | Yes | No | N/A
7 | Check coating surface imperfections and defects repair check | Yes | No | N/A
FINAL INSPECTION | External Roof Water proofing Application/Protection/Slope(If any)Check
8 | Work acceptance. Check the color, gloss, texture,adhesion (Optional) | Yes | No | N/A
INSPECTOR SIGNARUTE
9 | TLC Inspector Name - | Signature - Date of Sign Off's -

## WP system
WATER PROOFING SYSTEM - INSPECTION CHECK SHEET
Organization: | TLC Modular
Project Name: | TLC- General Project
DETAILS
Consent Number: |  |  |  | Date:
# | Item Descriptions | Response Type |  |  | Pictures
PREPARATORY WORKS
1 | Check the floor and wall surface | Yes | No | N/A
2 | Internal Board Joint Sealant application | Yes | No | N/A
3 | Angle Fillet or Fiber Mesh Rendering and upturn on Joints check | Yes | No | N/A
APPLICATION OF WATER PROOFING MEMBRANE
4 | Ensure the Floor traps & drains are treated well | Yes | No | N/A
5 | Waterproofing Membrane Applications | Yes | No | N/A
6 | Check water proofing Membrane Thickness, number of coats and curing time | Yes | No | N/A
WET AREA WATERPONDING TEST
7 | Conduct Wet Area Waterponding and Spray Test (All wet areas) & Ensure No Leaks | Yes | No | N/A
FINAL INSPECTION
8 | Ensure the Waterproofed floor is protected | Yes | No | N/A
INSPECTOR SIGNARUTE
9 | TLC Inspector Name - | Signature - Date of Sign Off's -

## Tiling & Grouting
TILING & GROUTING - INSPECTION CHECK SHEET
Organization: | TLC Modular
Project Name: | TLC- General Project
DETAILS
Consent Number: |  |  |  | Date:
# | Item Descriptions | Response Type |  |  | Pictures
PREPARATORY WORKS
1 | Check Water proofed Surface Condition and MEP Clearance | Yes | No | N/A
LAYING OF SCREED / RENDRING
2 | Ensure Correct Application of Screed/Render | Yes | No | N/A
3 | Ensure Screed to Cure | Yes | No | N/A
4 | Check Screed Surface Slope | Yes | No | N/A
TILE SETTING OUT
5 | Ensure Correct Tile Setting Out ( Floor & Wall) | Yes | No | N/A
TILE INSTALLATION
6 | Ensure Correct Preparation and Mixing of Tile adhesive Material | Yes | No | N/A
7 | Ensure to use plastic spacers for specified size of tiling joints | Yes | No | N/A
8 | Check Tile Surface level and Installation | Yes | No | N/A
9 | Check for Defective tiles ( Damages) | Yes | No | N/A
GROUNDTING WORKS AND PROTECTION
10 | Ensure Tiles and Joints cleaned before Grouting | Yes | No | N/A
11 | Ensure Correct method of tile grouting and Curing | Yes | No | N/A
FINAL INSPECTION - TILING WORK
12 | Final Acceptance and slope Check | Yes | No | N/A
INSPECTOR SIGNARUTE
13 | TLC Inspector Name - | Signature - Date of Sign Off's -

## Sanitary wares
SANITARY WARES & ACCESSORIES - INSPECTION CHECK SHEET
Organization: | TLC Modular
Project Name: | TLC- General Project
DETAILS
Consent Number: |  |  |  | Date:
# | Item Descriptions | Response Type |  |  | Pictures
PREPARATORY WORKS
1 | Ensure the materials are approved as per Specification | Yes | No | N/A
INSPECTION OF WATER CLOSET PAN & FLUSHING SYSTEM
2 | Ensure Water Closet Installtion | Yes | No | N/A
3 | Ensure no leak from Flush Valve of Cistern Tank | Yes | No | N/A
4 | Test Water Closet | Yes | No | N/A
5 | Ensure Basin Intallation | Yes | No | N/A
6 | Test Basin | Yes | No | N/A
7 | Ensure Shower Installtion | Yes | No | N/A
8 | Test Shower | Yes | No | N/A
9 | Ensure Accessories Installation | Yes | No | N/A
10 | Remove all Residual Water From Floor Waste/Basin/Taps/Hoses | Yes | No | N/A
11 | Ensure all Fittings & Fixtures has been Properly Protected | Yes | No | N/A
INSPECTOR SIGNARUTE
12 | Inspector Name - | Signature - Date of Sign Off's -

## Glazing Works
GLAZING - INSPECTION CHECK SHEET
Organization: | TLC Modular
Project Name: | TLC- General Project
DETAILS
Consent Number: |  |  |  | Date:
# | Item Descriptions | Response Type |  |  | Pictures
PREPARATORY WORKS
1 | Ensure the Type, Size and thickness,Marking of materials | Yes | No | N/A
2 | Check glass or mirror for Damages | Yes | No | N/A
INSTALLING SHOWER ENCLOSURE
3 | Ensure setting out dimensions | Yes | No | N/A
4 | Check the Enclosure railing or Framing Installation | Yes | No | N/A
5 | Check Glass Fixing and Acessories Installation | Yes | No | N/A
6 | Check Sealant finish | Yes | No | N/A
INSTALLING MIRRORS
7 | Ensure setting out dimensions required | Yes | No | N/A
8 | Check Mirror Installation | Yes | No | N/A
9 | Check Sealant finish | Yes | No | N/A
INSPECTION - MIRROR AND SHOWER ENCLOSURE INSTALLATION
10 | Final Inspection and Protection work | Yes | No | N/A
INSPECTOR SIGNARUTE
11 | TLC Inspector Name - | Signature - Date of Sign Off's -

## Internal Finishes
INTERNAL FINISHES- INSPECTION CHECK SHEET
Organization: | TLC Modular
Project Name: | TLC- General Project
DETAILS
Consent Number: |  |  |  | Date:
# | Item Descriptions | Response Type |  |  | Pictures
PREPARATORY WORKS
1 | Check for Surafce condition and MEP Clearance | Yes | No | N/A
2 | Check Material,Accessories as per approved drawing and material specification | Yes | No | N/A
INSTALL - Floor Finishes
3 | Floor underlay installation check | Yes | No | N/A
4 | Approved Floor Finishes, Skirting,Termination Strip/threshold installation check | Yes | No | N/A
INSTALL - KITCHEN/WARDROBE/VANITY/LAUNDRY/STORAGE CABINETS,BEDHEAD,WALL PANELS
5 | Ensure Installation of Steel Backing Plates and Studs for Fixing | Yes | No | N/A
6 | Cabinet /Wallpanel/Bed Head Installation Check | Yes | No | N/A
7 | Check For Alignment,Plumb,Levelness | Yes | No | N/A
8 | Fillers application ( If Required) | Yes | No | N/A
9 | Check Installation of Shelves & Accessories | Yes | No | N/A
10 | Check Installation of Install Cabinet Door panels/Drawers & Handles | Yes | No | N/A
11 | Check Kitchen/Vanity/Cistern Top Stone Installation | Yes | No | N/A
12 | Kitchen Splash Back Installation | Yes | No | N/A
13 | Check for Operation,Touch up,Defects and Repairs | Yes | No | N/A
INSTALL - PELMET/CURTAINS
14 | Check pelmet Installation | Yes | No | N/A
15 | Check Curtain Installation | Yes | No | N/A
INSTALL - WALL PAPER
16 | Check Wall Paper Installation ( If Applicable) | Yes | No | N/A
FINAL INSPECTION & PROTECTION
17 | Conduct Final Inspection on the Completed Work | Yes | No | N/A
18 | Check the Cleaning & Protection | Yes | No | N/A
INSPECTOR SIGNARUTE
19 | TLC Inspector Name - | Signature - Date of Sign Off's -

## Doors
PRE FABRICATED DOORS - INSPECTION CHECK SHEET
Organization: | TLC Modular
Project Name: | TLC- General Project
DETAILS
Consent Number: |  |  |  | Date:
# | Item Descriptions | Response Type |  |  | Pictures
1 | Door Type | "Text Area - Type of Product to be mention"
PREPARATORY WORKS
2 | Setting out reference line in relation to wall alignment | Yes | No | N/A
3 | Ensure the dimensions of Frames,Door panel,IronMongeries,Architraves are as per approved drawings | Yes | No | N/A
4 | Check the Dimensions of Wall Openings are as per approved drawings | Yes | No | N/A
INSTALL DOOR FRAME
5 | Door Frame Installation | Yes | No | N/A
6 | Check the Frame alignment and plumb | Yes | No | N/A
INSTALL DOOR LEAF PANEL & IRONMONGERY
7 | Door Panel,Stopper Installation and Alignment Check | Yes | No | N/A
8 | Ironmongeries,Door Seal Installation | Yes | No | N/A
INSTALL ARCHITRAVE
9 | Frame and Wall Gap Filler Installation | Yes | No | N/A
10 | Architrave Installations | Yes | No | N/A
FINAL INSPECTION
10 | Check For operation,Defects, Patch nail holes and Repair Works (If any) | Yes | No | N/A
11 | Final Inspection & Protection Work | Yes | No | N/A
INSPECTOR SIGNARUTE
12 | TLC Inspector Name - | Signature - Date of Sign Off's -

## Sliding Door
PREFABRICATED SLIDING DOOR - INSPECTION CHECK SHEET
Organization: | TLC Modular
Project Name: | TLC- General Project
DETAILS
Consent Number: |  |  |  | Date:
# | Item Descriptions | Response Type |  |  | Pictures
PREPARATORY WORKS
1 | Setting out reference line in relation to wall alignment and Sufarce condition | Yes | No | N/A
2 | Check Materials,Dimensions,Markings are as per approved drawings | Yes | No | N/A
3 | Sliding Door Casing Installation (If Required) | Yes | No | N/A
INSTALL WINDOW FRAME
4 | Check the Dimensions of Wall Openings are as per approved drawings | Yes | No | N/A
5 | Check the Openings has been installed with Build Wrap/Flashing tapes as per Approved Drawing | Yes | No | N/A
6 | PreFabricated Sliding Door Frame Installation | Yes | No | N/A
7 | Check Frame alignment and plumb | Yes | No | N/A
INSTALL WINDOW SASH
8 | Check Fixed and Operating Sash Installation | Yes | No | N/A
9 | Check the Sash alignment,plumb and operation | Yes | No | N/A
INSTALL ACCESSORIES AND FLASHINGS
10 | Check Accessories,Flashing Installation | Yes | No | N/A
FINAL INSPECTION
11 | Check Gap Fillers, Sealant finishes | Pass | Fail | N/A
12 | Check the Water Tightness test and Final check | Pass | Fail | N/A
INSPECTOR SIGNARUTE
13 | TLC Inspector Name - | Signature - Date of Sign Off's -

## Windows
PREFABRICATED WINDOWS - INSPECTION CHECK SHEET
Organization: | TLC Modular
Project Name: | TLC- General Project
DETAILS
Consent Number: |  |  |  | Date:
# | Item Descriptions | Response Type |  |  | Pictures
PREPARATORY WORKS
1 | Setting out reference line in relation to wall alignment and Sufarce condition | Yes | No | N/A
2 | Check Materials,Dimensions,Markings are as per approved drawings | Yes | No | N/A
3 | Window Casing Installation (If Required) | Yes | No | N/A
INSTALL WINDOW FRAME
4 | Check the Dimensions of Wall Openings are as per approved drawings | Yes | No | N/A
5 | Check the Openings has been installed with Build Wrap/Flashing tapes as per Approved Drawing | Yes | No | N/A
6 | PreFabricated Windows Frame Installation | Yes | No | N/A
7 | Check Frame alignment and plumb | Yes | No | N/A
INSTALL WINDOW SASH | External Roof Water proofing Application/Protection/Slope(If any)Check
8 | Check Fixed and Operating Sash Installation | Yes | No | N/A
9 | Check the Sash alignment,plumb and operation | Yes | No | N/A
INSTALL ACCESSORIES AND FLASHINGS
10 | Check Accessories,Flashing Installation | Yes | No | N/A
FINAL INSPECTION
11 | Check Gap Fillers, Sealant finishes | Pass | Fail | N/A
12 | Check the Water Tightness test and Final check | Pass | Fail | N/A
INSPECTOR SIGNARUTE
13 | TLC Inspector Name - | Signature - Date of Sign Off's -

## External Wall Linings&Finishes
EXTERNAL FINISHES - INSPECTION CHECK SHEET
Organization: | TLC Modular
Project Name: | TLC- General Project
DETAILS
Consent Number: |  |  |  | Date:
# | Item Descriptions | Response Type |  |  | Pictures
PREPARATORY WORKS
1 | Ensure Surface condition, Cleaning and usage of Approved materials | Yes | No | N/A
2 | MEP clearance check | Yes | No | N/A
EXTERNAL INSTALLATIONS
4 | External insulation installation Check | Yes | No | N/A
5 | External Thermal Break installation Check | Yes | No | N/A
6 | External Board installation is as per approved Shop Drawings | Yes | No | N/A
7 | Ensure the fastners are Fixed with correct spacings as per approved Shop Drawings | Yes | No | N/A
8 | External Board Sealant Apllication Check | Yes | No | N/A
9 | External BuildWarp/Batten installation Check | Yes | No | N/A
10 | External Roof Water proofing Application/Protection/Slope(If any)Check | Yes | No | N/A
11 | External Facade installation as per approved Drawing Check | Yes | No | N/A
FINAL INSPECTIONS
12 | Final Acceptance and Wrapping | Yes | No | N/A
INSPECTOR SIGNARUTE
13 | TLC Inspector Name - | Signature - Date of Sign Off's -

## Roof Water Proofing
ROOF WATER PROOFING - INSPECTION CHECK SHEET
Organization: | TLC Modular
Project Name: | TLC- General Project
DETAILS
Consent Number: |  |  |  | Date:
# | Item Descriptions | Response Type |  |  | Pictures
PREPARATORY WORKS
1 | Ensure the materials are as per approved project specifications | Yes | No | N/A
2 | Ensure the surface is clean | Yes | No | N/A
WATER PROOFING MEMBRANE INSTALLATIONS
3 | Ensure Sealant is applied in all corners/gaps/screws | Yes | No | N/A
4 | Inspect application of Primer | Yes | No | N/A
5 | Inspect installation of Water proofing menbrane | Yes | No | N/A
6 | Check the Overlap as per Specification | Yes | No | N/A
7 | Check Installation of Ubar+Fastner (If Any) | Yes | No | N/A
8 | Ensure the membrane is sealed without Gaps | Yes | No | N/A
9 | Ensure the Gutter Hole is Treated and Sealed Properly | Yes | No | N/A
10 | Ensure the final Slope (if Any) | Yes | No | N/A
FINAL INSPECTIONS
11 | Final Cleaning/Protection | Yes | No | N/A
INSPECTOR SIGNARUTE
12 | TLC Inspector Name - | Signature - Date of Sign Off's -

## Passive Fire
PASSIVE FIRE SYSTEM- INSPECTION CHECK SHEET
Organization: | TLC Modular
Project Name: | TLC- General Project
DETAILS
Consent Number: |  |  |  | Date:
# | Item Descriptions | Response Type |  |  | Pictures
PREPARATORY WORKS
1 | Ensure the materials are as per approved project specifications | Yes | No | N/A
FIRE AND SMOKE BARRIERS INSTALLATIONS
2 | Ensure Penetration Openings are as Per Approved Engineering Judgements | Yes | No | N/A
3 | Enusre Fire Stop Sealant/Fire Collars is applied as per Approved Engineering Judgements | Yes | No | N/A
4 | Ensure Fire Stop penetarions are Mapped for Fire Walls | Yes | No | N/A
INSPECTOR SIGNATURE
7 | TLC Inspector Name - | Signature - Date of Sign Off's -

## Final
FINAL ACCEPTANCE - INSPECTION CHECK SHEET
Organization: | TLC Modular
Project Name: | TLC- General Project
DETAILS
Consent Number: |  |  |  | Date:
| Item Descriptions | Response Type |  |  | Pictures
1 | Main Door/Riser Door/Bathroom Door/Bedroom Door | Yes | No | N/A
2 | Ceiling Cornice/Bulk Head | Yes | No | N/A
3 | Wall Painting/Panels/Bed Head | Yes | No | N/A
4 | Wall/Floor Tiles & Grouting | Yes | No | N/A
5 | Timber/Vinyl Floor/Skirtings/Carpets | Yes | No | N/A
6 | Laundry/Mirror/Vanity/Wardrobe cabinet | Yes | No | N/A
7 | Windows/Sliding Doors/Curtains/Pelmet | Yes | No | N/A
8 | Kithen Cabinet/Kitchen Island | Yes | No | N/A
9 | Selant Finishes | Yes | No | N/A
10 | Kitchen/Cistern/Vanity Top/Splash Backs | Yes | No | N/A
11 | Shower Screen/Bath Tub Screen/Glass Shelves | Yes | No | N/A
12 | Threshold/Trims | Yes | No | N/A
13 | Access panel | Yes | No | N/A
14 | Towel Racks/Paper Holder/Robe Hook | Yes | No | N/A
15 | Shower Set/Bath Set | Yes | No | N/A
16 | WC/BathTub/Wash Basin | Yes | No | N/A
17 | Floor Drain covers/Floor Traps | Yes | No | N/A
18 | Finished Floor Protection | Yes | No | N/A
19 | Module Cleaning | Yes | No | N/A
INSPECTOR SIGNATURE
19 | Inspector Name - | Signature - Date of Sign Off's -