## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-193-CIV- SSB-Unbound Flexible Pavement-Scale B
ITP Description: |  | SSB-Unbound Flexible Pavement-Scale B
Discipline (e.g. CIV/STR/RAIL: |  | 193-CIV-
Revision Number: |  | 0
Revision Date: |  | 2024-08-23
ITP created by: |  | VM
ITP approved for use by: |  | VM
Special Notes to ConQA Team : |  | ITP for Station Street, Beaconsfield
Unbound Flexible Pavement (Base and Subbase other than CT)-Scale B
[9 empty] | Revision: | 0
[9 empty] | Date: | 45527
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | Reference Documents: IFC Drawings | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 |  | VicRoads Section 173 (10/9/2008) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 |  | VicRoads Section 304 (13/8/13) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 |  | VicRoads Section 801 (19/07/18) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.5 |  | VicRoads Section 812 (13/07/16) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries-Materials
2.1 | Crushed Rock Mix Design | Section 304.03 Section 304.05 Section 812.04 Table 812.121 IFC Drawings | All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product. Enter: Teambinder Material Approval number [free text box] | Document Review | Material conformance as per Table 812.121 | HP | NA | TeamBinder Material Approval Number
3 | Preliminaries-Documentation
3.1 | Subgrade Preparation | 304.04 | Prior to placing subbase material, the subgrade shall meet the requirements of Section 204. Enter Subgrade Lot No: | Document Review | Each Lot | HP* | PE | Underlying layer Lot number
4 | Pre-construction / Pre-installation Activities
4.1 | Survey Set-out and Lot size | IFC Drawings Section 304.06 | Lot size shall be the lesser of 4000sqm or a days production. Clearly mark out limits of works as per IFC Drawings and VR 304.06. ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP) | Survey Document Review Measure | Each lot | IP | Surveyor SE | Sign ITP
5 | Construction / Installation Activities
5.1 | Placement of Material | Section 304.03 Section 304.08 | Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas. Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material. Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances. | Visual and Measure | Each lot | IP | SE/Site Supervisor | Sign ITP
5.2 | Construction - Jointing | Section 304.07 | The layout of joints shall conform to the following requirements: (a)for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m; (b)transverse joints shall be offset from one layer to the next by not less than 2 m; (c)longitudinal joints shall be offset from one layer to the next by not less than 150 mm; (d)longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane. | Visual and Measure | Each lot | IP | SE/Site Supervisor | Sign ITP
5.3 | Compaction test (Frequency) | 304 .11 (b) | The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification. The Contractor may reduce the frequency of compaction testing to the minimum test frequency (One per 2 Lots). Scales A and B: 6 samples Enter: last tested lot number [free text box] | Visual | Each Lot Where applicxable | IP | SE | Sign ITP
5.4 | Post Compaction Materials Testing (Frequency) | 304.11 (c ) | SCALE B: Atterberg Limits and Grading | Visual | Each Lot Where applicxable | IP | SE | Sign ITP
5.5 | Proof Roll | Section 304.09 | All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer. | Visual | Each lot | HP | Nominated Authority | Sign ITP
5.6 | Protection of compacted layer | Section 304.09 | The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence. | Visual | Each lot | IP | SE/Site Supervisor | Sign ITP
6 | Post-construction / Post-installation Activities
6.1 | Compaction Testing (results) | Section 173 Section 304.08 Table 304.081 | During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed. Density Ratio to be based on tests performed with Modified Comp active Effort. Scale B: Subbase Layer CDR ≥ 97% Base Layer CDR ≥ 98% 6 tests per lot for lots >500sqm. If the lot is < 500sqm, then 3 tests per lot. ATTACHL: Compaction Test Results | Document Review | Each Lot Where applicxable | IP | PE | Compaction Test Rersults
6.2 | Post Compaction Materials Testing (Results) | Section 304.10 Section 304.11 RC 500.02 | Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type. 20mm Class 3: Grading 26.5mm 100% 19.0mm 95-100% 13.2mm 75-95% 9.5mm 60-90% 4.75mm 42-76% 2.36mm 28-61% 0.425mm 14-29% 0.075mm 6-14% PI between 0 to 10 20mm Class 4: Grading 26.5mm 100% 4.75mm 42-76% 0.425mm 10-28% 0.075mm 2-14% PI between 0 to 20 PI x % passing 0.425 mm sieve (max) 450 Scale C: Post compaction material testing is not required (Choose NA) | Document Review | Each Lot Where applicable | IP | PE | Compaction Test Rersults
6.3 | Survey As-Built - Width and alignment | 304.06 (a) | The width of each side of the pavement shall not be less than the specified offset width or more than 50 mm outside the specified offset width when measured at right angles from the centre line or design line. Attach: Survey Report | Document Review | Each lot | IP | PE/Surveyor | Survey Conformance Report
6.4 | Survey As-Built Thickness of Pavement Layers CARPARK PAVEMENT | 304.06 (c ) | - Subbase course shall be not less than the specified thickness by more than 15 mm. - Base Course shall be not less than the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be less than specified thickness. - The combined thickness of subbase and base courses shall be not be less than the specified thickness by more than 15 mm. Attach: Survey Report | Document Review | Each lot | IP | PE/Surveyor | Survey Conformance Report
6.5 | Survey As-Built - Surface Level MAIN ALIGNMENT ONLY | IFC Drawings Section 304.06 (b) VR 304.06 (d) Table 304.061 Table 304.062 | - No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction. - At no location shall water pond on the surface of any pavement layer. Scale B: A minimum of 40 measurements per lot Subbase: mean range +8mm to -16mm, maximum Standard Deviation of 15mm Base: mean range ±8mm, maximum Standard Deviation of 10mm Attach: Survey Report | Document Review | Each lot | IP | PE/Surveyor | Survey Conformance Report
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /