## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-194-CIV-SSB-Cement Treated Crushed Rock CTCR-Scale B
ITP Description: |  | SSB-Cement Treated Crushed Rock CTCR-Roads
Discipline (e.g. CIV/STR/RAIL: |  | 194-CIV
Revision Number: |  | 0
Revision Date: |  | 2024-08-23
ITP created by: |  | Jadan Halkett
ITP approved for use by: |  | VM
Special Notes to ConQA Team : |  | ITP for Station Street, Beaconsfield
Inspection & Test Plan - Cementitious Treated Crushed Rock Scale B
[9 empty] | Revision: | 0
[9 empty] | Date: | 2024-08-23
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 306 Oct '19 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | IFC Drawings | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | VicRoads Spec. Code of Pratice 500.02 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Non Dependent | VicRoads Spec. TN 107 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.5 | Non Dependent | VicRoads Section 815 July '16 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Submit Mix Design - Cement treated crushed rock (CTCR) mix | VicRoads Spec. Cl. 815.05 VicRoads Spec. Cl.306.04 VicRoads Spec. TN 107 VicRoads Spec. CoC 500.02 IFC Drawings | Cement treated crushed rock mixes for use on specified works can be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175. CTCR shall comply with Section 815 & 821, TN107 & CoC 500.02 Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each mix design, 4 weeks prior to placement of concrete | HP | SE & Nominated Authority | Issue to TeamBinder: VicRoads registered cement treated crushed rock mix
2.2 | Hold Point - Alternate Binder (if applicable) | VicRoads Spec. Cl.306.09(a) | If a binder other than those listed in Table 306.091 is proposed for use, laboratory test results must be produced to show that binder satisfies the required working time and strength determined in accordance with the VicRoads Test Method. Enter: Teambinder Material Approval number [free text box] | Document Review | Once per material type, prior to commencement of works | HP | SE & Nominated Authority | Issue to TeamBinder: Test Records
3 | Preliminaries-Documentation
3.1 | Check that current revision drawings are being used | Project Drawings / Drawing Register | Issued For Construction (IFC) and latest available revision used | Document review | Each Lot | HP* | SE / Site Foreman | This ITP
3.2 | Previous Layer Conformance | IFC Drawings for Previous Layer Type | Confirm previous layer (prior to CTCR layer placemen) conforms to IFC drawing and specification requirements. Check the previous fill level/survey (e.g. fill, foundation . Subgrade, base course etc) to ensure CTCR minimum thickness requirements is achieved Enter: Previous Layer Lot number [Free text box] | Document Review | Each Lot | HP* | SE | This ITP Previous Lot Number
4 | Preconstruction
4.1 | Lot Size | VicRoads Spec. Cl.306.03(b) | The maximum size for a single lot shall be considered a single layer of 4000m² A lot shall consist of a single layer of pavement material placed on the same day | Visual Measure | Each lot | IP | SE | Signed ITP Attach: Lot Map
4.2 | Survey Set-out | IFC Drawings | Survey to set out works in accordance with IFC Drawings ATTACH: Lot Map | Measure Visual | Each lot prior to commencement | IP | Surveyor SE/PE/SPE | This ITP Attach: Lot Map
5 | Construction / Installation Activities
5.1 | Delivery | VicRoads Spec. Cl.306.07 | Review delivery dockets to ensure all information required as per 306.07 (b) is recorded and meets the specificaiton requirements. Attach: Delivery Dockets | Document Review | Each Lot | IP | SE | This ITP Attach: Delivery Dockets Attach: pour records
5.2 | Placement - Transverse Joints | VicRoads Spec. Cl.306.08(a)(c) | Material should be spread to minimise number of joints In any layer, transverse joints in adjoining paver runs shall be offset by not less than 2 m Transverse joints offset from one layer to next by not less than 2 metres | Visual Measure | Each Lot | IP | SE | This ITP
5.3 | Placement - Longitudinal Joints | VicRoads Spec. Cl.306.08(a)(d)(e) | Material should be spread to minimise number of joints Longitudinal joints offset from one layer to next by not less than 150mm Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane. | Visual Measure | Each Lot | IP | SE | This ITP
5.4 | Placement - Layer Thickness | VicRoads Spec. Cl.306.11 | Compacted layer thickness should be not less than 100mm and not greater than 180mm. | Visual Measure | Each Lot | IP | SE | This ITP
5.5 | Placement - Working Time | VicRoads Spec. Cl.306.07 VicRoads Spec. Cl.306.09 Table 306.091 | Working Shall Not be more than specified for each binder: Rapid Setting (GP) - 2hrs (Oct-Apr) 3hrs (May-Sept) Medium Setting (GB) - 3hrs (Oct-Apr) 5hrs (May-Sept) Slow Setting (Slag) - 8hrs (Oct-Apr) 12hrs (May-Sept) If the ambient temperature within the period from October to April on any day is less than 15°C, the May to September maximum allowable working times may be applied. Attach: Delivery Dockets Attach: Pour record | Measure Document Review | Each Lot | IP | SE | This ITP Delivery Dockets Attach: pour records
5.6 | Water | VicRoads Spec. Cl.306.06 | Except for the purpose of curing, no water shall be added to the cementitious treated material. Water shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances. | Visual | Each Lot | IP | SE | This ITP
5.7 | Cementious binder content & UCS requirements | VicRoads Spec. 815.10 | Contractor shall carry out the UCS Testing to determine the cemenetious binder meet the minimum 7days Attach: test results | Document Review | Each Lot | IP | SE | Test report
5.8 | Compaction - Modified Compactive Effort | VicRoads Spec. Cl.306.05 VicRoads Spec. Cl.306.09(a)(b) | Moisture content at time of spreading and compactions is within +0.5% and –1.0% of optimum moisture content Scale B: No. of tests per lot shall be 3 Mean density ratio > 96% | Document review | Each Lot | IP | SE | Attach: Test Report
5.9 | Test Rolling | VicRoads Spec. Cl.306.10 Table 306.091 | Test rolling to be carried out in accordance with the requirements of Section 173 on the cementitious treated pavement subbase layer within the maximum allowable working time for the relevant binder and time of year as specified in Table 306.091. | Visual | Each Lot | HP | SE, NA | This ITP
6 | Post Construction
6.1 | Curing | Vicroads Spec 306.11 | Pavement Design Modulus of 500 MPa: The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane | Visual | Each Lot | IP | SE/PE | This ITP
6.2 | Protection | Vicroads Spec 306.11 | Pavement Design Modulus of 500 MPa: Construction or other traffic shall not use a compacted layer within 24 hours of placement without the approval of the Superintendent. | Visual | Each Lot | IP | SE/PE | This ITP
6.3 | Surface level | VicRoads Spec. Cl.306.03(c) | No point on the surface of the cementitious subbase layer shall vary by more than 8 mm from a 3 metre straight edge placed in any direction. Water shall not pond on the surface of the cementitious treated subbase | Document review | Each Lot | IP | SE/PE | This ITP
6.4 | Conformity with drawings-Width and alignment | VicRoads Spec. Cl.306.03(b) Table 306.032 | Width and Alignment: The width of pavement measured on each side of the centreline or design line shall not deviate by more than 50 mm from the designed offset when measured at a right angle. | Document Review | Each Lot | IP | SE/PE | Attach: Survey Report
6.5 | Conformity with drawings-Survey Level | VicRoads Spec. Cl.306.03(b) Table 306.032 | Scale B: Measurements per Lot: 40 Subgrade: - Mean value of all level readings to range between +5/-25 - Standard deviation of all level readings to be less than or equal to 15 Subbase: - Mean value of all level readings to range between +6/-12 - Standard deviation of all level readings to be less than or equal to 13 | Document Review | Each Lot Scale B: 40 points per lot | IP | SE/PE | Attach: Survey Report
6.6 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Team Binder. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /