## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource ID
checklist | ITP-193-CIV-SSB-Unbound Flexible Pavement-Scale B | itp |  |  |  |  | ITP-193-CIV-SSB-Unbound Flexible Pavement-Scale B Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-193-CIV- SSB-Unbound Flexible Pavement-Scale B
label | ITP Description: SSB-Unbound Flexible Pavement-Scale B
label | Discipline (e.g. CIV/STR/RAIL): 193-CIV
label | Revision Number: 0
label | Revision Date: 23/08/2024
label | ITP created by: VM
label | ITP approved for use by: VM
label | 1.1 Non Dependent
label | Reference: IFC Drawings
label | 1.2 Non Dependent
label | Reference: VicRoads Section 173 (10/9/2008)
label | 1.3 Non Dependent
label | Reference: VicRoads Section 304 (13/8/13)
label | 1.4 Non Dependent
label | Reference: VicRoads Section 801 (19/07/18)
label | 1.5 Non Dependent
label | Reference: VicRoads Section 812 (13/07/16)
section | Preliminaries-Documentation
checkpoint | 2.1 Crushed Rock Mix Design
label | REFERENCE: Section 304.03
label | ○ Section 304.05
label | ○ Section 812.04
label | ○ Table 812.121
label | ○ IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Material conformance as per Table 812.121
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: NA
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: TeamBinder Material Approval Number
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Preliminaries-Documentation
checkpoint | 3.1 Subgrade Preparation
label | REFERENCE: 304.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Prior to placing subbase material, the subgrade shall meet the requirements of Section 204.
textbox | Enter Subgrade Lot No:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Underlying layer Lot number
date | Date Completed:
section | Pre-construction / Pre-installation Activities
checkpoint | 4.1 Survey Set-out and Lot size
label | REFERENCE: IFC Drawings, Section 304.06
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Lot size shall be the lesser of 4000sqm or a days production.
label | ○ Clearly mark out limits of works as per IFC Drawings and VR 304.06.
label | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Survey, Document Review, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
section | Construction / Installation Activities
checkpoint | 5.1 Placement of Material
label | REFERENCE: Section 304.03, Section 304.08
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas.
label | ○ Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material.
label | ○ Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual and Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
checkpoint | 5.2 Construction - Jointing
label | REFERENCE: Section 304.07
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The layout of joints shall conform to the following requirements:
label | (a) for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
label | (b) transverse joints shall be offset from one layer to the next by not less than 2 m;
label | (c) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
label | (d) longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual and Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
checkpoint | 5.3 Compaction test (Frequency)
label | REFERENCE: 304 .11 (b)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification.
label | ○ The Contractor may reduce the frequency of compaction testing to the minimum test frequency (One per 2 Lots).
label | ○ Scales A and B: 6 samples
textbox | Enter: last tested lot number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot Where applicxable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
checkpoint | 5.4 Post Compaction Materials Testing (Frequency)
label | REFERENCE: 304.11 (c)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: SCALE B: Atterberg Limits and Grading
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot Where applicxable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
checkpoint | 5.5 Proof Roll
label | REFERENCE: Section 304.09
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 Protection of compacted layer
label | REFERENCE: Section 304.09
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 6.1 Compaction Testing (results)
label | REFERENCE: Section 173, Section 304.08, Table 304.081
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed.
label | ○ Density Ratio to be based on tests performed with Modified Comp active Effort.
label | Scale B:
label | – Subbase Layer CDR ≥ 97%
label | – Base Layer CDR ≥ 98%
label | ○ 6 tests per lot for lots >500sqm. If the lot is < 500sqm, then 3 tests per lot.
label | ATTACH: Compaction Test Results
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot Where applicxable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Compaction Test Rersults
date | Date Completed:
checkpoint | 6.2 Post Compaction Materials Testing (Results)
label | REFERENCE: Section 304.10, Section 304.11, RC 500.02
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type.
label | 20mm Class 3: Grading
label | ○ 26.5mm 100%
label | ○ 19.0mm 95-100%
label | ○ 13.2mm 75-95%
label | ○ 9.5mm 60-90%
label | ○ 4.75mm 42-76%
label | ○ 2.36mm 28-61%
label | ○ 0.425mm 14-29%
label | ○ 0.075mm 6-14%
label | ○ PI between 0 to 10
label | 20mm Class 4: Grading
label | ○ 26.5mm 100%
label | ○ 4.75mm 42-76%
label | ○ 0.425mm 10-28%
label | ○ 0.075mm 2-14%
label | ○ PI between 0 to 20
label | ○ PI x % passing 0.425 mm sieve (max) 450
label | Scale C: Post compaction material testing is not required (Choose NA)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot Where applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Compaction Test Rersults
date | Date Completed:
checkpoint | 6.3 Survey As-Built - Width and alignment
label | REFERENCE: 304.06 (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The width of each side of the pavement shall not be less than the specified offset width or more than 50 mm outside the specified offset width when measured at right angles from the centre line or design line.
label | Attach: Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Surveyor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Survey Conformance Report
date | Date Completed:
checkpoint | 6.4 Survey As-Built Thickness of Pavement Layers (CARPARK PAVEMENT)
label | REFERENCE: 304.06 (c)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: - Subbase course shall be not less than the specified thickness by more than 15 mm.
label | ○ Base Course shall be not less than the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be less than specified thickness.
label | ○ The combined thickness of subbase and base courses shall be not be less than the specified thickness by more than 15 mm.
label | Attach: Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Surveyor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Survey Conformance Report
date | Date Completed:
checkpoint | 6.5 Survey As-Built - Surface Level (MAIN ALIGNMENT ONLY)
label | REFERENCE: IFC Drawings
label | ○ Section 304.06 (b)
label | ○ VR 304.06 (d)
label | ○ Table 304.061
label | ○ Table 304.062
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: - No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction.
label | ○ At no location shall water pond on the surface of any pavement layer.
label | ○ Scale B: A minimum of 40 measurements per lot
label | ○ Subbase: mean range +8mm to -16mm, maximum Standard Deviation of 15mm
label | ○ Base: mean range ±8mm, maximum Standard Deviation of 10mm
label | Attach: Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Surveyor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Survey Conformance Report
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP
checklist | ITP-194-CIV-SSB-Cement Treated Crushed Rock CTCR-Scale B | itp |  |  |  |  | ITP-194-CIV-SSB-Cement Treated Crushed Rock CTCR-Scale B Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-194-CIV-SSB-Cement Treated Crushed Rock CTCR-Scale B
label | ITP Description: SSB-Cement Treated Crushed Rock CTCR-Roads
label | Discipline (e.g. CIV/STR/RAIL): 194-CIV
label | Revision Number: 0
label | Revision Date: 23/08/2024
label | ITP created by: Jadan Halkett
label | ITP approved for use by: VM
label | 1.1 Non Dependent
label | Reference: VicRoads Section 306 Oct '19
label | 1.2 Non Dependent
label | Reference: IFC Drawings
label | 1.3 Non Dependent
label | Reference: VicRoads Spec. Code of Pratice 500.02
label | 1.4 Non Dependent
label | Reference: VicRoads Spec. TN 107
label | 1.5 Non Dependent
label | Reference: VicRoads Section 815 July '16
section | Preliminaries - Materials
checkpoint | 2.1 Submit Mix Design - Cement treated crushed rock (CTCR) mix
label | REFERENCE: VicRoads Spec. Cl. 815.05
label | ○ VicRoads Spec. Cl.306.04
label | ○ VicRoads Spec. TN 107
label | ○ VicRoads Spec. CoC 500.02
label | ○ IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Cement treated crushed rock mixes for use on specified works can be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
label | ○ CTCR shall comply with Section 815 & 821, TN107 & CoC 500.02
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE & Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Issue to TeamBinder: VicRoads registered cement treated crushed rock mix
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Hold Point - Alternate Binder (if applicable)
label | REFERENCE: VicRoads Spec. Cl.306.09(a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: If a binder other than those listed in Table 306.091 is proposed for use, laboratory test results must be produced to show that binder satisfies the required working time and strength determined in accordance with the VicRoads Test Method. Enter: Teambinder Material Approval number [free text box]
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once per material type, prior to commencement of works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE & Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Issue to TeamBinder: Test Records
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Preliminaries-Documentation
checkpoint | 3.1 Check that current revision drawings are being used
label | REFERENCE: Project Drawings / Drawing Register
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE / Site Foreman
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.2 Previous Layer Conformance
label | REFERENCE: IFC Drawings for Previous Layer Type
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Confirm previous layer (prior to CTCR layer placemen) conforms to IFC drawing and specification requirements.
label | ○ Check the previous fill level/survey (e.g. fill, foundation . Subgrade, base course etc) to ensure CTCR minimum thickness requirements is achieved
textbox | Enter: Previous Layer Lot number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, Previous Lot Number
date | Date Completed:
section | Preconstruction
checkpoint | 4.1 Lot Size
label | REFERENCE: VicRoads Spec. Cl.306.03(b)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The maximum size for a single lot shall be considered a single layer of 4000m²
label | ○ A lot shall consist of a single layer of pavement material placed on the same day
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Signed ITP
label | ○ Attach: Lot Map
date | Date Completed:
checkpoint | 4.2 Survey Set-out
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Survey to set out works in accordance with IFC Drawings
label | ATTACH: Lot Map
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot prior to commencement
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
label | ○ Attach: Lot Map
date | Date Completed:
section | Construction / Installation Activities
checkpoint | 5.1 Delivery
label | REFERENCE: VicRoads Spec. Cl.306.07
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Review delivery dockets to ensure all information required as per 306.07 (b) is recorded and meets the specificaiton requirements.
label | Attach: Delivery Dockets
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
label | ○ Attach: Delivery Dockets
label | ○ Attach: pour records
date | Date Completed:
checkpoint | 5.2 Placement - Transverse Joints
label | REFERENCE: VicRoads Spec. Cl.306.08(a)(c)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Material should be spread to minimise number of joints
label | ○ In any layer, transverse joints in adjoining paver runs shall be offset by not less than 2 m
label | ○ Transverse joints offset from one layer to next by not less than 2 metres
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.3 Placement - Longitudinal Joints
label | REFERENCE: VicRoads Spec. Cl.306.08(a)(d)(e)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Material should be spread to minimise number of joints
label | ○ Longitudinal joints offset from one layer to next by not less than 150mm
label | ○ Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.4 Placement - Layer Thickness
label | REFERENCE: VicRoads Spec. Cl.306.11
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Compacted layer thickness should be not less than 100mm and not greater than 180mm.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.5 Placement - Working Time
label | REFERENCE: VicRoads Spec. Cl.306.07, VicRoads Spec. Cl.306.09, Table 306.091
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Working Shall Not be more than specified for each binder:
label | ○ Rapid Setting (GP) - 2hrs (Oct-Apr) 3hrs (May-Sept)
label | ○ Medium Setting (GB) - 3hrs (Oct-Apr) 5hrs (May-Sept)
label | ○ Slow Setting (Slag) - 8hrs (Oct-Apr) 12hrs (May-Sept)
label | ○ If the ambient temperature within the period from October to April on any day is less than 15°C, the May to September maximum allowable working times may be applied.
label | Attach: Delivery Dockets
label | Attach: Pour record
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, Delivery Dockets
label | ○ Attach: pour records
date | Date Completed:
checkpoint | 5.6 Water
label | REFERENCE: VicRoads Spec. Cl.306.06
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Except for the purpose of curing, no water shall be added to the cementitious treated material.
label | ○ Water shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.7 Cementious binder content & UCS requirements
label | REFERENCE: VicRoads Spec. 815.10
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Contractor shall carry out the UCS Testing to determine the cemenetious binder meet the minimum 7 days
label | Attach: test results
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Test report
date | Date Completed:
checkpoint | 5.8 Compaction - Modified Compactive Effort
label | REFERENCE: VicRoads Spec. Cl.306.05, VicRoads Spec. Cl.306.09(a)(b)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Moisture content at time of spreading and compactions is within +0.5% and –1.0% of optimum moisture content
label | Scale B:
label | ○ No. of tests per lot shall be 3
label | ○ Mean density ratio > 96%
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Attach: Test Report
date | Date Completed:
checkpoint | 5.9 Test Rolling
label | REFERENCE: VicRoads Spec. Cl.306.10, Table 306.091
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Test rolling to be carried out in accordance with the requirements of Section 173 on the cementitious treated pavement subbase layer within the maximum allowable working time for the relevant binder and time of year as specified in Table 306.091.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE, NA
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Post Construction
checkpoint | 6.1 Curing
label | REFERENCE: Vicroads Spec 306.11
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Pavement Design Modulus of 500 MPa: The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.2 Protection
label | REFERENCE: Vicroads Spec 306.11
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Pavement Design Modulus of 500 MPa: Construction or other traffic shall not use a compacted layer within 24 hours of placement without the approval of the Superintendent.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.3 Surface level
label | REFERENCE: VicRoads Spec. Cl.306.03(c)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: No point on the surface of the cementitious subbase layer shall vary by more than 8 mm from a 3 metre straight edge placed in any direction. Water shall not pond on the surface of the cementitious treated subbase
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.4 Conformity with drawings-Width and alignment
label | REFERENCE: VicRoads Spec. Cl.306.03(b), Table 306.032
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Width and Alignment: The width of pavement measured on each side of the centreline or design line shall not deviate by more than 50 mm from the designed offset when measured at a right angle.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Attach: Survey Report
date | Date Completed:
checkpoint | 6.5 Conformity with drawings-Survey Level
label | REFERENCE: VicRoads Spec. Cl.306.03(b), Table 306.032
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Scale B: Measurements per Lot: 40
label | Subgrade:
label | ○ Mean value of all level readings to range between +5/-25
label | ○ Standard deviation of all level readings to be less than or equal to 15
label | Subbase:
label | ○ Mean value of all level readings to range between +6/-12
label | ○ Standard deviation of all level readings to be less than or equal to 13
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot, Scale B: 40 points per lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Attach: Survey Report
date | Date Completed:
checkpoint | 6.6 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Team Binder.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP