## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-156-STR-SSB-Precast Barriers and Kerbs Installation | itp |  |  |  |  | ITP-156-STR-SSB-Precast Barriers and Kerbs Installation Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-156-STR-SSB-Precast Barriers and Kerbs Installation
label | ITP Description: SSB-Precast Barriers and Kerbs Installation
label | ITP Number: 156
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 1/05/2024
label | ITP created by: Justin Kreinberg
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: VicRoads Section 610 Feb 2020
label | 1.2 Non Dependent
label | Reference: VicRoads Section 620 May 2009
label | 1.3 Non Dependent
label | Reference: VicRoads Section 630 October 2013
label | 1.4 Non Dependent
label | Reference: VicRoads Section 670 October 2013
label | 1.5 Non Dependent
label | Reference: VicRoads Section 671 October 2013
section | Preliminaries Materials
checkpoint | 2.1 Grout
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Details of the grout to be placed between the precast elements to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, for each product
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Preliminaries - Documents
checkpoint | 3.1 Precast Elements
label | REFERENCE: IFC Drawings VR 610
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | i. Certificate of Compliance / Birth Certificate
label | ii. Compressive strength test results
label | iii. Precast Lifting Design
label | iv. Pre-pour check sheet / ITP
label | v. Post-pour check sheet / ITP
label | vi. Covermeter check record
label | vii. Record of dimensional measurements
label | ○ These documents are typically stored in a MDR Lot in Team Binder.
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.2 Bridge Deck / Foundation Compressive Strength
label | REFERENCE: 671.03
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: For Preccast elements installed on bridge deck, check that the 7 day compressive strength as shown on the IFC Drawings has been achieved.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each installation location
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Pre-installation Activities
checkpoint | 4.1 Survey Set-out of Precast Elements
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances.
label | ○ Where anchor bolts are cast in to the concrete, ensure that these are within tolerance.
label | ○ If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
label | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.2 Bearing Shims or Bearing Strip Placement
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Place the bearing shims, strip or variety of shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
label | Note: If the precast elements are to be grouted, the minimum and maximum thicknesses of the bearing will determine the product for the grouting activities (usually 10mm min.)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, each installation location
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.3 Bitumen Board and Ableflex placement
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Adhere any bitumen impregnated fibre-board and ableflex into the positions shown on the IFC Drawings and where grout or concrete ingress will affect the end use (such as around conduits).
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, each installation location
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Installation Activities
checkpoint | 5.1 Precast Handling
label | REFERENCE: 620.07 Crane Lift Study
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.2 Precast Placement
label | REFERENCE: IFC Drawings VR 670.05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Precast elements shall be placed onto the bearing shims and not released from the crane until sufficiently braced or restrained by bolted connection, in accordance with the approved temporary works design and/or IFC drawings.
label | Adjustments to be made to achieve following tolerances:
label | (a) Departure from plan position: 25 mm
label | (b) Departure from alignment: 5 mm
label | (c) Irregularities in alignment: 3 mm in 3 m
label | (d) Variation in joint gap width: 3 mm
label | (e) Verticality of posts, panels, balusters and openings: ±2 mm
label | ○ The nominal gap between elements is as per the IFC Drawings.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.3 Hold-down Bracket Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
label | REFERENCE: IFC Drawings 630.20 (a) & (c) AS5131 Clause 8.3
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Place washers and nuts onto the embedded thread as detailed on the IFC Drawings.
label | ○ Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
label | ○ Tighten with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
label | ○ Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, each bolted connection
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.4 Precast Traceability
label | REFERENCE: 620.09
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
label | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-installation Activities
checkpoint | 6.1 Flowable Grout Pour
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Grout shall be poured at connections between elements and/or in the gap between the bottom of the precast element and top of the bridge deck/foundation following full sealant application.
label | Complete: Grout Pedestals & Bearings ITP
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Grout Pedestals & Bearings ITP
date | Date Completed:
checkpoint | 6.2 As-built Survey
label | REFERENCE: IFC Drawings VR 670.05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per VR 670.05
label | (a) Departure from plan position: 25 mm
label | (b) Departure from alignment: 5 mm
label | (c) Irregularities in alignment: 3 mm in 3 m
label | (d) Variation in joint gap width 3 mm
label | (e) Verticality of posts, panels, balusters and openings: ±2 mm
label | Attach: Survey As-builts / Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP