## Sheet1
15.01 | Rock Armour Grading | T+T NAL Recovery Specifications: 10.4.3.1.1 | Rock armour material shall be well graded as indicated on the drawings. | Poorly graded or gap graded armour rock shall not be permitted except as approved by the Engineer. | For every section of rock armour | Rock Specifications | HOLD | External | JFC | REVIEW | TCHAR(AMP)T | 15.01 - Rock Armour Grading | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 10.4.3.1.1 | SPECIFICATION DETAIL SUMMARY: Rock armour material shall be well graded as indicated on the drawings. | ACCEPTANCE CRITERIA: Poorly graded or gap graded armour rock shall not be permitted except as approved by the Engineer. | TEST SPEC AND FREQUENCY: For every section of rock armour | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Rock Specifications | HOLD / WITNESS: HOLD | INTERNAL / EXTERNAL: External | PS3 OWNER: JFC | HOLD / WITNESS: REVIEW | PS4 OWNER SIGN OFF: TCHAR(AMP)T | 15.01 - Rock Armour Grading
15.02 | Rock Armour - Placement | T+T NAL Recovery Specifications: 10.4.4.4 | The placement method of armour and underlayers directly on geotextile filter fabric shall be approved by the Engineer prior to placement | Engineer to approve methodology | Prior to rock armour placement | Method Statement, Written Confirmation of Engineer’s Approval | HOLD | External | JFC | HOLD | TCHAR(AMP)T | 15.02 - Rock Armour - Placement | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 10.4.4.4 | SPECIFICATION DETAIL SUMMARY: The placement method of armour and underlayers directly on geotextile filter fabric shall be approved by the Engineer prior to placement | ACCEPTANCE CRITERIA: Engineer to approve methodology | TEST SPEC AND FREQUENCY: Prior to rock armour placement | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Method Statement, Written Confirmation of Engineer’s Approval | HOLD / WITNESS: HOLD | INTERNAL / EXTERNAL: External | PS3 OWNER: JFC | HOLD / WITNESS: HOLD | PS4 OWNER SIGN OFF: TCHAR(AMP)T | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 10.4.3.1.1
15.03 | Tolerances | T+T NAL Recovery Specifications: 10.4.5.2 | Rock materials must be placed according to the drawings' levels, dimensions, and slopes, and the surface profile must be measured using the specified tolerances: - Subgrade levels -0.1 m to +0.1 m - Armour underlayer thickness (average per profile): -0.1 m to +0.2 m - Armour rock thickness (average per profile): -0.1 m to +0.5 m | Tolerances are adhered to | For every section of rock material placed | QA Checksheet(s), Photos | HOLD | External | JFC | REVIEW | TCHAR(AMP)T | 15.03 - Tolerances | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 10.4.5.2 | SPECIFICATION DETAIL SUMMARY: Rock materials must be placed according to the drawings' levels, dimensions, and slopes, and the surface profile must be measured using the specified tolerances: - Subgrade levels -0.1 m to +0.1 m - Armour underlayer thickness (average per profile): -0.1 m to +0.2 m - Armour rock thickness (average per profile): -0.1 m to +0.5 m | ACCEPTANCE CRITERIA: Tolerances are adhered to | TEST SPEC AND FREQUENCY: For every section of rock material placed | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: QA Checksheet(s), Photos | HOLD / WITNESS: HOLD | INTERNAL / EXTERNAL: External | PS3 OWNER: JFC | HOLD / WITNESS: REVIEW | PS4 OWNER SIGN OFF: TCHAR(AMP)T | SPECIFICATION DETAIL SUMMARY: Rock armour material shall be well graded as indicated on the drawings.
ACCEPTANCE CRITERIA: Poorly graded or gap graded armour rock shall not be permitted except as approved by the Engineer.
TEST SPEC AND FREQUENCY: For every section of rock armour
CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Rock Specifications
HOLD / WITNESS: HOLD
INTERNAL / EXTERNAL: External
PS3 OWNER: JFC
HOLD / WITNESS: REVIEW
PS4 OWNER SIGN OFF: TCHAR(AMP)T
15.02 - Rock Armour - Placement
DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 10.4.4.4
SPECIFICATION DETAIL SUMMARY: The placement method of armour and underlayers directly on geotextile filter fabric shall be approved by the Engineer prior to placement
ACCEPTANCE CRITERIA: Engineer to approve methodology
TEST SPEC AND FREQUENCY: Prior to rock armour placement
CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Method Statement, Written Confirmation of Engineer’s Approval
HOLD / WITNESS: HOLD
INTERNAL / EXTERNAL: External
PS3 OWNER: JFC
HOLD / WITNESS: HOLD
PS4 OWNER SIGN OFF: TCHAR(AMP)T
15.03 - Tolerances
DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 10.4.5.2
SPECIFICATION DETAIL SUMMARY: Rock materials must be placed according to the drawings' levels, dimensions, and slopes, and the surface profile must be measured using the specified tolerances: - Subgrade levels -0.1 m to +0.1 m - Armour underlayer thickness (average per profile): -0.1 m to +0.2 m - Armour rock thickness (average per profile): -0.1 m to +0.5 m
ACCEPTANCE CRITERIA: Tolerances are adhered to
TEST SPEC AND FREQUENCY: For every section of rock material placed
CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: QA Checksheet(s), Photos
HOLD / WITNESS: HOLD
INTERNAL / EXTERNAL: External
PS3 OWNER: JFC
HOLD / WITNESS: REVIEW
PS4 OWNER SIGN OFF: TCHAR(AMP)T